## Slide 1
PMG 202
Project Planning
Prepared by Dr. Maryam ZORGUI
Lecture 9
Monitoring
&
Controlling
PART II :
Execution and Control Phases

## Slide 2: In the previous lessons…
The Project Eecution phase is the third phase in the Project Life Cycle; and the most demanding. In the project Execution Phase:
The team carries out all the planned activities, constructs deliverables, and presents them to project stakeholders
The project manager changes to performing and supervising all activities to create deliverables as outlined in the project plan
He needs to continuously track the project’s progress and ensure that the milestones and deliverables stick to the project schedule
The Project Manger needs to step back a bit and let your team carry out the project plan

## Slide 3: In the previous lessons…
The execution phase is where all the action happens and the plans start materializing. There will be changes to the scope and the documentation will change as a result.
Project deliverables
Change requests
Performance data
Issue log
Documentation updates
Lecture 9

## Slide 4: In the previous lessons…
In essence, the project manager has three main objectives during the execution phase:
Managing people
Managing processes
Managing communication
The benefits of a well-executed project are threefold:
The project can be completed on time and budget
Team morale can be maintained
Stakeholders are satisfied with overall project progress
Lecture 9

## Slide 5: Outcomes of the lesson
In this lesson, we’ll:
Learn the steps, methodology, and processes that lead to successful Project Monitoring and Controlling Phase.
Find Project Monitoring and Controlling Steps and Processes, the helpful tools to support your Project’s next success, and the importance of both Monitoring and Controlling along all the phases of the Project Life Cycle .
Lecture 9

## Slide 6: Syllabus .
III- Reports That Every Project Controls Team Should Have
II- Importance of the Key Performance Indicators
I- the Project Monitoring and Controlling Phase
VI- What are the roles of the Project Manager during the Project Monitoring and Control Phase?
V- Project Monitoring and Control Process: 10 Key Activities
Lecture 9

## Slide 7: I- The Project Monitoring and Controlling Phase
Based on the progress of the Project, Changes, and Deliverables, the Initiating Processes can be triggered to review the Project Charter.
The Planning Processes can be triggered to revise Planning.
The Executing Processes can be triggered to repair defects or implement approved changes.
Lastly, if all Objectives of the Project are met and Results are as planned, Closing Processes are triggered.
Lecture 9

## Slide 8: I- The Project Monitoring and Controlling Phase
I-1- Definition
Once the Project Execution Phase gets underway, the Project Monitoring and Controlling Phase also kicks in. This parallel phase keeps the Project on track and aligned with its initial purpose, while allowing Teams to correct course where necessary.
In the Project Life Cycle, the Project Monitoring and Control Phase happens in tandem with the Execution Phase .
This Project Monitoring and Controlling involves actively reviewing the status of your project as it proceeds, evaluating potential obstacles, and implementing necessary changes. .
Lecture 9

## Slide 9: I- The Project Monitoring and Controlling Phase
Monitoring refers to the process of watching, keeping track of and gathering data about performance.
Controlling on the other hand refers to the process of actively exercising power over, guiding and supervising behaviour, tasks and activities in a Project or organisation.
Controlling can include setting up a system, procedures and policies to guide and regulate work processes.
Lecture 9

## Slide 10: I- The Project Monitoring and Controlling Phase
I-2- Project Monitoring
I-2-1- Definition of Project Monitoring
Project Monitoring is defined as a process which is performed to track the progress of Project eExecution so that potential problems can be identified well in time for the taking of the corrective actions for the purpose of controlling the execution of the Project.
It is a continuing function during Project implementation which provides management of an ongoing development intervention with indications of the extent of progress and achievement of objectives and progress in the use of allocated funds.
It provides information and ensures the use of such information by management to assess Project effects – both intentional and unintentional – and their impact. It aims at determining whether or not the intended Project Goals and Objectives are being on the track.
Lecture 9

## Slide 11: I- The Project Monitoring and Controlling Phase
It focuses on reviewing of progress against achieving of goals. In other words, monitoring is not only concerned with the taking of the actions but is also concerned with making the progress towards achievement of the results. In the more limited approach, monitoring can focus on tracking project with regards to the use of the resources. In the broader approach, monitoring also involves tracking strategies and actions being taken by management, and figuring out what new strategies and actions need to be taken to ensure progress towards the project objectives.
Lecture 9

## Slide 12: I- The Project Monitoring and Controlling Phase
I-2-2- General aspects of project monitoring
Project monitoring provides opportunities at regular predetermined points to validate the logical progress of the project, its activities and their implementation and to make adjustments as needed.
It is very difficult to evaluate project progress which is not well designed and which is not systematically monitored.
Project monitoring provides records of activities and results, and signals problems to be remedied along the way.
Without effective monitoring it is normally impossible to judge if work is going in the right direction, whether progress and success can be claimed and how further efforts can be improved.
Lecture 9

## Slide 13: I- The Project Monitoring and Controlling Phase
I-2-3- Project monitoring activities
Project monitoring is carried out
(i) measuring progress of project activities against established schedules and indicators of success,
(ii) identifying factors affecting the progress of project activities,
(iii) measuring the response of the decision taken on the project activities and its effect on the progress of project implementation, and
(iv) to minimize the risks of project failure.
Lecture 9

## Slide 14
Lecture 9

## Slide 15: I- The Project Monitoring and Controlling Phase
Project monitoring serves several purposes.
It brings into focus the problems in the implementation of the projects which are brewing up and which need solutions for the smooth progress of the project.
Project monitoring always relate to pre-identified results in the development plan of the project.
It is an essential management tool to support the project and helps in the management commitment to accountability for results and effective utilization of resources entrusted to it.
Lecture 9

## Slide 16: I- The Project Monitoring and Controlling Phase
I-3- Project Controls
I-3-1- Definition of project controlling
Project Controls is a process that encompasses the Resources, Procedures, and Tools for the Planning, Monitoring, and Controlling of all phases of the capital Project Lifecycle.
It includes estimating, cost and schedule management, risk management, change management, earned value progressing, and forecasting.
Successful performance of a project depends on appropriate planning.
Lecture 9

## Slide 17: I- The Project Monitoring and Controlling Phase
I-3-2- General aspects of project conTrolling
The Execution of a Project is based on a robust Project Plan and can only be achieved through an effective Cost and Schedule Control methodology.
The Development of a Suitable Project Control System is an important part of the overall Project Management effort and supports the achievement of Project Objectives.
It has been proven time and again that project performance can be improved if dedicated project controls systems are in place. Good project control practices can result in more predictable cost and schedule outcomes.
Lecture 9

## Slide 18: I- The Project Monitoring and Controlling Phase
I-3-3- Project controlling activities
Aligning projects with portfolio/organization goals and objectives
Developing a work-breakdown structure (WBS)
Collaborating on initial project schedules
Developing a risk management plan
Project budgeting and forecasting
Controlling project costs
Feedback and reporting
Optimizing project strategies to enable better outcomes in the future
Lecture 9

## Slide 19
I-3-4- Processes That Define Project Controls

## Slide 20: II- Importance of the Key Performance Indicators
During your Planning Phase, you may have established a series of Checkpoints or Milestones for your Project. Alternatively, you might have set Goals of completing a specific number of Deliverables per day, week, or month. Quantifiable measures like these, which are used to evaluate the success of your Project, are called Key Performance Indicators (KPIs).
During the Project Monitoring and Controlling Phase, keeping tabs on KPIs is essential to ensure your Team is on the right track.
One way to keep your entire Team up to date is to set up automated status reports that go out to all interested parties.

## Slide 21: II- Importance of the Key Performance Indicators
II-1- Key Performance Indicators Definition
KPIs are quantifiable measurements that reflect the critical success factors of a business.
Key Drivers that have a major impact on the performance of the business.
A handful of numbers that give the owner an “at a glance” view of the business.
Keep their finger on the pulse of the business.
Identify hot spots that need attention.
Act quickly to drive the business forward.

## Slide 22: II- Importance of the Key Performance Indicators
Key Performance Indicators define:
factors the institution needs to benchmark and monitor.
assessment techniques provide the mechanism for measuring and evaluating the defined factors to evaluate progress or impact.
KPIs specify what is measured and assessment techniques detail how and when it will be measured.
KPI is a measure used to define and evaluate how successful an organization is.
Typically is expressed in terms of making progress towards its long-term organizational goals.
KPI incorporates information on the sources, calculations and definitions for each measure and sets out the timetable for submission of monthly data.

## Slide 23: II- Importance of the Key Performance Indicators
KPIs assist Project to define and measure progress toward organisational goals and objectives.
Once an organisation has analysed its mission and defined its Goals, it needs to measure progress towards those goals.
KPIs provide a measurement tool.
KPIs assist a Project to measure that it is “on track” – most often, that it is working towards and attaining a beneficial outcome or improvement. In many cases, KPIs are used in projects and to measure service delivery.

## Slide 24: II- Importance of the Key Performance Indicators
II-2- Key Performance Indicators Characteristics
Many KPI characteristics are identified in the literature.
A KPI does not need to satisfy all of these characteristics to be useful to the organisation and characteristics may overlap.
A KPI should be:
*relevant to and consistent with the specific organisation’s vision, strategy and objectives (see Figure 2);
*focused on organisation wide strategic value rather than non-critical local business outcomes – selection of the wrong KPI can result in counterproductive behaviour and sub optimised outcomes;
*representative – appropriate to the organisation together with its operational performance;

## Slide 25: II- Importance of the Key Performance Indicators
*realistic – fits into the organisation’s constraints and cost effective;
* specific – clear and focused to avoid misinterpretation or ambiguity;
attainable – requires targets to be set that are observable, achievable, reasonable and credible under expected conditions as well as independently validated;
measurable – can be quantified/measured and may be either quantitative or qualitative;
used to identify trends – changes are infrequent, may be compared to other data over a reasonably long time and trends can be identified;

## Slide 26: II- Importance of the Key Performance Indicators
timely – achievable within the given timeframe;
understood – individuals and groups know how their behaviours and activities contribute to overall organisational goals;
agreed – all contributors agree and share responsibility within the organisation;
reported – regular reports are made available to all stakeholders and contributors;
governed – accountability and responsibility is defined and understood; and
resourced – the program is cost effective and adequately resourced throughout its lifetime

## Slide 27: II- Importance of the Key Performance Indicators
II-3- Why are KPIs important?

## Slide 28: III- Reports That Every Project Controls Team Should Have
The Project Monitoring and Control Process aims at tracking and reviewing the Project and is undertaken from the Initiation of the Project to its Closure.
Various activities performed during this process assess if the Project is being run in accordance with the established Plan.
This process is based on the PMBOK Framework. This means it is a proven practice that is applied widely in Project Management.
Monitoring and Controlling a Project facilitate identification of deviations that pose a threat to successful completion of the Project.
If deviations are not identified and addressed, they result in unplanned and undesired project outcomes. Thus, this process ensures that abnormalities are detected and acted upon early on to prevent their escalation, which may lead to major and costly issues.
Lecture 9

## Slide 29: III- Reports That Every Project Controls Team Should Have
When unplanned issues are eliminated, there is an assurance that the Project will be completed on time and that envisioned results will be achieved.
There are several methods that are applied by Project Managers together with other key Stakeholders to evaluate the Project Performance.
Monitoring and Evaluation consist one of these approaches and it should be undertaken regularly at different Project phases.
Doing that will make sure that issues that arise are recognized and addressed on time.
Lecture 9

## Slide 30: III- Reports That Every Project Controls Team Should Have
Too often, Project Controls are perceived as “back office analytics,” without a clear understanding of how it directly relates back to
Project Performance and ROI (Return On Investment).
This makes it difficult for Project Teams to grab the attention of management.
However, when recommendations are backed by facts and actionable data, teams are more likely to embrace them. This is why it’s essential to build smart, automated and regular reports into the process.
Here are a few reports that help to socialize project controls concepts with project teams and allow everyone to align on the best path forward:
Notes: Return on investment, or ROI, is a mathematical formula that investors can use to evaluate their investments and judge how well a particular investment has performed compared to others. An ROI calculation is sometimes used with other approaches to develop a business case for a given proposal. The overall ROI for an enterprise is used as a way to grade how well a company is managed.

## Slide 31: III- Reports That Every Project Controls Team Should Have

## Slide 32: IV- What are the roles of the Project Manager during the Project Monitoring and Control Phase?
The role of the Project Manager in the Project Monitoring and Control Phase can be summarized briefly in three items:

## Slide 34: V- Project Monitoring and Control Process: 10 Key Activities
Project Monitoring and Control processes help to check whether the project is going as well as planned.
These Project Monitoring and Control processes identify if there are any deviations in actual results from the planned values.
For instance, whether the Project is under Budget, whether the Project will be finished on time, whether quality Requirements are met etc. are all checked and evaluated with the help of Project Monitoring and Control Processes.
The following activities are performed during Project Monitoring and Control phase:

## Slide 35
Activities performed during
Project Monitoring and Control Phase