جامعة ميدأوشن

كلية الإدارة

قسم/تخصص إدارة المشاريع

أثر دمج الذكاء الاصطناعي في مهام وأدوات مكاتب إدارة المشاريع في قطاع الإنشاءات: التحديات والفرص

إعداد

الطالب/ عمرو سامي بن صديق

الرقم الجامعي/ 243001834

إشراف

د. الفيصل عبد الحميد                                               د. فايز جراد

العام الدراسي

2024

Midocean University

School of Management

Department/Specialty Project Management

Effect of Integrating Artificial Intelligence into Project Management Office Tasks and Tools in Construction Sector  - Challenges and Opportunities

Prepared By

Student \Amro Sami BinSiddik

Academic No.\ 243001834

Supervisors

Dr. Al-Faisal Abdel Hamid                                                 Dr. Fayez Jarad

Academic Year:

2024

شكر وتقدير

الشكر لله أولا وأخيرا على ما وهبنا من نعم ودفع عنا من نقم

أخص بالشكر والدي ووالدتي على كل ما قدموه وبذلوه، أتقدم بالشكر أيضاً لعائلتي الصغيرة زوجتي وأبنائي على كل الدعم، إخوتي وأصدقائي لكم مني كل الشكر والعرفان.

كما أتقدم بالشكر والعرفان لجامعة ميدأوشن على إتاحة الفرصة لدارسة مرحلة الماجستير والتي كانت بمثابة حلم يلوح في الأفق، الشكر لدكاترة المواد الذين شاركونا هذه الرحلة ولم يبخلوا علينا بالعلم والمعرفة والنصيحة.

أخص بالشكر أيضا الدكاترة مشرفي البحث على حرصهم وسعة صدورهم وكأنهم يحملون على عاتقهم رفعة هذه الأمة.

أتقدم بالشكر والعرفان لجميع من ساندني ودعمني في هذه الأوقات الصعبة.

الباحث

Copyright Notice

Copyright is owned by Midocean University. All materials and content within this research/study are the property of the university and may not be used, re published or distributed with prior permission form Midocean University.

Index of Contents:

List of Schedules:

Index of Shapes:

Abstract :Abstract

Chapter One

# Introduction:

In recent decades, project management has been going through significant transformation. Project management evolved from been informal and reactive practices to structured, well-established frameworks, methodologies, tools, and organizational frameworks (Shamim, 2024). Project Management Office (PMO), plays a crucial role in standardizing project practices, allocating resources, enforcing governance, to make sure that projects are align with organizational goals. Recently, PMOs become a strategic hubs that provide consistency, efficiency, and excellence during the project delivery (Vukadinović & Fabac, 2022).

As the Fourth Industrial Revolution continues to develop and also digital technologies, new technology has emerged rapidly, which includes Artificial Intelligence (AI). AI technologies started to offer the ability to process massive amounts of data, detect patterns, make predictions, automate repetitive tasks, and simulate complex human decision-making using machine learning (ML), natural language processing (NLP), computer vision (CV), big data analytics, internet of things (IoT), robotics, and expert systems. These technologies are already reshaping how businesses operate and deliver value (Rampini & Cecconi, 2022; Silitonga & Jin, 2024).

PMOs, during evolutions of it provided support for organizations on process discipline, standardization, and oversight within project management practices. The integration of AI within PMO daily functions and tools can presents a complex framework of opportunities and challenges. However, the incorporation of AI has the potential to fundamentally transform the execution of project activities, the decision-making methodology, and the generation of value within organizations. Academic exploration of the implications associated with AI integration is needed, particularly in terms of process innovation, decision-making enhancement, and overall organizational impact. The use of AI is not considered like technological upgrade, but a fundamental shift to how PMOs can contribute to project success and achieve business strategy (Ibadildin et al., 2025; Salimimoghadam et al., 2025).

This study highlights the significant potential of AI to improve Project Management Office (PMO) performance, but achieving effective implementation will requires further development. Organizations willing to adopt AI might face several critical questions: Which PMO tasks are most suitable for enhancement through AI? What technical, organizational, or cultural barriers might arise? How to manage can resistance to change effectively? What ethical considerations need to be addressed? How to measure the impact of AI be measured in proper ways?

The study will offer a comprehensive analysis for the integration of AI into Project Management Office PMO functions within the construction sector. It aims to identify key opportunities and challenges, bridge existing knowledge gaps, and provide practical insights that can support AI adoption by organizations to enhance their overall performance and achieve more strategic and impactful outcomes.

# - Study problem.

Since the rapid development of AI as a transformative force in different industries, there is still notable gap in adopting AI technologies into Project Management Office functions and understanding the impacts, both positive and negative. This challenge is especially important considering the investments organizations make in both PMO infrastructure and AI technologies, especially with the absence of a clear strategy to align these resources for optimal organizational strategic outcomes (Salimimoghadam et al., 2025).

This study will try to fill gaps in knowledge related to understand AI adoption. First, there is limited practical evidence on PMO tasks that are suitable for AI enhancement, as organizations face challenges in finding practical guidance for the implementation of AI. Second, some organizations struggle to understand the feasibility and value of AI technologies. Third, the technical, organizational, and ethical barriers to integrating AI within PMOs is not much studied, and there is a shortage in existing literature to address these challenges. Furthermore, structured frameworks for assessing return on investment (ROI) in this domain are currently lacking (Shamim, 2024).

Additionally, the required changes by organization for integrating AI is underestimated which include change of work culture, workflow, and leadership. Also, the absence of clear implementation frameworks or roadmaps leaves project professionals without adequate guidance for AI integration. Finally, the potential benefits of AI are generally acknowledged, but there is a notable lack of practical research that quantifies these advantages specifically within the context of PMOs (Salimimoghadam et al., 2025). Therefore, This study aims to address these deficiencies by systematically examining AI integration into PMO functions within the construction sector, identifying possible challenges and opportunities, and getting insights to facilitate informed strategic decision-making.(Adamantiadou & Tsironis, 2025)

# - Study Importance:

The importance of this study comes from its contributions to the academic sector by understanding how Artificial Intelligence can be integrated into Project Management Office functions within the construction sector. The existing literatures has examined AI applications in project management, but significant gap remains regarding its specific role in enhancing overall function PMO processes, governance, and strategic alignment in construction projects. The study extends current theoretical frameworks by exploring this gap to offer practical evidence that may inform future academic work. It also builds on recent systematic literature reviews and emerging research that highlight the transformative potential of AI in organizational project management. Also, research study contributes to the understanding of the benefits and challenges of AI implementation within the project management domain, which is still an under-researched area (Hashfi & Raharjo, 2023).

The study will focus on current literature and explore the practical effects of AI integration in PMO environments and highlights suitable tasks within the PMO that can benefit from AI enhancement. It also explores the challenges and opportunities that come with implementing these technologies therefore provides valuable insights for both researchers and PMO professionals in the construction field.

The results for doing this study will provide important insights for organizations, helping them make better decisions when it comes to investing artificial intelligence, especially in PMOs by improving operational efficiency and supporting strategic alignment in complex construction projects. These findings can lead to notable improvements in project results. Additionally, this study contributes to the broader conversation about digital transformation in project management, setting the stage for future discovery in this fast-evolving field.

# - Study Objectives:

The main objective of this study is to examine the integration of  AI into the tasks and tools of PMOs, with focus on the opportunities and challenges introduced by this technological evolution by the following specific objectives:

- Assess the current PMO functions and tools, to identify the specific areas where AI technologies could enhance performance, improve capabilities, or address existing limitations.

- Identify and the challenges associated with AI integration in PMOs, including technical, organizational, ethical, and implementation-related issues.

- Explore the opportunities and added value that AI can add to PMO operations, by improving efficiency, effectiveness, and strategic contribution.

- Gather insights from existing literature on AI implementation across project management environments in various industries, to highlight common trends, success factors, and recurring obstacles.

- Develop a practical framework to support the successful integration of AI into PMO functions, to cover technical implementation and organizational change issues.

- Provide recommendations for PMO leaders and decision-makers on how to approach AI adoption strategically to maximize benefits and managing associated risks.

Together, these objectives aim to provide clear understanding of AI's impact on PMOs, offering both theoretical insight and practical guidance to support real-world integration.

# -Research Questions

This study on “Effect of Integrating Artificial Intelligence into Project Management Office Tasks and Tools in Construction Sector - Challenges and Opportunities” seeks to answer the following study questions:

- What is the current status of PMO tasks and tools in the construction sector, and which of these are most suitable for development using AI technologies?

- What are the main technical, organizational, and cultural challenges to integrating AI technologies into PMOs?

- How can Al technologies enhance PMO efficiency and impact the construction sector?

- What are the expected future trends for adopting AI technologies in PMOs within the construction sector?

These questions have been designed to closely align with the survey questioneers developed by the researcher for this study to ensure that the collection and analysis of data remain consistent with the study’s objectives.

# - Study Hypothesis

This study will examine the relationship between the integration of Artificial Intelligence (AI) technologies and the performance of Project Management Offices (PMOs) in the construction sector. Accordingly, the following hypotheses have been formulated:

Hypothesis 1: There is a significant relationship between the integration of AI technologies and improvements in PMO functional effectiveness in the construction sector.

Hypothesis 2: Technical, organizational, and ethical challenges negatively impact the successful integration of AI into PMO operations in construction projects.

Hypothesis 3: The integration of AI technologies significantly enhances the strategic value delivered by PMOs in construction projects, particularly in governance, decision-making, and portfolio optimization.

Hypothesis 4: The adoption of AI tools in PMOs is positively correlated with increased efficiency in project governance, decision-making, and task automation.

Hypothesis 5: Organizational readiness and change management practices significantly moderate the relationship between AI integration and PMO performance in the construction industry.

These hypotheses aim to provide a structured approach to examining and understand the impact of AI on PMOs, covering aspects from functional effectiveness to strategic value and operational challenges.

# - The scientific theory used to prepare the research

This study is based in two theoretical models: the Diffusion of Innovations Theory (DOI) and the Technology Acceptance Model (TAM). These theories can provide a robust foundation for understanding the mechanisms behind the adoption and integration of Artificial Intelligence (AI) within Project Management Offices (PMOs) in the construction sector (Blythe, 1999).

The Diffusion of Innovations Theory, which was developed by Everett Rogers, explains how new technologies spread across social systems over time. It highlights five critical factors that influence the integrating process of new technology: relative advantage, compatibility, complexity, trialability, and observability. AI integrating in PMOs can be seen as a process progressing through the stages of knowledge, persuasion, decision, implementation, and confirmation. The study by Aizstrauta et. al (2015) explored the DOI theory by how organizational factors, communication structures, and perceived characteristics of AI, can influence the rate and success of its diffusion within construction project environments (Aizstrauta et al., 2015).

The second model is Technology Acceptance Model (TAM) which adds an individual-level perspective. It focuses on how users’ perceptions shape their intention to use AI tools. It centers on two key elements: Perceived Usefulness (PU) and Perceived Ease of Use (PEOU), which when combined can determine user acceptance level(Aizstrauta et al., 2015; Na et al., 2022). This model helps explain how PMO team members and stakeholders can evaluate AI systems in terms of added value and usability, and the effect of their willingness to adapt and engage with this new technology.

By using both DOI and TAM, the research can comprehensively analyze AI integration into PMOs functions by considering both the macro-level organizational spread and micro-level individual acceptance. This combination of both models can provide an understanding of success factors and challenges in PMO contexts (Felicetti et al., 2024).

This study combines two theoretical perspectives. Independent Variable - AI Integration into Project Management Office Functions. And Dependent Variable - PMO Effectiveness and Strategic Value Contribution.

The third variable is the moderating variables - which impact the relationship between AI integration and PMO effectiveness including: Organizational readiness, Change management practices, Ethical and technical barriers. These moderating variables are considered because they can influence the strength and nature of how AI integration affects PMO effectiveness and strategic value.

This theoretical structure supports the empirical investigation and hypotheses and analysis tools to examine how AI affects project governance, decision-making, resource management, and overall project performance in construction PMOs. It can also allow for a good understanding of both the macro-level publishing of AI technologies across organizations and the micro-level acceptance by individual users.(Venkatesh, 2022)

Chapter Two

Previous Studies

# -Introduction

This chapter will present a comprehensive review of previous studies that was conducted about the integration of artificial intelligence within project management offices, especially the ones related to the construction industry. Also, will provide a historical overview and discussion of the development of PMOs AI technology, and outline the evolution of these two domains, underscoring significant milestones and technological advancements that have paved the way for their present-day convergence in optimizing project delivery (Tominc et al., 2024).

## Project Management Offices (PMOs):

History and Evolution: the concept of a Project Management Office (PMO) started to evolve over the past years as a result from the increase of projects scale and complexity. Its early roots can be traced to the rise of scientific management in the early 20th century, particularly the work of  Frederick Taylor, who focused on systematic approaches to planning, coordination, and efficiency (Giraudo & Monaldi, 2015). Then in the 1930s, one of the earliest documented “project offices” was established by the U.S. Air Corps to oversee aircraft development, marking a practical application of centralized project governance.

Later during the 1950s, the U.S. military advanced this concept by introducing “System Program Offices” (SPOs) to manage complex weapons programs composed of numerous interrelated sub-projects. As a result, early PMO structures showed the value of centralized oversight, including integrated planning, standardized procedures, and enhanced cost control. Next in the 1980s, the adoption of computing tools for project scheduling and tracking provided more support for the expansion of PMO practices beyond the defense sector into industries such as construction and information technology (Umasekar, 2024).

The 1990s witnessed a global proliferation of project management standards and professional organizations. Methodologies such as PRINCE2, originating in the UK, extended PMO practices to new sectors, while the Project Management Institute (PMI) in the USA and the International Project Management Association (IPMA) in Europe gained significant influence. This era reinforced the necessity for structured governance to address the growing number and complexity of projects, prevent cost overruns, reduce delays, and resolve resource conflicts.

During the 1990s, the development of project management standards and the emergence of professional organizations such as PMI and IPMA and methodologies such as PRINCE2, improved the adoption of PMO practices across many sectors. The Project Management Institute (PMI) in the United States and the International Project Management Association (IPMA) in Europe established their influence into PMOs. This period was critical because of the need for structured governance frameworks to cope with the increasing scale and complexity of projects to better mitigate cost overruns, minimize delays, and address resource allocation challenges (de Almeida, 2024)

By the 21st century, PMOs had evolved from administrative support units into strategic ones which help organizations to be aligned with business objectives. Currently, PMO become embedded in different organizations worldwide such as IT, finance, construction, and other sectors. And PMO not only focus on standardizing processes and monitoring performance but also enabling strategic portfolio management and ensuring projects deliver the intended business value. Over time, the PMO has shifted from a monitoring role to a central driver of organizational excellence.

Definition and Roles: There is no single formula for a PMO as its form and function can vary between organizations (“no one-size-fits-all”). In general, a PMO is an organizational structure dedicated to centralizing and coordinating the management of projects. The common definition of PMO is the one by PMI’s Guide to the Project Management Body of Knowledge (PMBOK®) as “an organizational structure that standardizes the project-related governance processes and facilitates the sharing of resources, methodologies, tools and techniques”.

As stated by the definition above, the PMO sets common standards and best practices for project execution, provides support services (such as training, templates, lessons learned), and often oversees governance to make sure projects align with organizational goals and objectives. Depending on its intended role, a PMO's responsibilities may range from advisory (providing consultative support to project teams) to directive (having authority to manage projects directly). For example, PMI categorizes PMOs as supportive, controlling, or directive based on the degree of control they have, and as project-specific, departmental, or enterprise-level based on their scope within the organization. Despite these variations, the role of any PMO is to enhance consistency and predictability in project delivery (Silvius, 2021)

## A well-functioning PMO can help organizations with better project selection and prioritization, better efficient resource utilization, and improved project success rates by applying uniform standards and leveraging organizational knowledge. PMOs also taken the role on strategic level functions such as portfolio management, benefits realization, to bridge the gap between project execution and organizational strategy (Umasekar, 2024).

## Artificial Intelligence (AI):

Historical Background: Artificial Intelligence (AI) as a formal field of study was born in the mid-20th century. The term “Artificial Intelligence” was found in 1956 at the Dartmouth College conference organized by computer scientist John McCarthy. During the conference researchers gathered to explore the possibility of creating machines that could simulate human intelligence, marking the official beginning of AI research. McCarthy and colleagues hypothesized that aspects of human intelligence (such as learning and reasoning) could be precisely defined that a machine could be built to simulate them. Early AI research resulted in the 1950s–1960s programs that could solve algebra problems, prove logical theorems, and play chess, which led to optimism about rapid progress of AI research (Haenlein & Kaplan, 2019).

However, the field also encountered periods of slower advancement known as “AI winters” which was during 1970s and late 1980s, when early AI expectations failed. Then, from the 1990s onward, AI entered a new growth phase due to improved computing power, larger data availability, and new algorithms. One notable milestone when IBM’s Deep Blue defeated a chess champion in 1997. Another is the proliferation of machine learning techniques in the 2000s that demonstrated AI’s growing capabilities. Later in the 2010s, deep learning (multi-layer neural networks) revolutionized fields like computer vision and speech recognition, taking AI into mainstream applications (from virtual assistants to self-driving cars).

Today, AI development is global and driven by research and investments across North America, Europe, and Asia, and is recognized as a major contributor of the Fourth Industrial Revolution worldwide. The global AI research community continues to push toward more general and autonomous forms of AI, and governments and industries invest in AI for its transformative potential in the economy. This historical shift shows AI's evolution from an academic curiosity in the 1950s to a pervasive technological force in the 2020s(Darko et al., 2020)

Definitions and Concepts: AI has been defined in various ways over time, based on its broad scope. A common definition by McCarthy et al. describes AI as “the science of making a machine behave in ways that would be called intelligent if a human behaved similarly”. Similarly, The AI pioneer Marvin Minsky defined it as “the effort to make machines carry out tasks that would require intelligence if done by humans”(Adebayo et al., 2025).

These definitions emphasize that AI systems can copy human behaviors associated with human intelligence such as learning, reasoning, problem-solving, perception, or language use. Modern definitions of AI often center on the idea of intelligent agents: systems that perceive their environment and take actions to maximize their chances of achieving goals (Russell & Norvig, 2022). In practice artificial intelligence is considered an umbrella term for computer systems or machines that can simulate cognitive functions such as understanding, learning from experience, adapting to new inputs, and performing tasks that usually require human intellect.

Key subfields of AI include:

Machine Learning (ML): ML is techniques that allow computers to learn from data and improve their performance over time without being explicitly programmed for every scenario. For instance, ML algorithm can be trained from historical project data to recognize patterns and make predictions. This is why ML is often defined as the ability of a computer to extract patterns from data and learn to make decisions/predictions based on those patterns. ML has different sub-categories such as, deep learning, which uses multi-layered neural networks to handle huge datasets and complex patterns, as a result of this combination it can enable advances in image and speech recognition (Dodge et al., 2019).

Natural Language Processing (NLP): Is a branch of AI that deals with understanding and generating human language by allows AI systems to interpret text or voice inputs. One common example of this type is chatbots, which can search project queries and provide answers (Neveditsin et al., 2025).

Computer Vision: another AI technique to interpret and understand visual information from the world by recognizing objects in images or video. In construction, computer vision can enable automated progress monitoring or safety inspections by analyzing site photos.

Expert Systems and Reasoning: These AI systems encode expert knowledge to make decisions or solve problems in specific domains. For example, an expert system can be used to provide guidance on project risk management by drawing on a knowledge base of best practices.

Robotics and Autonomous Agents: This is an example of the integration of AI in machines that can perform tasks in the physical world. This includes robots that use AI to navigate and perform construction tasks, or software “agents” that autonomously execute tasks in digital environments.

AI is thus multifaceted, and its definition shows a range of computational techniques aiming to mimic intelligent behavior. This explains what makes a system "AI" is its ability to perceive, analyze, decide, and act in a way that appears intelligent or adaptive. Modern AI systems can process huge number of datasets, learn from feedback, and operate autonomy. For example, an AI application can not only learn from historical project data to forecast outcomes, but also adapt its recommendations as new data arrives, which shows a level of responsiveness and input far beyond traditional software (Shamim, 2024)

## Nowadays AI is recognized as a general-purpose technology, with its development driven by international collaboration among academic institutions, industries, and governments. Its integration into initiatives like "Industry 4.0" and "Construction 4.0" highlights how AI has become worldwide, especially in the digital transformation of various sectors. In summary, the author sees AI as the pursuit of machine intelligence – creating systems that can perform tasks that typically needs human intelligence and benefit from techniques such as machine learning to robotics to help enable it intended capability.

## AI in Project Management

Enhancing Decision-Making and Efficiency: The integration of AI into project management has rapidly become a significant area of researcher’s interest. Organizations in different sectors including construction nowadays recognize AI's potential to improve project outcomes. AI technologies can enhance project management by automating routine tasks, providing data-driven insights, discovering trends, risks, and assisting in complex decision-making. For example, AI systems can automatically collect and analyze project data (schedules, budgets, quality, risk logs, etc.), to helps project managers identify trends and issues much faster than manual methods.

A recent PMI market analysis highlights that the global market for AI in project management is projected to grow from about USD 2.5 billion in 2023 to USD 5.7 billion by 2028 (a 17.3% annual growth rate)(Sahadevan, 2023). This growth clearly reflects a broad, global drive to leverage AI for organizations and projects success. AI is revolutionizing project efficiency and predictability, organizations are leveraging AI tools to automate repetitive tasks, extract insights from data sets, support decisions, and serve as intelligent assistants that actively empower project managers and teams.

Intelligent Scheduling and Resource Allocation: AI can assist in generating and updating project schedules, as it can learn from the data of past project performance. Then AI algorithms can predict task durations and resource needs, which can help to create more realistic project schedules. Also, AI-based scheduling tools can optimize resources by matching the right people to the right tasks at the right time. As a result, this AI technology leads to better utilization of resources and adjustment of assignments in real-time as project conditions change (Nagireddy, 2023).

Predictive Analytics for Project Outcomes: the use of AI Machine learning models can forecast project outcomes, like final costs or completion dates, by analyzing historical project data and real-time metrics. This predictive Planning enables project managers to predict potential cost overruns or delays earlier and with greater accuracy. Therefore, this can support project managers to make proactive decisions, by adjusting scope or adding resources. Also, advanced AI technology can run simulations of project scenarios, giving managers insight into the results of different decisions that can help them navigate their projects (a sort of "virtual what-if analysis" powered by data).

Risk Identification and Management: AI is being applied by some organizations to improve risk management by using historical data for generating warning signs. Risk identification was done by using human developed checklists and now has been performed by AI systems that detect patterns linked to risk in project reports, schedules, or even external data such as economic indicators and weather forecasts). Studies such as the one conducted by (Savio & Ali, 2023) show that AI can analyze several datasets from past project archives, to flag potential risks that a human might overlook or cannot predict. For example, an AI tool might learn that specific design changes typically result in cost overruns and alert the PMO when such changes occur, providing early warnings and even prioritizing risks by estimated impact. AI also allows project managers and risk officers to plan mitigation measures for risks as data-driven approach enhances the traditional risk registers by continuously updating risk profiles as conditions evolve.

Automation of Routine PMO Tasks: Many tasks in project management such as status reports, issues tracking, updating dashboards, can be partially or fully automated using AI. For instance, natural language generation algorithms can make weekly status reports from raw project data, and chatbots can respond to team inquiries about project procedures or schedules. As a result, AI help to frees up project managers and PMO staff to focus on important tasks and activities that need human judgment, like stakeholder communication and team leadership. Automation also can help reduces human error in project records and ensures more timely updates are produced form the data (Fridgeirsson et al., 2023).

Intelligent Assistance and Communication: AI-powered virtual assistants, also sometimes called project chatbots or digital project assistants, are emerging to support project managers and teams. These assistants can answer questions about the project status or even interact with project management software on behalf of users. This technology uses natural language processing to understand queries and can operate 24/7, improving team communication and responsiveness. Additionally, AI can facilitate better collaboration by analyzing communication patterns in project teams such as emails and suggesting improvements or flagging potential issues in communication (Patil et al., 2025).

Impact and Emerging Trends: The effect of all these AI applications in a project environment that is more data-driven and proactive is notable. Predictive insights can now inform decisions that relied heavily on a manager's intuition and judgments. Routine process compliance checks, status updates, can be continuously monitored by AI, ensuring nothing falls behind. According to a Harvard Business Review analysis, the coming years will likely bring major shifts in the project management profession due to AI. By 2030, technology is expected to significantly enhance project selection and prioritization, automate progress tracking and reporting, and enable real-time testing and adaptation of project plans.

In this expected future scenario, project managers' roles may evolve to focus less on micromanaging or monitoring and more on providing human leadership. Project managers can provide coaching for teams, manage stakeholders effectively, and make strategic decisions, as AI is handling routine and repetitive tasks. PMI and other professional bodies have launched initiatives such as “PMI's PMI x AI program” to explore the possibilities of AI adoption with project management practices. But this adopting of AI in project management comes with challenges, including data quality issues, change management, fear of change, and ethical considerations, and bias. However, research indicates that AI adoption in project management is gaining more attention globally from organization and academics and is expected to transform the field in the next decade (Adamantiadou & Tsironis, 2025).

In summary, AI can offer powerful tools and technology to help project managers and PMOs to improve forecasting accuracy, fast information processing, and informed decision-making. AI has the potential to increase project success rates if well implemented, by reducing uncertainties and inefficiencies that traditional project management techniques cannot easily address or predict. The global focus on AI to develop and adopt it is notable, as tech startups, large consulting firms, and even government initiatives, are investing and doing more experiments with AI-driven project management solutions, which will lead to a new era of smarter project delivery and more efficient PMOs.

## AI in Construction Project Management

AI Applications in the Construction Industry: The construction sector is known for its labor-intensive and project-based nature, and complexity as projects are not similar although they might seem. Therefore, this industry is still lagging behind in adopting AI compared to other industry. But nowadays the interest in applying AI to improve project management and execution is increasing rapidly. Construction projects present complex challenges such as uncertain site conditions, evolving designs, and coordination of many stakeholders that generate large amounts of data (Silitonga & Jin, 2024). Construction sector started to notice its benefits on other sectors and as a result AI technologies are increasingly seen as key to leveraging this data and enhancing decision-making in construction projects. Recent systematic reviews indicate that AI applications in construction project management have concentrated mainly in the project planning phase and the monitoring and control phase of projects (Adebayo et al., 2025).

For example, in Planning construction projects AI techniques are used to optimize schedules, forecast costs, and refine project plans, while in monitoring. AI also can helps in resource allocations and track progress and detect issues in real time. Common benefits for AI in construction include decision support, prediction, optimization, and performance improvement (Adebayo et al., 2025). In other words, AI is being employed to predict project outcomes which can help to optimize construction processes for better efficiency, quality and safety. All this can help to continually improve project execution and outcomes through data-driven feedback.

Examples of AI in construction management include:

Cost Estimation and Budgeting: Cost forecasting is a very crucial element in the construction sector as it is one of the major project constraints. In this regard, AI is transforming the way estimators and quantity surveyors to perform work. Traditionally, cost estimation relied on expert experience and manual models, which can be subjective, bias and error prone. AI methods, particularly machine learning, can analyze historical cost data from past projects to predicts cost as it can learn the complex relationships between project parameters such as design features, materials, market conditions. Some construction firms used Machine learning models,  or regression models and neural networks to generate more accurate and consistent cost estimates early in the project lifecycle (G. Chen et al., 2025).

Some Studies have noted that intelligent cost estimating techniques significantly reduce the effort and time required by project teams and it also improves accuracy by minimizing  human bias and error. For instance, an AI system can quickly evaluate thousands of similar past project data points to predict the cost, and also the impact of a design decision. Research in the UK found that while AI-based estimating is still in its early stages in construction, it is rapidly growing and seen as a key solution for handling the uncertainty in early-stage cost forecasts (Adebayo et al., 2025). Organizations are beginning to deploy AI-driven estimating tools or use existing estimation tools that are AI supported to continuously improve cost estimation, ultimately helping prevent budget overruns by more accurately predicting costs.

Scheduling and Site Management: Construction schedules are prone to delays due to factors like weather, materials delays, or on-site productivity or construction issues. AI algorithms can improve scheduling by analyzing historical schedule performance of similar projects, and real-time project data to predict possible delays or resource issues. For example, AI can integrate weather forecasts and crew productivity data to warn if a task is likely to slip, allowing project managers to re-sequence activities, allocate extra resources proactively or plan proper risk mitigation. In large projects, reinforcement learning algorithms have been experimented to find optimal construction sequences or crane movements, effectively learning the best way to construct a project through simulation (Sahadevan, 2023).

As a result, AI-based schedule optimization can therefore increase efficiency and reduce idle times of resources. Also, AI-powered tools sensors enable real-time monitoring of construction progress, and computer vision systems can compare daily site photographs or 3D laser scans against Building Information Modeling (BIM) to assess work completed to the plan which can help in flagging any deviations. This enhances the monitoring process by providing objective and valuable progress data rather than relying solely on periodic human inspections (Merdžanović et al., 2023).

Quality and Safety Management: Ensuring quality and safety are crucial in construction projects and one of its constraints. AI is being applied to these areas via technologies such as computer vision and pattern recognition. For quality control, AI systems can automatically detect defects or inconsistencies in construction work by analyzing images. For example, identifying cracks in structures or incorrect installations captured in photos/drone footage and then the system compare it to the learning data that is been feed into his system (Luo et al., 2025). Similarly for safety, AI-driven video analytics can monitor site videos to recognize unsafe behaviors or conditions. Workers not wearing protective gear or equipment can be detected by the system such as computer vitions and can alert supervisors in real time to prevent accidents (Waqar et al., 2023)

Additionally, predictive models that use AI have been used to foresee safety incidents by learning from past incident data. Also, some organizations use it to identify which combinations of factors or site conditions like schedule pressure, weather, and crew experience correlate with higher accident rates. By identifying high-risk situations in advance, project managers can apply more safety measures and lower accidents or accidents. This proactive risk management through AI is a developing area aimed at achieving zero-incident projects. (Shanti et al., 2021)

Design and Engineering Optimization: In project design, AI is aiding architects and engineers in the design phase, which indirectly benefits project management by reducing scope changes and the resulting downstream from these design changes. Some AI techniques like generative design, powered by AI algorithms, can rapidly produce and evaluate numerous design alternatives under given constraints, allowing optimal solutions for cost, sustainability, resources and construction method to be used. It means that before construction begins, AI helps in value engineering, finding best possible design approaches that meet project objectives and customer needs at lower cost or risk.

Moreover, AI in the form of structural optimization algorithms can ensure that materials are used efficiently, schedules are realistic, and potential construction difficulties are discovered in the design stage, therefore minimizing costly changes and delays during construction. For example, AI can analyze data from various sources like smart devices and BIM system to identify patterns in construction performance and usage, for future construction needs (Egwim et al., 2023).

Industry 4.0 and Future Trends: Construction 4.0 is moving forwards to digitization of construction and by the integration of AI technologies like, IoT, Big Data, robotics, and more. AI is become one of the core technologies driving this transformation of construction globally. Many industry bodies are developing strategies to integrate AI into construction processes as part of digitizing the sector. Recent research show a rapid increase in studies on AI in construction, with the United States, UK, and China among the leaders in publication output, and they underscoring the global scope of interest and they concluded that the impact of AI has begun to make is significant as it is revolutionizing the industry; offering innovative solutions to enhance efficiency, reduce costs, and improve decision making in construction project management (Adebayo et al., 2025).

Empirical analyses of AI use in construction discovered that employing AI leads to improved performance especially in terms of time and cost savings and better adherence to project specifications and requirements (Adebayo et al., 2025). For example, machine learning models that optimize equipment usage can cut idle time and save energy, while AI-driven predictive maintenance for construction machinery can prevent breakdowns that might stop a project. Furthermore, the integration of AI with other advanced technologies, such as the IoT and BIM, forms a robust digital ecosystem that enhances data collection, analysis, and make actionable insights for proactive project management (H.-P. Chen & Ying, 2022).

Also several AI-related trends are already influence construction project management: Digital twins allow AI to run simulations and optimizations continually during project execution. Advanced robotics and autonomous machines may handle repetitive or hazardous construction tasks such as bricklaying robots or autonomous earthmoving equipment with AI systems ensuring they operate safely and efficiently alongside human workers.

AI is also being applied to sustainability goals in construction – for instance, optimizing energy use on worksites or designing buildings for lower lifecycle energy consumption is aligning with the industry's aim for greener projects (Adebayo et al., 2025). Furthermore, as data from various sources, drones, sensors, smart devices, becomes more valuable on construction sites, Big Data analytics in combination with AI will play a bigger role in integrating information and providing actionable insights to project managers. Despite the promises AI can provide, the construction industry's adoption of AI is still in its early stages. Many firms are piloting AI tools on a small scale and challenges such as data quality, lack of AI expertise in organizations, and the need for change management are being observed and addressed gradually. Therefore, case studies and research consistently show that AI can be a powerful to improve construction project outcomes as it can help in reducing cost overruns, enhancing safety, AI's contributions align closely with the objectives of project management in construction.

In summary, as the construction industry undergoes a digital transformation, project management offices (PMOs) and project managers are increasingly embracing AI-driven tools to boost planning, streamline project execution, and deliver better project outcomes. The evolution of both AI and PMO methodologies is converging in this sector, empowering modern construction teams to benefit from data-driven insights, automate complex tasks, and proactively manage risks. As Integrating AI throughout the project lifecycle, today's PMOs can set new standards for efficiency, adaptability, and success in construction project management.

# Previous Studies

In this section, we review ten relevant studies from around the globe on the use of Artificial Intelligence (AI) in project management offices (PMOs) and the construction industry, including each study’s location and key outcomes. This overview highlights the current research landscape, spanning systematic literature reviews and empirical investigations, to identify common findings and gaps in this domain.

- Bento et al. (2022) – AI for Efficiency in Project Management

- Study Location: Portugal (literature review of global studies)

- Outcome: Bento and colleagues conducted a systematic review of the use of AI in project management and found that AI implementation can significantly improve project efficiency and precision, which is leading to notable cost reductions and shorter delivery times (Bento et al., 2022). Their analysis indicated that AI-driven tools such as predictive analytics and machine learning systems helped enhanced decision-making and real-time project control, and overall project performance. This study shows valuable AI’s potential to the processes of AI adoption such as scheduling and forecasting. However, it also noted the need to address challenges like data requirements and change management to use the benefits of AI(Bento et al., 2022).

- Hashfi & Raharjo (2023) – AI’s Impact Across PMBOK Process Groups

- Study Location: Indonesia (literature review of global studies)

- Outcome: Hashfi and Raharjo performed a systematic literature review to map AI's challenges and impacts onto the Project Management Body of Knowledge (PMBOK) and focused on process groups (Hashfi & Raharjo, 2023). Their findings show that AI tools enhanced multiple project management activities during the Initiating phase of the projects. AI also improves risk assessment and cost prediction in the Planning stage. It also helps in project selection, cost estimation, resource allocation, and decision-making (Hashfi & Raharjo, 2023).

They also mentioned that during execution stage, advanced AI techniques (e.g., machine learning algorithms) boost productivity and resource allocation and reducing costs and supporting faster decision-making. In Monitoring and Controlling, AI systems such as real-time analytics and anomaly detection, increased efficiency, improved quality control, and provide timely decision support (Hashfi & Raharjo, 2023). Even in Closing of projects, AI helps optimize resource handover and minimize waste. Overall, this study highlights that AI integration can lead to more agile and data-driven project management practices across all phases of a project's lifecycle, while also emphasizing the importance of organizational readiness to overcome adoption barriers.

- Regona et al. (2022) – AI Adoption Challenges in Construction

- Study Location: Australia (PRISMA-based literature review of global construction industry studies)

- Outcome: Regona examined the opportunities and adoption challenges of AI in the construction industry. Their found that despite AI's known benefits, the construction sector has been slow in embracing these technologies (Regona et al., 2022).

They also found that AI adoption in construction projects remains relatively limited compared to other sectors like finance and manufacturing (Regona et al., 2022). Key opportunities include AI's ability to improve project outcomes such as schedule optimization, cost efficiency, and safety monitoring. However, they noted many barriers are slowing the implementation in construction. Issues with integrating AI into existing systems and processes, the high cost of AI solutions, resistance to change among project teams, and concerns about data quality and privacy (Regona et al., 2022). This study agrees with literature that addressing these challenges – through better data strategies, change management, and cost-benefit clarity is crucial for construction organizations to capitalize on AI-driven improvements in project delivery.

- Adebayo et al. (2025) – Applications and Trends of AI in Construction PM

- Study Location: United Kingdom & Nigeria (structured literature review of global research)

- Outcome: Adebayo and his colleagues conducted a comprehensive structured literature review on AI in construction project management, by analyzing 135 peer-reviewed articles from 1985 to 2024. Their study found that AI technologies are most applied during the Project Planning and Monitoring/Control phases, and using AI tools like predictive modeling and computer vision, which helped in enhance decision-making, forecasting, and performance tracking (Adebayo et al., 2025). They outlined purposes of AI usage by construction firms include decision support, risk prediction, schedule optimization, and overall performance improvement. Also, they identified several factors for AI adoption in construction, such as the availability of advanced technology, the need for better project outcomes (time, cost, quality), competitive advantage pressures, and sustainability goals (Adebayo et al., 2025).

At the same time, the review also highlighted some barriers like those found by Regona et al., difficulties in data integration, high implementation costs, stakeholder resistance to technological change, and ethical and privacy concerns (Adebayo et al., 2025). The researcher also pointed future trends in construction including the use of digital twins, autonomous robotics on job sites, and AI for energy efficiency and sustainability improvements (Adebayo et al., 2025). This study provides a global perspective that confirms that as AI is revolutionizing as a technology, construction project management and PMOs also improving efficiency and decision quality, organizations must navigate adoption hurdles to fully leverage these innovations.

- Fridgeirsson et al. (2021) – Future Impact of AI on PM Knowledge Areas

- Study Location: Iceland (survey of project management experts internationally)

- Outcome: Fridgeirsson and colleagues carried out an authoritative study exploring how AI will support project management profession over the next decade, focusing on the ten PM knowledge areas on PMI's PMBOK(Fridgeirsson et al., 2021). Through a survey done for experienced project managers worldwide, the study found that AI will become an integrated part of future project management practices, with a powerful impact in the knowledge areas of Cost Management, Schedule Management, and Risk Management (Fridgeirsson et al., 2021). Respondents indicated that AI provide good benefits in processes that uses historical data which improves planning and estimation. For example, AI can accurately forecast project costs and durations, monitor schedules in real time, adjust forecasts as conditions change, and help maintain baselines by flagging deviations (Fridgeirsson et al., 2021). The study results suggest that AI-driven analytics will significantly aid in identifying and mitigating risks, thus improving on-time and on-budget delivery of projects. However, they concludes that AI's impact will not still benefit in areas requiring human judgment and leadership, such as team building, stakeholder management, and other domains demanding emotional intelligence (Fridgeirsson et al., 2021). In summary, experts believe AI will improve project managers by automating analytical and routine tasks, thereby allowing professionals to focus on strategic and people-oriented aspects that AI cannot replicate.

- Shanti et al. (2021) – AI-Driven Construction Safety in the UAE

- Study Location: United Arab Emirates (case implementation on construction sites)

- Outcome: Shanti and co-researchers presented a novel implementation of an AI-based "smart" safety inspection system for construction projects in the UAE. The AI model which is leveraging computer vision and deep learning was designed to automatically detect safety violations on site, discovering workers missing protective equipment or unsafe conditions in real time. The implementation's results were highly promising: the AI system achieved an accuracy of over 91% with approximately 99% precision in identifying safety issues, and a recall rate of about 90% (Shanti et al., 2021). These performance metrics indicate that the model can reliably recognize most hazards or non-compliance incidents on construction sites. The study outcomes also verify the effectiveness of AI in enhancing construction safety monitoring, as the system was able to control potential violations proactively and help avoid accidents before they occurred (Shanti et al., 2021). In practice it means project managers and PMOs in construction can deploy AI-driven surveillance to significantly reduce on-site risks, improve compliance with safety regulations, and protect workers. This will  not only save lives but also prevent costly schedule disruptions due to accidents and lost time due to safety accidents. This case shows real time example how AI tools can deliver tangible improvements in construction project performance through risk reduction and increased safety surveillance, especially in fast-developing regions like the Middle East that are investing in innovative construction technologies.

- Luo et al. (2025) – AI Assimilation and Performance in Chinese Construction

- Study Location: China (quantitative survey of construction firms)

- Outcome: Luo and co-authors investigated how the internal adoption of AI  within construction companies influences organizational performance under innovative business models. Their study surveyed 174 practitioners from China construction industry and analyzed the data using structural equation modeling (PLS-SEM). The results shows that exploratory innovation, i.e., a firm's use of new ideas and technologies, significantly improves company performance through what they called ”AI assimilation”. In other words, firms that are more innovative and better at integrating AI into their processes see enhanced project outcomes and efficiency therefore better competitive advantage for them in the market (Luo et al., 2025).

Similarly, adopting novel business models works well with AI as they stated, as new business approaches promote deeper AI utilization, which in turn drives performance gains (Luo et al., 2025). The study also found out that competitive market plays a moderating role: in highly competitive environments, the positive effect of exploratory innovation on AI assimilation becomes stronger, but the direct contribution of AI assimilation to performance gains is somewhat weakened(Luo et al., 2025).

This approach suggests that AI integration generally boosts construction project performance, through better cost control and innovation, which in return provide competition and immediate performance returns. This research provides empirical evidence that AI adoption can result in significant improvements in construction project success. However, organizations must also consider market conditions in strategizing their AI investments (Luo et al., 2025).

- Abioye et al. (2021) – AI Applications and Challenges in Construction

- Study Location: United Kingdom (critical literature review with global scope)

- Outcome: Abioye, and colleagues performed a critical review of the current status, opportunities, and challenges of AI applications in the construction industry (Abioye et al., 2021). This UK study noted that the construction sector faces many complex challenges including high cost/time overruns, safety issues, labor shortages, etc. They found that AI technology like machine learning, knowledge-based systems, computer vision, robotics, and optimization algorithms – has the potential to address many of these issues (Abioye et al., 2021).

The authors reviewed how AI techniques have been successfully applied in other industries, to understand and identify possible AI applications to be used or devolped for the construction sector. These include activity monitoring on sites by using drones or cameras with AI to track progress and safety, risk management using AI predicting project risks or failures, and resource/waste optimization by using algorithms improving resource allocation and minimizing material waste (Abioye et al., 2021). The study also outlined the opportunities that AI offers for the construction such as increased productivity, improved safety, and enhanced decision-making, while understand what are the challenges that still exist in using these benefits. Challenges mentioned include the construction industry's low level of digitization, lack of AI expertise among construction teams, data quality and availability issues, and organizational resistance to adopting new technologies (Abioye et al., 2021).

Abioye et al. conclude with insights into how the industry can benefit from AI, asking stakeholders to invest in digital infrastructure, training, and change management. This review shows how AI can help solve ongoing problems in construction project management. It also points out that, to use AI successfully, organizations need to prepare and plan carefully.

- Kumar et al. (2021) – Practitioner Perspectives on AI as a Success Factor

- Study Location: India (qualitative study with global expert interviews)

- Outcome: Kumar, Pandey, and Singh explored if AI is considered as a critical success factor for construction projects by experienced project practitioners (Kumar et al., 2021). The researchers conducted interviews with senior project managers involved in large-scale construction projects worldwide to gain a comprehensive understanding of their perspectives on the influence of artificial intelligence (AI) on project success.

- The results show that experienced project managers take a cautious view of AI. While they generally recognized that AI could enhance project performance by automating basic tasks or improving data analysis, they did not consider AI to be as important as traditional success factors like strong leadership or effective stakeholder management that is been currently used in real world.

The study highlights several perceived drawbacks of current AI technologies from the practitioner viewpoint: (i) AI systems lack soft skills and emotional intelligence, (ii) they lack the flexible human-like reasoning needed to interpret ambiguous situations, and (iii) they cannot replicate the relationship-building and people management capabilities that project managers use to drive project success (Kumar et al., 2021).

They argued that AI, as of now, remains a set of advanced tools that is different from conventional project management software, and is "still years away" from developing any form of self-awareness or human-like judgment (Kumar et al., 2021).

Thus, while AI can support project managers through better data insights, these practitioners believe that successful project delivery still relies primarily on human expertise and leadership. Therefore this study provides an important practical perspective: in the eyes of top project managers, AI is an enabler but not a substitute for the human elements critical to project success, at least with today's technology.

- Salimimoghadam et al. (2025) – Opportunities and Barriers of AI in Project Management

- Study Location: Australia (systematic literature review of global project management research)

- Outcome: Salimimoghadam and colleagues conducted a recent systematic literature review (published in Buildings 2025) examining current opportunities, enablers, and barriers related to implementing AI and machine learning in project management. This review of literature aimed to present a comprehensive framework for AI adoption in project settings. The findings highlight several transformative benefits of AI for project management. For example, AI technologies can improve forecasting accuracy such as schedule and cost predictions, enhance risk mitigation through advanced analytics, facilitate better stakeholder collaboration via AI-driven communication and knowledge management tools, and strengthen safety management on projects (Salimimoghadam et al., 2025).

These advantages align with other studies, reinforcing that AI can optimize resource allocation and automate routine processes, leading to more efficient and informed project execution. On the other hand, the review also identifies critical challenges and barriers. Most important was difficulties of integrating AI solutions with legacy systems already in use by organizations, problems with data quality and availability that can affect AI insights, and organizational resistance to change (Salimimoghadam et al., 2025). The authors note that specific enablers like top management support, staff training, and a strong data governance framework can help overcome these barriers.

This study outcome provide valuable insight, as it shows while AI holds great promise to reshape project management practices across industries and making them more data-driven and proactive. On other hand success largely depends on how well organizations manage the adoption process, address technical and cultural hurdles, and capitalize on the enablers that make AI implementation viable and effective.

Summary of past studies:

Each of these studies contributes to a growing understanding that AI is gradually becoming an integral part of project management and PMO functions, particularly in data-intensive sectors like construction. Overall, they illustrate that AI can offer substantial efficiency improvements, such as optimizing scheduling and forecasting, reducing costs, and enabling faster decision-making through predictive analytics (Bento et al., 2022). They also highlight AI's capacity to enhance risk management and overall project outcomes. At the same time, AI's full potential requires overcoming significant adoption challenges, including issues with data quality and integration, high implementation costs, and organizational resistance to change(Regona et al., 2022).

This research emphasizes that human expertise remains crucial, with AI functioning primarily as a tool to enhance the capabilities of project managers. By automating routine tasks and offering data-driven insights, AI allows human leaders to focus on complex decision-making and the essential "soft skills" that are vital for project success. (Bento et al., 2022; Luo et al., 2025). This comprehensive review of prior work thus sets the stage for further research into strategies for effectively blending AI tools with project management best practices to enhance success in construction and beyond.

# - Theoretical framework

This study is grounded in two complementary theoretical models: the Diffusion of Innovations Theory [Rogers, E. M.. Diffusion of Innovations (5th ed.). Free Press.] and the Technology Acceptance Model [Davis, F. D.. Perceived usefulness, perceived ease of use, and user acceptance of information technology. MIS Quarterly, 13, 319-340.]. These theories collectively provide a robust foundation for understanding the mechanisms behind the adoption and integration of Artificial Intelligence within Project Management Offices in the construction sector.

The Diffusion of Innovations Theory, as developed by Everett Rogers, explains how new technologies spread across social systems over time. It highlights five critical factors influencing the adoption process: relative advantage, compatibility, complexity, trialability, and observability. Within this framework, AI adoption in construction PMOs can be seen as a process progressing through the stages of knowledge, persuasion, decision, implementation, and confirmation. By applying DOI, the study explores how organizational factors, communication structures, and the perceived characteristics of AI — such as its relative advantage in automating complex construction schedules or improving safety compliance, or its complexity when integrating with existing Building Information Modeling systems — influence the rate and success of its diffusion within dynamic construction project environments. This macro-level perspective helps identify the organizational conditions conducive or detrimental to AI integration.

In parallel, the Technology Acceptance Model adds an individual-level perspective, focusing on how users’ perceptions shape their intention to use AI tools. It centers on two key constructs: Perceived Usefulness and Perceived Ease of Use, which jointly determine user acceptance. This model helps explain how PMO team members and stakeholders in construction evaluate AI systems in terms of their perceived usefulness for tasks like precise cost estimation or risk prediction specific to construction projects, and their perceived ease of use given varying levels of digital literacy within construction teams. Their willingness to adopt and engage with the technology, therefore, directly impacts individual-level integration.

By integrating DOI and TAM, this research can comprehensively analyze AI integration by understanding how macro-level organizational factors create an environment that shapes individual perceptions and intentions. For example, strong organizational readiness (a DOI-related factor) might lead to better training and support, thereby enhancing users' perceived ease of use, which in turn accelerates broader organizational diffusion. This combined approach offers a nuanced understanding of success factors and challenges in AI adoption within construction PMO contexts.

This study combines these two theoretical perspectives to investigate:

- Independent Variable: AI Integration into Project Management Office Functions.

- Dependent Variable: PMO Effectiveness and Strategic Value Contribution.

The research framework also includes moderating variables that can impact the relationship between AI integration and PMO effectiveness:

- Organizational readiness:

- Change management practices: (Moderates as it facilitates or hinders the implementation and acceptance process, aligning with both DOI's implementation stage and TAM's user acceptance)

- Ethical barriers: (Moderates by affecting the 'decision' stage of DOI and potentially undermining 'perceived usefulness' in TAM if concerns are high)

- Technical barriers: (Moderates by directly impacting 'perceived ease of use' in TAM and 'complexity' in DOI, thus slowing or preventing successful integration)

These moderating variables are considered because they can influence the strength and nature of how AI integration affects PMO effectiveness and strategic value. For instance, high organizational readiness and effective change management are expected to strengthen the positive impact of AI integration, while significant technical or ethical barriers are likely to weaken it.

This theoretical foundation supports the empirical investigation and guides the development of hypotheses and analysis tools to examine how AI affects project governance, decision-making, resource management, and overall project performance in construction PMOs. This combined theoretical approach allows for a nuanced understanding of both the macro-level dissemination of AI technologies across organizations and the micro-level acceptance by individual users.