## Slide 1
Prepared by Dr. Tarek Mohamed
Project Procurement and
Supply Chain
Lecture 7
PMG 433

## Slide 2
Procurement systems in Project Management
Lecture 7
PMG 433
Dr. Tarek Mohamed
Prepared by

## Slide 3
Course Agenda
At the end of this session, participants will be able to:
Define project procurement systems.
Explain the procurement management process.
Identify procurement methods.
Understand procurement documentation.
Describe e-procurement systems.
Evaluate procurement performance.
Apply AI in project procurement
Chapter

## Slide 4: What is Procurement?
Definition
Procurement is the process of obtaining goods, services, and works from
external sources to meet project requirements.
Procurement management is performed throughout the project life cycle
Objectives
Obtain required resources
Minimize costs
Ensure quality
Reduce risks
Meet project schedule

## Slide 5: Procurement Management in PMBOK
Definition
According to the PMBOK® Guide (Project Management Body of Knowledge),
Project Procurement Management includes the processes required to purchase or acquire products, services, or results needed from outside the project team.
It also involves managing contracts and relationships with suppliers, contractors, consultants, and vendors throughout the project life cycle.

## Slide 6: Procurement Management in PMBOK
Project Procurement Management includes
Plan Procurement Management
Conduct Procurement
Control Procurement

## Slide 7: PMBOK Procurement Management Processes
1. Plan Procurement Management
Purpose: Determine what to procure, when to procure it, and how to procure it.
Key Activities:
Make-or-Buy Analysis
Procurement strategy development
Defining procurement requirements
Preparing procurement documents
Selecting contract types
Developing the Procurement Management Plan
Key Outputs:
Procurement Management Plan
Procurement Statement of Work (SOW)
Bid documents (RFI, RFQ, RFP)
Source selection criteria

## Slide 8: Make-or-Buy Analysis
Factors
Cost
Time
Expertise
Risk
Quality
Strategic importance
Example
Should a company build software internally or outsource development?

## Slide 9: Procurement Documents
Document | Purpose
RFI (Request for Information) | Gather information about potential suppliers and available solutions.
RFQ (Request for Quotation) | Obtain price quotations for clearly defined goods or services.
RFP (Request for Proposal) | Request detailed technical and commercial proposals for complex procurements.
ITB (Invitation to Bid) | Invite suppliers to submit competitive bids for well-defined requirements.
Contract | Legally binding agreement between buyer and seller.

## Slide 10: PMBOK Procurement Management Processes
2. Conduct Procurements
Purpose: Obtain seller responses, evaluate proposals, select suppliers, negotiate contracts, and award contracts.
Key Activities:
Advertise procurement opportunities
Receive supplier proposals
Evaluate bids
Conduct negotiations
Select suppliers
Award contracts
Key Outputs:
Selected sellers
Signed contracts
Resource calendars
Change requests (if needed)

## Slide 11: PMBOK Procurement Management Processes
3. Control Procurements
Purpose: Monitor contract performance, manage relationships with suppliers, and ensure both parties fulfill contractual obligations.
Key Activities:
Monitor supplier performance
Inspect deliverables
Manage contract changes
Resolve disputes
Process payments
Close procurement contracts
Key Outputs:
Work performance information
Procurement documentation updates
Closed contracts
Lessons learned

## Slide 12: PMBOK Procurement Management Flow
Plan Procurement Management
│
▼
Determine procurement requirements
│
▼
Prepare procurement documents
│
▼
Conduct Procurements
│
▼
Evaluate proposals
│
▼
Negotiate contracts
│
▼
Award contracts
│
▼
Control Procurements
│
▼
Monitor supplier performance
│
▼
Contract closure

## Slide 13: Procurement Approaches (PMBOK Perspective)
1. Competitive Procurement
The buyer solicits bids or proposals from multiple qualified sellers.
Examples
Request for Proposal (RFP)
Request for Quotation (RFQ)
Invitation for Bid (IFB/ITB)
Advantages
Fair competition
Better pricing
Greater transparency

## Slide 14: Procurement Approaches (PMBOK Perspective)
2. Sole-Source Procurement
The buyer purchases from only one supplier because no reasonable alternative exists.
Typical Reasons
Unique expertise
Proprietary technology
Emergency procurement
Compatibility with existing systems

## Slide 15: Procurement Approaches (PMBOK Perspective)
3. Single-Source Procurement
The buyer chooses one supplier from several available suppliers.
Unlike sole-source procurement, alternatives exist, but one supplier is selected based on strategic or business reasons.

## Slide 16: Procurement Approaches (PMBOK Perspective)
4. Procurement through Framework Agreements
The buyer establishes long-term agreements with one or more suppliers for future purchases.
Benefits
Reduced procurement time
Lower administrative effort
Stable supplier relationships

## Slide 17: Procurement Management Knowledge Areas
Project procurement management is closely integrated with:
Project Scope Management –Defines what must be procured.
Project Schedule Management –Ensures timely procurement.
Project Cost Management –Controls procurement costs.
Project Risk Management –Identifies and mitigates supplier and contract risks.
Project Quality Management –Ensures procured deliverables meet quality standards.
Project Stakeholder Management –Coordinates with suppliers, contractors, and clients.

## Slide 18: What is a Procurement System?
A Procurement System is
An integrated framework of policies, procedures, technologies, people, and
controls used to plan, execute, monitor, and close procurement activities
throughout the project life cycle.
A procurement system provides standardized procedures for acquiring goods and services

## Slide 19: Components of a Procurement System
People
↓
Policies
↓
Procedures
↓
Technology
↓
Suppliers
↓
Contracts
↓
Performance Monitoring

## Slide 20: Types of Procurement Systems
1. Traditional Procurement System (Design–Bid–Build)
Definition: The project owner hires a designer to complete the design before selecting a contractor through competitive bidding.
Characteristics:
Separate contracts for design and construction
Design completed before construction begins
Competitive tendering
Well-defined project scope
Advantages:
Transparent procurement process
Competitive pricing
High owner control
Disadvantages:
Longer project duration
Limited contractor involvement during design
Changes can be costly
Best for: Projects with clearly defined requirements

## Slide 21: Types of Procurement Systems
2. Design–Build Procurement System
Definition: A single contractor is responsible for both the design and construction of the project.
Characteristics:
One contract
Single point of responsibility
Overlapping design and construction phases
Advantages:
Faster project completion
Better coordination
Reduced disputes
Disadvantages:
Less owner control over design
Difficult to compare proposals
Best for: Fast-track and complex projects.

## Slide 22: Types of Procurement Systems
3. Construction Management Procurement System
Definition: A Construction Manager (CM) is appointed to manage planning, coordination, and execution while multiple contractors perform the work.
Characteristics:
Professional management
Multiple trade contracts
Early contractor involvement
Advantages:
Flexible project execution
Better cost control
Faster delivery
Disadvantages:
Complex coordination
Higher management effort

## Slide 23: Types of Procurement Systems
4. Management Contracting System
Definition:
A management contractor oversees subcontractors and coordinates project execution on behalf of the owner.
Advantages:
Early project start
Flexibility
Efficient coordination
Disadvantages:
Increased management costs
Greater contractual complexity

## Slide 24: Types of Procurement Systems
5. Engineering, Procurement, and Construction (EPC)
Definition: A single contractor is responsible for engineering, procurement, construction, and project delivery.
Characteristics:
Turnkey approach
Single point of accountability
Fixed completion targets
Advantages:
Simplified contract management
Cost and schedule certainty
Reduced owner involvement
Disadvantages:
Higher initial contract value
Less flexibility after contract award
Best for: Large industrial, energy, and infrastructure projects

## Slide 25: Types of Procurement Systems
6. Electronic Procurement (E-Procurement)
Definition: A digital procurement system that uses information technology to manage purchasing activities electronically.
Features:
Electronic tendering
Online supplier portals
Electronic purchase orders
Digital contract management
Electronic invoicing
Advantages:
Faster procurement
Lower administrative costs
Improved transparency
Better supplier communication

## Slide 26: Comparison of Procurement Systems
Procurement System | Number of Main Contracts | Main Advantage | Best Suited For
Traditional (Design–Bid–Build) | Two (Design & Construction) | Competitive pricing and owner control | Well-defined projects
Design–Build | One | Faster delivery and single responsibility | Fast-track projects
Construction Management | Multiple | Flexibility and professional management | Large, complex projects
Management Contracting | Multiple | Early project start | Complex projects with phased work
Public–Private Partnership (PPP) | Long-term partnership | Risk sharing and private financing | Public infrastructure
Engineering, Procurement & Construction (EPC) | One | Turnkey delivery | Industrial and infrastructure projects
E-Procurement | Digital platform | Speed, transparency, and automation | Organizations adopting digital procurement

## Slide 27: Procurement Methods
Competitive Bidding
Open Tender
Restricted Tender
Single Source
Direct Procurement
Framework Agreements
Competitive Negotiation

## Slide 28: Comparison of Procurement Methods
Procurement Method | Competition | Best Used For | Main Advantage
Open Tendering | High | Public projects | Transparency
Selective Tendering | Medium | Specialized projects | Better-qualified suppliers
RFQ | Medium | Standard goods and services | Price comparison
RFP | Medium | Complex projects | Best overall value
RFI | None | Market research | Supplier information gathering
Single-Source | Low | Strategic suppliers | Speed and continuity
Sole-Source | None | Unique products or services | Only feasible option
Direct Procurement | None | Small or urgent purchases | Simplicity
Framework Agreement | Limited | Recurring purchases | Efficiency and consistency

## Slide 29: Procurement Contract Types
Fixed Price Contract
Cost Reimbursable Contract
Time and Material Contract
Unit Price Contract
Comparison table

## Slide 30: Comparison of Procurement Contract Types
Feature | Fixed-Price (FP) | Cost-Reimbursable (CR) | Time & Material (T&M)
Cost certainty | High | Low | Medium
Scope definition | Well defined | Uncertain | Partially defined
Buyer risk | Low | High | Medium
Seller risk | High | Low | Medium
Flexibility | Low | High | Medium
Administration | Simple | Complex | Moderate
Best for | Construction, equipment | R&D, innovation | Consulting, maintenance

## Slide 31: Supplier Selection Criteria
Price
Quality
Experience
Capacity
Financial Stability
Risk
Past Performance
Sustainability

## Slide 32: Supplier Evaluation Matrix
Criteria | Weight
Price | 30%
Quality | 25%
Delivery | 20%
Technical Capability | 15%
Financial Strength | 10%

## Slide 33: Digital Procurement Systems
E-Procurement
Characteristics
Electronic catalogs
Electronic bidding
Supplier portals
Online approvals
Electronic payments
Benefits
Faster
Transparent
Lower cost
Reduced paperwork

## Slide 34: ERP Procurement Systems
Examples
SAP
Oracle
Microsoft Dynamics
Odoo
Functions
Purchase Orders
Inventory
Contracts
Finance
Supplier Database

## Slide 35: Artificial Intelligence in Procurement
Applications
Supplier selection
Spend analytics
Contract review
Predictive procurement
Risk prediction
Supplier performance analysis
Negotiation support
Chatbots
Fraud detection

## Slide 36: Procurement Risks
Supplier failure
Schedule delays
Cost escalation
Poor quality
Legal disputes
Currency fluctuations
Political risks
Cybersecurity

## Slide 37: Risk Mitigation
Multiple suppliers
Performance bonds
Insurance
Contract clauses
Supplier audits
Continuous monitoring

## Slide 38: Procurement Performance
Procurement KPIs
Procurement Cycle Time
Cost Savings
Supplier Quality
On-Time Delivery
Contract Compliance
Purchase Price Variance
Supplier Performance Index

## Slide 39: Procurement Ethics
Transparency
Fair Competition
Confidentiality
Conflict of Interest
Compliance
Anti-Corruption

## Slide 40: Future Procurement Systems
Emerging Technologies
Artificial Intelligence
Blockchain
Smart Contracts
IoT
Digital Twins
Robotic Process Automation (RPA)
Predictive Analytics
Cloud Procurement

## Slide 41: Summary
Procurement systems are critical to project success.
Effective procurement aligns cost, quality, time, and risk objectives.
Digital platforms and AI improve procurement efficiency, transparency, and decision-making.
Supplier selection, contract management, and performance monitoring are continuous processes throughout the project life cycle.

## Slide 42
Summary of Learning Objectives
Define project procurement systems.
Explain the procurement management process.
Identify procurement methods.
Understand procurement documentation.
Describe e-procurement systems.
Evaluate procurement performance.
Apply AI in project procurement

## Slide 43
Morris, P. W., & Pinto, J. K. (Eds.). (2007). The Wiley guide to project technology, supply chain, and procurement management (Vol. 4). John Wiley & Sons.
Schwalbe, K. (2015). Information technology project management. Cengage Learning.
Baily, P., Farmer, D., Crocker, B., Jessop, D., & Jones, D. (2008). Procurement principles and management. Pearson Education.
Supply Chain Council
PMBOK® Guide (Project Management Body of Knowledge),
Essential Reference

## Slide 44
Thank You