## Slide 1: PMG 622 Agile Project Management LECTURE 06: ORGANIZATIONAL CONSIDERATIONS FOR PROJECT Agility
Everyone’s Smart University
دكتور مهندس استشاري ادارة المشروعات
Eng. Dr. Akram Mustafa Suliman Ali,
PhD. AU, BEng. & MSc. AAST, CEng CMarEng MIMarEST, PE, PMP®,
ASQ CSSBB, ISO Lead Auditor, NDT Level II,

## Slide 2: FREE PROJECT MANAGEMENT AND RELATED RESOURCES
Infringement of intellectual property is a violation of Project Management Code of Ethics.
There is a free alternative to all resources requiring special license.
Based on your specialty list the software and other resources that require a license and their free alternative.
Could your organization recognize the free alternatives and if not what do you think are the obstacles.
Forum Topic: FREE RESOURCES

## Slide 3: introduction
Cultures, structures, and policies can influence both the direction and the outcome of any project.
Project leaders are expected to navigate organizational dynamics skillfully
Leaders can explore options for change, to increase project success
Project agility is more effective and sustained as the organization adjusts to support it

## Slide 4: ORGANIZATIONAL CHANGE MANAGEMENT

## Slide 5: iNTRODUCTION
Organizational change management covers the skills and techniques for influencing changes that support agility

## Slide 6: PMI Managing Change in Organizations: A Practice Guide recommendations
Models for describing change dynamics,
Framework for achieving change, and
Application of change management practices at the project, program, and portfolio levels

## Slide 7: THE RELATIONSHIP BETWEEN CHANGE MANAGEMENT AND AGILE APPROACHES

## Slide 8: DRIVERS FOR CHANGE MANAGEMENT
All projects are about change. However, there are two key factors that further motivate the use of change management practices in an agile context:
  Changes associated with accelerated delivery.
    Agile approaches emphasize delivering project outputs early and often.
    However, the receiving organization may not be fully prepared to incorporate those outputs at an increased pace.
    Customer acceptance of and alignment with project outputs becomes even more prevalent in an agile environment.
  Changes associated with agile approaches.
    Higher degrees of collaboration may require more frequent handoffs between teams, departments, or vendors.
    Decomposing work into iterative prototypes involves rework that could be viewed negatively.
    Leaders should consider change management techniques to address the hurdles of transitioning to the use of agile approaches.
Notes: 1- Successfully discovering and delivering a project's features is not enough. If the organization resists the project's output, then the targeted return on investment is delayed.
2- Organizations just beginning to use agile approaches also experience high degrees of change.

## Slide 9: READINESS FOR CHANGE

## Slide 10: organizational change-friendly characteristics
Executive management's willingness to change;
Organization's willingness to shift the way it views, reviews, and assesses employees;
Centralization or decentralization of project, program, and portfolio management functions;
Focus on short-term budgeting and metrics versus long-term goals;
Talent management maturity and capabilities.

## Slide 11: Organizational roadblock to change
Work is decomposed into departmental silos, creating dependencies that prevent accelerated delivery instead of building cross-functional teams with guidance from centers of competencies.
Procurement strategies are based on short-term pricing strategies, rather than long-term competencies.
Leaders are rewarded for local efficiencies rather than end-to-end flow of project delivery or optimizing the whole (in regard to the organization).
Employees are specialized contributors with limited tools or incentives to diversify their skills instead of building T-shaped specialists.
Decentralized portfolios pull employees simultaneously onto too many projects at once instead of keeping them focused on one project at a time.

## Slide 12: approaches to accelerate a cultural compatibility:
Visible and active executive sponsorship,
Change management practices, including communication and coaching,
Progressively pacing the adoption of agile practices on a project-by project basis
Incremental introduction of agile practices to the team; and
Leading by example by using agile techniques and practices where possible.

## Slide 13: ORGANIZATIONAL CULTURE

## Slide 14: organization's DNA
An organization's culture is its DNA—its core identity.
Culture will always influence the use of agile approaches.
Organizational culture runs along a continuum, from highly predictive plans to lean startup where everything is an experiment.
Although agile approaches fit well with the lean startup culture, a highly predictive organization can encourage empirical measurements, small experiments, and learning so they can move toward agility.

## Slide 15: “Culture eats strategy for breakfast”—Peter Drucker
This statement stresses the importance of people's commitment and passion for a cause.
No matter what strategy or plan you implement with your team, its success is going to be governed by the people implementing the plan.
If the people who are driving the strategy aren't passionate about the change, or worse, are apathetic about their job and their organization, then you stand little chance of implementing the change.
Notes: Peter Ferdinand Drucker
(November 19, 1909 – November 11, 2005)
An Austrian management consultant, educator, and author, whose writings contributed to the philosophical and practical foundations of the modern business corporation.
He invented the concept known as management by objectives and self-control
He has been described as "the founder of modern management".

## Slide 16: CREATING AN ENVIRONMENT OF SAFETY
The most important cultural norm in an organization willing to try any new method or technique is enabling a safe work environment.
Only in a safe, honest, and transparent environment can team members and leaders truly reflect on success and failed projects in order to apply lessons learned.

## Slide 17: ASSESSING ORGANIZATIONAL CULTURE
Notes: In this example, a project leader initiates a conversation about organizational priorities with stakeholders, team members, and senior management.
Those priorities are then recorded as positions on a sliding scale between two extremes.
The results are then used to find agile techniques that best fit with those priorities.

## Slide 18: Tip: Culture versus Structure
Some people insist new organizational structures be installed before any cultural shift can begin.
Others maintain the opposite—those new organizational structures are only superficial adjustments until the collective culture moves in a meaningful direction.
In reality, one cannot progress without the other.
Project leaders wanting to achieve agility should consider the current and future states of both of these aspects in their organization.
Notes: Process Re-engineering
Re-structuring
Evolution
Revolution

## Slide 19: PROCUREMENT AND CONTRACTS

## Slide 20: customer–supplier relationship
“customer collaboration over contract negotiation”
A shared-risk-reward relationship, where all sides win rather than a perspective of winners vs. losers
It is possible to create agile contracts.
Agile is built on a synergy of collaboration and trust.
The supplier can help by delivering value early and often.
The customer can help by providing timely feedback.

## Slide 21: Multi-tiered structure
Project parties can achieve more flexibility by describing different aspects in different documents.
Mostly fixed items (e.g., warranties, arbitration) can be locked in a master agreement.
Meanwhile, all parties list other items subject to change (e.g., services rates, product descriptions) in a schedule of services.
The contract can reference them in the master services agreement.
Finally, more dynamic items such as scope, schedule, and budget can be formalized in a lightweight statement of work.
Isolating the more changing elements of a contract into a single document simplifies modifications and thus flexibility.
Notes: General terms and conditions
Special terms and conditions
Boiler plate
Annexes
Drawings
Itemized price list
Scope of work
Manufacturing Records Book

## Slide 22: Emphasize value delivered
Many vendor relationships are governed by fixed milestones or “phase gates” focused on intermediate artifacts, rather than a full deliverable of incremental business value.
Often, these controls limit the use of feedback to improve the product.
Instead, milestones and payment terms can be structured based on value-driven deliverables in order to enhance the project's agility.

## Slide 23: Fixed-price increments
Rather than lock an entire project scope and budget into a single agreement, a project can decompose the scope into fixed-price microdeliverables, such as user stories.
For the customer, this gives more control over how the money is spent.
For the supplier, it limits the financial risk of over-commitment to a single feature or deliverable

## Slide 24: Not-to-exceed time and materials
Customers incur unwanted risk from a traditional time and materials approach.
One alternative is to limit the overall budget to a fixed amount.
This allows the customer to incorporate new ideas and innovations into the project not originally planned.
When customers want to incorporate new ideas, they will have to manage to a given capacity, replacing original work with new work.
Work should be closely monitored as hours allocated reach their limit.
Also, additional contingency hours could be planned into the maximum budget if considered helpful

## Slide 25: Graduated time and materials
Another alternative is a shared financial risk approach.
In agile, the quality criteria are part of what done means.
Therefore, the supplier can be rewarded with a higher hourly rate when delivery is earlier than the contracted deadline.
Conversely, the supplier would suffer a rate reduction for late delivery.

## Slide 26: Early cancellation option
When an agile supplier delivers sufficient value with only half of the scope completed, the customer should not be bound to pay the remaining half if the customer no longer needs it.
Instead, a contract can offer the customer to buy the remainder of the project for a cancellation fee.
The customer limits budget exposure and the supplier earns positive revenue for services no longer required

## Slide 27: Dynamic scope option
For those contracts with a fixed budget, a supplier may offer the customer the option to vary the project scope at specified points in the project.
The customer can adjust features to fit the capacity.
Then the customer can leverage innovation opportunities, while limiting the supplier's risk of over commitment

## Slide 28: Team augmentation
Arguably the most collaborative contracting approach is to embed the supplier's services directly into the customer organization.
Funding teams instead of a specific scope preserves the customer's strategic discretion on what work should actually be done

## Slide 29: Favor full-service suppliers
In order to diversify risk, customers may seek a multi-supplier strategy
However, the temptation will be to contract the work such that each supplier does only one thing, which creates a web of dependencies before any usable service or product emerges.
Instead, place an emphasis on engagements that deliver full value (as in the idea of completed independent feature sets)

## Slide 30: BUSINESS PRACTICES

## Slide 31: POLICIES AND PRACTICES CHALLANGE
Once teams start to work in a cohesive and cooperative manner, they will challenge internal management policies.
Human resources may notice individual incentives make less sense, and managers may struggle with the performance appraisals of self-organizing employees.
In each case, these are opportunities to review the degree to which existing practices support agile ways of working.
As organizations progress to greater agility, there will be obvious needs for additional business units to change the way they interact and perform their responsibilities.
The changes that have benefited other areas of the organization should now be embraced so the effectiveness of the entire organization can be realized.

## Slide 32: MULTITEAM COORDINATION AND DEPENDENCIES (SCALING)

## Slide 33: FRAMEWORKS
The guidance of the most widespread agile methods such as Scrum and eXtreme Programming focus on the activities of a single, small, usually co-located, cross-functional team.
While this is very useful for efforts that require a single team, it may provide insufficient guidance for initiatives that require the collaboration of multiple agile teams in a program or portfolio.
A range of frameworks (such as the Scaled Agile Framework, Large Scale Scrum, and Disciplined Agile) and approaches (e.g., Scrum of Scrums) have emerged to cater to just such circumstances.
More details on these can be found in Annex A3.

## Slide 34: CONSIDERATIONS
There is more than one way to scale work.
The team might need to scale the work of several agile projects into a single agile program.
Alternatively, the organization can design a structure that supports agile approaches across the entire portfolio.
Teams can achieve successful outcomes even when everything is not completely transformed into an agile approach.
Regardless of the approach, a critical success factor is the healthy agile team.
The goal of large-scale agile projects is to coordinate the efforts of different teams to bring value to customers.
Teams may use a formal framework or apply agile thinking to adjust existing program management practices.
Notes: If using an agile approach for a single team is not successful, do not try to scale up to using it more broadly; instead, address the organizational impediments that prevent teams from working in an agile way.

## Slide 35: AGILE AND THE PROJECT MANAGEMENT OFFICE (PMO)

## Slide 36: AN AGILE PMO IS VALUE-DRIVEN
Any project should deliver the right value, to the right audience, at the right time.
The PMO's objective is to facilitate and enable this goal.
An agile-based PMO approach is based on a customer-collaboration mindset and is present in all PMO programs.
Notes: In many cases, this means the PMO operates as if it were a consulting business, tailoring its efforts to meet specific needs requested by a given project.
-
Some projects may need tools and templates, while others may benefit from executive coaching.

## Slide 37: AN AGILE PMO IS INVITATION-ORIENTED
In order to accelerate progress on a value-based charter, a PMO may be tempted to mandate certain solutions or approaches, for example, to make everyone do it the same way to get some quick wins.
However, a more deliberate perspective incorporates the desire for employee engagement.
This is achieved by inviting only those interested to engage with PMO services.
Higher engagement with PMO practices makes it easier for those practices to be “sticky.”
If the PMO is delivering value to its clients, it is more likely that clients will request its services and adopt its practices.
Notes: Quality Circles

## Slide 38: AN AGILE PMO IS MULTIDISCIPLINARY
Some organizations have been transforming their PMOs into agile centers of excellence that provide such services as:
  Developing and implementing standards
  Developing personnel through training and mentoring
  Multi-project management
  Facilitating organizational learning
  Managing stakeholders
  Recruiting, selecting, and evaluating team leaders
  Executing specialized tasks for projects

## Slide 39: ORGANIZATIONAL STRUCTURE

## Slide 40: key characteristics
Geography
Functionalized structures
Size of project deliverable
Allocation of people to projects
Procurement-heavy organizations

## Slide 41: EVOLVING THE ORGANIZATION

## Slide 42: Initial ranked backlog for changes

## Slide 43: Using backlog and Kanban boards to organize and track change work