## Slide 1
Prepared by Dr. Tarek Mohamed
Project Procurement and
Supply Chain
Lecture 8
PMG 433

## Slide 2
The role of tender management in projects
Lecture 8
PMG 433
Dr. Tarek Mohamed
Prepared by

## Slide 3
Course Agenda
Understand the contents of project tender management.
Describe the work involved in project tendering process.
Relationship Between PMBOK® Guide and Tender Management
Key PMBOK® Documents Used in Tender Management.
Example of Tender Management Process in Projects.
Real-World Companies That Use Formal Tender Management
Chapter

## Slide 4: TENDER MANAGEMENT
Tender Management in Project Management is the structured process of planning, preparing, issuing, evaluating, awarding, and administering tenders (bids) to procure goods, services, or works from external suppliers.
It is a key part of Project Procurement Management and helps ensure that the project selects the most suitable supplier while achieving value for money, transparency, fairness, and compliance with organizational policies.
Definition
Tender Management is the process of managing all activities involved in inviting suppliers to submit bids (tenders), evaluating those bids, selecting the best contractor or supplier, and managing the contract throughout the project.

## Slide 5: TENDER MANAGEMENT
Most projects will, at one stage or another, need to go to the marketplace to procure the expertise, materials, equipment, and services required for development, implementation, or execution.
The way this is done can have a profound impact on project success and profitability.
The economics of top-class procurement are compelling.
With the growth of outsourcing, third-party goods and services can account for between 40 percent and 80 percent of a project or company activity.

## Slide 6: Objectives of Tender Management
Obtain the best value for money.
Ensure fair and transparent competition.
Select qualified and reliable suppliers.
Reduce procurement risks.
Ensure compliance with legal and organizational requirements.
Achieve project objectives within budget and schedule.

## Slide 7: Tender Management Process
Procurement Planning
Identify project procurement needs.
Decide what products or services should be purchased externally.
Develop the procurement strategy.
Prepare the procurement schedule.
Output:
Procurement Management Plan

## Slide 8: Tender Management Process
2. Preparation of Tender Documents
Prepare documents that suppliers need to submit their bids.
Typical contents include:
Statement of Work (SOW)
Technical specifications
Scope of work
Bill of Quantities (BOQ)
Project schedule
Contract terms and conditions
Evaluation criteria
Instructions to bidders

## Slide 9: Tender Management Process
3. Invitation to Tender
The organization announces the procurement opportunity by:
Open Tender
Selective Tender
Limited Tender
Electronic Tender (E-Tender)
Suppliers are invited to submit proposals before the deadline.

## Slide 10: Tender Management Process
4. Receiving and Opening Bids
Receive bids before the closing date.
Securely store submissions.
Open bids according to procurement procedures.
Record all submitted proposals.

## Slide 11: Tender Management Process
5. Bid Evaluation
Evaluate suppliers using predefined criteria such as:
Technical capability
Price
Experience
Quality
Delivery schedule
Financial stability
Past performance
Risk assessment
Many organizations use a weighted scoring model.
Example:
Evaluation Criteria | Weight
Technical proposal | 40%
Price | 30%
Experience | 15%
Delivery schedule | 10%
Financial capability | 5%

## Slide 12: Tender Management Process
6. Negotiation
Negotiate with the preferred supplier regarding:
Price
Delivery dates
Payment terms
Warranties
Scope
Risks
Contract conditions

## Slide 13: Tender Management Process
7. Contract Award
Select the winning bidder.
Obtain approvals.
Sign the contract.
Notify unsuccessful bidders.

## Slide 14: Tender Management Process
8. Contract Administration
Monitor supplier performance throughout project execution activities include:
Performance monitoring
Progress reporting
Quality inspections
Change management
Payment approvals
Claims management
Risk management

## Slide 15: Tender Management Process
9. Contract Closeout
After completing the project:
Verify all deliverables.
Finalize payments.
Resolve claims.
Archive procurement records.
Conduct supplier performance evaluation.
Close the contract.

## Slide 16: Types of Tendering
Type | Description
Open Tender | Any qualified supplier may submit a bid.
Selective Tender | Only shortlisted suppliers are invited.
Limited Tender | A small number of suppliers are invited.
Single-Source Tender | Only one supplier is selected.
Electronic Tender | Tendering is conducted online.

## Slide 17: Common Tender Documents
Invitation to Tender (ITT)
Request for Proposal (RFP)
Request for Quotation (RFQ)
Request for Information (RFI)
Statement of Work (SOW)
Technical Specifications
Bill of Quantities (BOQ)
Draft Contract
Evaluation Criteria Bid Submission Forms

## Slide 18: Roles in Tender Management
Role | Responsibility
Project Manager | Oversees procurement activities and ensures alignment with project objectives.
Procurement Manager | Manages the tendering process.
Technical Experts | Evaluate technical proposals.
Finance Team | Reviews financial aspects of bids.
Legal Team | Reviews contracts and compliance.
Suppliers | Submit bids and execute the contract if selected.

## Slide 19: Benefits of Effective Tender Management
Competitive pricing
Improved supplier quality
Reduced procurement risks
Better contract performance
Increased transparency
Compliance with procurement policies
Improved project success

## Slide 20: Example of Tender Management Process
A construction company plans to build a new office building.
The project team prepares the technical specifications and Statement of Work.
An open tender is advertised.
Six contractors submit bids.
The evaluation committee scores each proposal based on technical capability, price, experience, and schedule.
The highest-ranked contractor is selected.
The contract is negotiated and signed.
The contractor performs the work while the project team monitors quality, schedule, and costs.
After successful completion, the contract is closed and supplier performance is documented.

## Slide 21: Relationship Between PMBOK® Guide and Tender Management
PMBOK® Procurement Process | Tender Management Activities
Plan Procurement Management | Identify procurement requirements, define procurement strategy, determine contract type, prepare procurement management plan, develop tender schedule.
Conduct Procurements | Prepare tender documents, advertise the tender, invite suppliers, receive bids, evaluate proposals, negotiate with bidders, select the winning supplier, award the contract.
Control Procurements | Monitor supplier performance, manage contract execution, approve payments, manage changes, resolve claims, conduct contract closeout.

## Slide 22: Mapping Tender Management Activities to PMBOK®
1. Plan Procurement Management
The PMBOK® Guide focuses on planning before issuing the tender.
Tender management activities include:
Defining procurement objectives
Identifying goods and services to be procured
Selecting the procurement method (open, selective, limited, or single-source tender)
Choosing the contract type (Fixed-Price, Cost-Reimbursable, or Time & Material)
Developing evaluation criteria
Preparing the Procurement Management Plan
PMBOK® Output:
Procurement Management Plan
Procurement Statement of Work (SOW)
Source Selection Criteria
Procurement Documents

## Slide 23: Conduct Procurements
This process corresponds most closely to the core of tender management.
Tender management activities include:
Preparing tender documents
Publishing the invitation to tender
Responding to bidders' questions
Receiving bids
Opening bids
Evaluating technical and financial proposals
Negotiating with suppliers
Selecting the successful bidder
Awarding the contract
PMBOK® Outputs:
Selected Sellers Agreements (Contracts) Resource Calendars
Change Requests (if applicable)

## Slide 24: Control Procurements
After the contract is awarded, tender management shifts to contract administration.
Activities include:
Monitoring supplier performance
Tracking delivery schedules
Inspecting quality
Processing payments
Managing contract changes
Resolving disputes and claims
Closing the contract
PMBOK® Outputs:
Work Performance Information
Procurement Documentation Updates
Closed Procurement Records

## Slide 25
Project Procurement Management (PMBOK®)
│
├───────────────► Plan Procurement Management
│ │
│ ├─ Procurement Strategy
│ ├─ Contract Type
│ ├─ Tender Documents
│ └─ Evaluation Criteria
│
├───────────────► Conduct Procurements
│ │
│ ├─ Issue Tender
│ ├─ Receive Bids
│ ├─ Evaluate Bids
│ ├─ Negotiate
│ └─ Award Contract
│
└───────────────► Control Procurements
│
├─ Monitor Performance
├─ Manage Changes
├─ Approve Payments
├─ Resolve Claims
└─ Close Contract

## Slide 26: Key PMBOK® Documents Used in Tender Management
PMBOK® Document | Purpose in Tender Management
Procurement Management Plan | Defines how procurement activities will be managed.
Statement of Work (SOW) | Describes the work to be performed.
Procurement Documents | Includes the Invitation to Tender (ITT), Request for Proposal (RFP), Request for Quotation (RFQ), and bidding instructions.
Source Selection Criteria | Defines how suppliers will be evaluated.
Contract | Formal agreement with the selected supplier.
Procurement Performance Reviews | Measures supplier performance during contract execution.

## Slide 27: Benefits of Integrating PMBOK® and Tender Management
Ensures procurement aligns with project objectives.
Promotes transparency and fairness in supplier selection.
Supports compliance with organizational and legal requirements.
Improves supplier selection through objective evaluation criteria.
Reduces procurement and contractual risks.
Enhances cost, quality, and schedule performance.
Strengthens contract administration and supplier relationship management.

## Slide 28: Example of Tender Management Process in Projects
Example 1 : Construction Project
Project: Construction of a New Hospital
Project Budget: $50 million
Step 1: Identify Procurement Requirements
The project team determines that the following must be procured from external suppliers:
Construction contractor
Medical equipment
HVAC systems
Elevators
Electrical systems

## Slide 29: Example of Tender Management Process in Projects
Step 2: Prepare Tender Documents
The procurement team prepares:
Statement of Work (SOW)
Technical specifications
Bill of Quantities (BOQ)
Drawings
Contract conditions
Evaluation criteria
Bid submission instructions

## Slide 30
Step 3: Issue the Tender
An Open Tender is advertised.
Five construction companies submit bids.
Example of Tender Management Process in Projects
Company | Bid Price
Company A | $48 million
Company B | $47 million
Company C | $50 million
Company D | $46 million
Company E | $49 million

## Slide 31
Step 4: Evaluate the Bids
The evaluation committee uses a weighted scoring model.
Although Company D submitted the lowest price, Company C achieved the highest overall score due to its superior technical proposal and experience.
Example of Tender Management Process in Projects
Criteria | Weight
Technical Capability | 40%
Price | 30%
Experience | 15%
Project Schedule | 10%
Financial Stability | 5%
Company | Technical | Price | Experience | Schedule | Total Score
A | 38 | 26 | 14 | 9 | 87
B | 35 | 28 | 13 | 8 | 84
C | 39 | 24 | 15 | 10 | 88
D | 32 | 30 | 12 | 8 | 82
E | 37 | 25 | 14 | 9 | 85

## Slide 32
Step 5: Negotiate
Negotiations are held with Company C regarding:
Payment schedule
Completion date
Warranty period
Performance guarantees
Risk allocation
Example of Tender Management Process in Projects

## Slide 33
Step 6: Award the Contract
The contract is signed with Company C.
Step 7: Contract Administration
During construction, the project manager monitors:
Progress against schedule
Construction quality
Safety performance
Cost control
Change orders
Example of Tender Management Process in Projects

## Slide 34
Step 8: Contract Closeout
Upon project completion:
Final inspection is conducted.
Defects are corrected.
Final payment is released.
Contractor performance is evaluated.
Contract documentation is archived.
Example of Tender Management Process in Projects

## Slide 35
Example 2: Information Technology (IT) Company
Company: A commercial bank implementing a new Core Banking System
Procurement Need
Purchase:
Banking software
System implementation services
Staff training
Technical support
Example of Tender Management Process in Projects

## Slide 36
Tender Process
Prepare Request for Proposal (RFP).
Invite software vendors.
Vendors submit technical and financial proposals.
Technical evaluation committee assesses functionality and compliance.
Financial proposals are evaluated.
Vendor demonstrations are conducted.
Contract negotiations take place.
The highest-ranked vendor is selected.
Implementation begins.
Performance is monitored using Service Level Agreements (SLAs)
Example of Tender Management Process in Projects

## Slide 37
Example 3: Pharmaceutical Company
Company: Pfizer (or any large pharmaceutical manufacturer)
Project: Construction of a new sterile manufacturing line
Procurement requirements include:
Cleanroom construction
Production equipment
HVAC systems
Laboratory instruments
Example of Tender Management Process in Projects

## Slide 38
Tender Activities
Develop technical specifications.
Invite pre-qualified suppliers.
Conduct technical evaluation.
Perform site visits to suppliers.
Evaluate financial offers.
Negotiate delivery schedules.
Award contracts.
Monitor installation and commissioning.
Example of Tender Management Process in Projects

## Slide 39
Real-World Companies That Use Formal Tender Management
Company | Typical Procurement Projects
Siemens | Power plants, industrial automation, rail systems
Bechtel | Infrastructure, airports, highways, energy projects
Samsung Engineering | Petrochemical and industrial construction
Toyota | Manufacturing equipment, robotics, production lines
Pfizer | Pharmaceutical facilities, laboratory equipment, packaging lines
Nestlé | Food processing equipment, logistics services, packaging materials
Microsoft | Cloud infrastructure, data center construction, IT services
Shell | Offshore platforms, pipelines, drilling equipment, engineering services

## Slide 40
Tender Management is more than choosing the lowest bidder.
Successful organizations evaluate suppliers based on technical capability, quality, experience, risk, delivery schedule, financial strength, and total value.
This approach aligns with the PMBOK® Guide's emphasis on selecting sellers using predefined evaluation criteria and managing contracts throughout the project lifecycle.
Request for Quotation (RFQ) is mainly used to obtain price quotations for standard products or services
Key Lessons

## Slide 41
Summary of Learning Objectives
Understand the contents of project tender management.
Describe the work involved in project tendering process.
Relationship Between PMBOK® Guide and Tender Management
Key PMBOK® Documents Used in Tender Management.
Example of Tender Management Process in Projects.
Real-World Companies That Use Formal Tender Management

## Slide 42
Morris, P. W., & Pinto, J. K. (Eds.). (2007). The Wiley guide to project technology, supply chain, and procurement management (Vol. 4). John Wiley & Sons.
Schwalbe, K. (2015). Information technology project management. Cengage Learning.
Baily, P., Farmer, D., Crocker, B., Jessop, D., & Jones, D. (2008). Procurement principles and management. Pearson Education.
Supply Chain Council
PMBOK® Guide (Project Management Body of Knowledge),
Essential Reference

## Slide 43
Thank You