## ورقة1
student name |  |  | student Id
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
1 | THREATS | Increase tickets or general costs, as consequence of Economic inflation | high | moderate | Global Oil Prices | Long-term contracting. Diversification of supply sources. | Procurements Manager | مشروع مترو الرياض
2 | THREATS | process, systems and controls shut down duo to electrical failure | high | moderate | Shut down in electrical power | multiple back-up generators for electrical power | Operating Control Center Manager | مشروع مترو الرياض
3 | OPPORTUNITIES | inside metro retailing / sales. | moderate | low | increase number for metro users/citizens | choosing the right products to sale and the right sales representitive | Procurements manager | مشروع مترو الرياض
4 | OPPORTUNITIES | metro mini stations across Riyadh city for depositing airport luggage before flights | low | low | ticket holder | small fees for depositing luggage before flights service | Procurements manager | مشروع مترو الرياض
5
6
7
8
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## ورقة2 (hidden)
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low