## Slide 1
Project Resources and Time Management
Lecture 10
PMG 605
Dr. Eng. Abdullah Jameel Halawany
Prepared by
MS Project as a Tool for Resources and Time Management

## Slide 2
Session Outline
Lecture
10
10–2
MS Project as a Tool for Resources and Time Management
MS Project 2019 Overview
Set Project Calendar
WBS
Task Type
Add and Level Resources
Timeline
Reports

## Slide 3: Add A Holiday To The Project Calendar
10–3

## Slide 4
10–4
Create WBS codes in Project desktop
Lecture
10

## Slide 5
10–5
Add A Milestone
Lecture
10
Before your project gets rolling, you will probably want to mark its major goals with milestones.
Create a milestone with zero duration
Add a milestone with a duration

## Slide 6: Create A Milestone With Zero Duration
10–6

## Slide 7: Add A Milestone With A Duration
10–7

## Slide 8: Level Resource Assignments
10–8

## Slide 9: Modify Leveling Settings
10–9

## Slide 10: Modify Leveling Settings
10–10

## Slide 11: Some Tips You Can Use While Leveling
10–11

## Slide 12: Some Tips You Can Use While Leveling
10–12

## Slide 13
10–13
The POM+ Project - Big Kola Company
Lecture
10

## Slide 14: The POM+ Project - Big Kola Company – Part 1
10–14

## Slide 15
10–15
The POM+ Project - Big Kola Company
Lecture
10
Develop the WBS outline using the software available.

## Slide 16
10–16
The POM+ Project - Big Kola Company
Lecture
10
2. Use this file and the information provided below to create a project schedule.
The following holidays are observed:
  New Yer January 1,
  July 4th,
  Labor Day (first Monday in September),
  Thanksgiving Day (4th Thursday in November),
  December 25 and 26.
The project team works eight-hour days, Saturday through Thursday.

## Slide 17
10–17
The POM+ Project - Big Kola Company
Lecture
10
The project will begin on November 3 , 2025
Based on this schedule, submit a memo that answers the following questions:
  a. When is the project estimated to be completed? How many working days will it take?
  b. What is the critical path?
  c. Which activity has the most total slack?
  d. How sensitive is this network?
  e. Identify two sensible milestones and explain your choice.

## Slide 18: The POM+ Project - Big Kola Company
10–18

## Slide 19: The POM+ Project - Big Kola Company
10–19

## Slide 20: The POM+ Project - Big Kola Company
10–20

## Slide 21: The POM+ Project - Big Kola Company
10–21

## Slide 22
10–22
The POM+ Project - Big Kola Company – Part 2
Lecture
10
Remember the old saying, “A project plan is not a schedule until resources are committed.” This exercise illustrates this sometime subtle, but important point.
Using your files from Part 1, input resources and their costs if you have not already done so.

## Slide 23
10–23
The POM+ Project - Big Kola Company – Part 2
Lecture
10

## Slide 24
10–24
The POM+ Project - Big Kola Company – Part 2
Lecture
10

## Slide 25
10–25
The POM+ Project - Big Kola Company – Part 2
Lecture
10
Remember the old saying, “A project plan is not a schedule until resources are committed.” This exercise illustrates this sometime subtle, but important point.
Using your files from Part 1, input resources and their costs if you have not already done so.
Prepare a memo that addresses the following questions:
1. Which if any of the resources are over allocated?
2. Assume that the project is time constrained and try to resolve any over allocation problems by leveling within slack. What happens?
3. Assume the project is resource constrained and resolve any over allocation problems by leveling outside of slack. What happens?

## Slide 26
10–26
The POM+ Project - Big Kola Company – Part 2
Lecture
10
1. Which if any of the resources are over allocated?

## Slide 27
10–27
The POM+ Project - Big Kola Company – Part 2
Lecture
10
1. Which if any of the resources are over allocated?

## Slide 28
10–28
The POM+ Project - Big Kola Company – Part 2
Lecture
10
1. Which if any of the resources are over allocated?

## Slide 29
10–29
The POM+ Project - Big Kola Company – Part 2
Lecture
10
1. Which if any of the resources are over allocated?

## Slide 30: The POM+ Project - Big Kola Company – Part 2
10–30
2. Assume that the project is time constrained and try to resolve any overallocation problems by leveling within slack. What happens?

## Slide 31: The POM+ Project - Big Kola Company – Part 2
10–31
2. Assume that the project is time constrained and try to resolve any over allocation problems by leveling within slack. What happens?

## Slide 32: The POM+ Project - Big Kola Company – Part 2
10–32
Before Leveling within Slack
After Leveling within Slack

## Slide 33: The POM+ Project - Big Kola Company – Part 2
10–33
3. Assume the project is resource constrained and resolve any over allocation problems by leveling outside of slack. What happens?

## Slide 34: The POM+ Project - Big Kola Company – Part 3
10–34
3. Assume the project is resource constrained and resolve any over allocation problems by leveling outside of slack. What happens?

## Slide 35: The POM+ Project - Big Kola Company – Part 3
10–35
3. Assume the project is resource constrained and resolve any over allocation problems by leveling outside of slack. What happens?

## Slide 36
10–36
The POM+ Project - Big Kola Company – Part 3
Lecture
10
Top management has accepted the April 16th completion schedule created at the end of Part 2. Prepare a brief memo that addresses the following questions:
1. How much will the project cost? What is the most expensive activity?

## Slide 37: The POM+ Project - Big Kola Company – Part 3
10–37

## Slide 38: The POM+ Project - Big Kola Company – Part 3
10–38

## Slide 39: The POM+ Project - Big Kola Company – Part 3
10–39
Baseline Cost
$1,692,000.00

## Slide 40: The POM+ Project - Big Kola Company – Part 3
10–40
Chart: 
| Need survey | Set product specs | Shelf life report | Nutrition report | R&D Development | Secure fruit suppliers | Equipment rehab | Production trials | Quality trials | Quality metrics | Quality training | Initial Production Begin | Market testing | Package design | Select distributors | Complete FDA certification | Register trademark | Product legally Registered | Prepare product launch | Project completed
Baseline Cost | 64000 | 57600 | 19200 | 9600 | 0 | 9600 | 528000 | 235200 | 86400 | 12000 | 136800 | 0 | 96000 | 31200 | 80000 | 43200 | 14400 | 0 | 268800 | 0

## Slide 41
10–41
Timeline
Lecture
10

## Slide 42
10–42
The POM+ Project - Big Kola Company – Part 4
Lecture
10
Assume that today is February 8, 2026, and Table A2.3 contains the tracking information for the project up till now. Enter this information into your saved baseline file and prepare a status report for the first three months of the POM+ project.
Your status report should also address the following questions:
1. How is the project progressing in terms of cost and schedule?
2. What activities have gone well? What activities have not gone well?
3. What are the CPI and SPI of the project?
4. What is the forecasted cost at completion (EACf)?
5. What is the estimated date of completion?

## Slide 43
10–43
The POM+ Project - Big Kola Company – Part 4
Lecture
10
Task Name | Actual Start | Actual Finish | Actual Duration
Need survey | 11/3/2025 | 11/29/2025 | 22 days
Set product specs | 11/30/2025 | 12/20/2025 | 18 days
Shelf-life report | 12/23/2025 | 1/4/2026 | 10 days
Nutrition report | 1/7/2026 | 1/11/2026 | 4 days
Equipment rehab | 12/23/2025 | NA | 23 days
Status Report February 8, 2026

## Slide 44: The POM+ Project - Big Kola Company – Part 4
10–44

## Slide 45
10–45
The POM+ Project - Big Kola Company – Part 4
Lecture
10
SPI = EV/PV = $555,200.00 / $982,080.00 = 0.57
CPI = EV / AC = $555,200.00 / $563,520.00 = 0.99
SPI | CPI
0.57 | 0.99
Name | Remaining Cost | Baseline Cost | Cost Variance | EAC | ACWP | BCWS | BCWP | Finish
POM+Project | $1,136,800.00 | $1,692,000.00 | $8,320.00 | $1,717,355.62 | $563,520.00 | $982,080.00 | $555,200.00 | 4/26/2026

## Slide 46
10–46

## Slide 47
10–47
Change The Task Type For More Accurate Scheduling
Lecture
10
You just assigned a few people to a task, and the task duration got longer, not shorter as you expected. Or maybe the reverse happened. Either way, you’re stumped.
Some tasks, such as curing cement, take a fixed amount of time no matter how workers are assigned to pouring the cement.
Others, like building roads or software, grow or shrink in their durations, depending on the people and resources applied to them.
To change the task types to better reflect these realities, double-click the task, click Advanced, and change the task type.

## Slide 48
10–48
How Task Types Change Your Schedule
Lecture
10
Project uses a scheduling formula that relates the three values of work, duration, and assignment units:
Work = Duration x Units
Setting a task’s type allows you to “fix” (or make unchangeable) one of these values.
Fixing one of the values places a priority on that value by telling Project not to change it when the other two values change.

## Slide 49
10–49
Work = Duration x Units
How Task Types Change Your Schedule
Lecture
10
Work: Total Resource Hours required to Complete the task (Hours)
Duration: Number of Days to complete the task (Days)
Units: Number of Resource (Hours/Day) required to Complete the Task
Here’s a handy table to help keep all the moving parts of the scheduling formula in mind.

## Slide 50
10–50
How Task Types Change Your Schedule
Lecture
10
https://support.microsoft.com/en-us/office/change-the-task-type-for-more-accurate-scheduling-b0b969ad-45bc-4e9e-8967-435587548a72

## Slide 51
10–51
Project Resources And Time Management: Latest Developments
Lecture
10
The field is shifting fast toward AI-augmented planning, data-driven resourcing, and human-centered time practices.
Artificial intelligence (AI) is revolutionizing how project managers handle resource allocation and time management, especially in distributed and hybrid teams.

## Slide 52
10–52
AI for Resource Optimization in Project Management
Lecture
10
Data-driven allocation: AI analyzes skills, availability, and workload across multiple locations to recommend the best resource assignments.
  Example: A global IT project uses AI to match cybersecurity experts in Europe with urgent tasks while balancing workloads for developers in Asia.
Predictive issue detection: AI forecasts bottlenecks, overallocations, or risks before they occur.
  Example: In a construction project, AI predicts that a shortage of skilled electricians will delay milestones, prompting managers to hire contractors early.

## Slide 53
10–53
Advanced Strategies Enabled by AI
Lecture
10
Skills-based allocation: AI ensures tasks are assigned to the most qualified person, not just the next available.
Scenario modeling: Managers can simulate “what-if” situations (e.g., losing a resource, shifting deadlines) to see impacts instantly.
Dynamic prioritization: AI continuously reorders tasks based on changing dependencies and deadlines.

## Slide 54
Resources
Project Management
The Managerial Process
Fifth Edition
By: Erik W. Larson
Oregon State University
Clifford F. Gray
Oregon State University
10-48

## Slide 55
Thank You