## Slide 1
Prepared by Dr. Usama Al-Fendi
Project Risk Management
Lecture 10
PMG 510
Project Risk Management

## Slide 2
Lecture Organization
Lecture
10
www.midocean.ae
Project Risks in a Turbulent Environment

## Slide 3
Lecture Organization
Lecture
10
www.midocean.ae
Introduction to Risk in Turbulent Environments.
Geopolitical Risk and Its Characteristics.
Traditional Risks vs Systemic Risks.
Geopolitical Context and Regional Dynamics.
Supply Chain Disruptions and Logistics Risks.
Energy Price Shocks and Cost Structures.
Macroeconomic and Financial Risks.
Advanced Risk Management Tools

## Slide 4
General Framework
Lecture
10
www.midocean.ae
The business environment in the Middle East represents a vivid example of what is known as highly turbulent environments, where economic, financial, and geopolitical factors intersect in complex ways. This necessitates a fundamental shift in how project risks are understood and managed. It is no longer sufficient to rely on traditional risk management tools; instead, a dynamic and strategic perspective must be adopted—one that accounts for the evolving and unpredictable nature of risks.

## Slide 5
Definition of Risk in the Context of Geopolitical Crises
Lecture
10
www.midocean.ae
Traditionally, risk is defined as:
“the probability of an undesirable event occurring and its impact on project objectives.”
However, this definition becomes insufficient when dealing with geopolitical crises, as such risks exhibit fundamentally different characteristics.

## Slide 6
Definition of Risk in the Context of Geopolitical Crises
Lecture
10
www.midocean.ae
In this context, project risks can be defined as:
“A set of unexpected or semi-expected threats arising from political, military, or economic shifts at the regional or international level, which directly or indirectly affect project continuity, cost, schedule, quality, and even economic feasibility.”

## Slide 7
Characteristics of Geopolitical Risks:
Lecture
10
www.midocean.ae
High impact: may lead to complete project shutdown
Low predictability: difficult to model accurately
Rapidly evolving: change over short periods
Transnational: not confined to one country
Interconnected: affect multiple dimensions simultaneously (financial, operational, logistical)

## Slide 8
Characteristics of Geopolitical Risks:
Lecture
10
www.midocean.ae
Practical Example
Disruptions in shipping routes or rising energy prices are not merely “operational risks,” but direct consequences of geopolitical factors, elevating risk from the project level to the entire economic system.

## Slide 9
Difference Between Traditional Risks and Systemic Risks
Lecture
10
www.midocean.ae
First: Traditional Risks
These arise within the project boundaries or within a relatively controllable scope, such as:
Supplier delays
Cost overruns
Design errors
Weak human resource management

## Slide 10
Difference Between Traditional Risks and Systemic Risks
Lecture
10
www.midocean.ae
First: Traditional Risks
Characteristics:
Identifiable
Quantifiable
Relatively controllable
Limited impact within the project

## Slide 11
Difference Between Traditional Risks and Systemic Risks
Lecture
10
www.midocean.ae
Second: Systemic Risks
Systemic risks originate outside the project and affect entire economic or sectoral systems, often spreading across sectors.
Definition: “Macro-level risks that cause widespread disruptions in economic, financial, or logistical systems, affecting multiple projects and organizations simultaneously.”

## Slide 12
Difference Between Traditional Risks and Systemic Risks
Lecture
10
www.midocean.ae
Second: Systemic Risks
Characteristics:
Non-isolatable
Cascading effects
Wide impact across the economy
Confidence-driven (e.g., financial crises)
Difficult to predict and model

## Slide 13
Required Shifts in Project Management
Lecture
10
www.midocean.ae
Shift toward flexibility
  Adaptive planning
  Iterative project phases
Scenario-based planning
  Best-case
  Base-case
  Worst-case

## Slide 14
Required Shifts in Project Management
Lecture
10
www.midocean.ae
Decision-making under uncertainty
  Judgment-based decisions
  Reduced reliance on purely quantitative models
Enhanced responsiveness
  Faster adaptation
  Reduced decision-making time

## Slide 15
Geopolitical Context and Its Impact on Projects
Lecture
10
www.midocean.ae
Geopolitics has become a key determinant of the business environment. Projects no longer operate in purely economic contexts, but within a complex global system influenced by conflicts, alliances, energy security, and strategic routes.

## Slide 16
Implications of Conflict with Iran on the Middle East
Lecture
10
www.midocean.ae
Any military or political escalation involving Iran represents a strategic turning point due to its geographic position, energy market influence, and regional role.

## Slide 17
Implications of Conflict with Iran on the Middle East
Lecture
10
www.midocean.ae
A. Economic:
Rising oil and gas prices
Increased inflation in energy-importing countries
Decline in foreign investments
Dimensions of Impact:

## Slide 18
Implications of Conflict with Iran on the Middle East
Lecture
10
www.midocean.ae
B. Financial:
Currency volatility
Higher financing costs (risk premium)
Stock market instability
Dimensions of Impact:

## Slide 19
Implications of Conflict with Iran on the Middle East
Lecture
10
www.midocean.ae
C. Logistical:
Threats to maritime shipping routes
Supply chain disruptions
Increased transport and insurance costs
Dimensions of Impact:

## Slide 20
Implications of Conflict with Iran on the Middle East
Lecture
10
www.midocean.ae
D. Institutional:
Reassessment of project feasibility
Delays or cancellations
Greater focus on crisis management
Dimensions of Impact:

## Slide 21
Implications of Conflict with Iran on the Middle East
Lecture
10
www.midocean.ae
Cost instability
Schedule disruptions
Reduced ROI
Increased risk of failure
Impact on Projects:

## Slide 22
Strategic Importance of the Strait of Hormuz
Lecture
10
www.midocean.ae
The Strait of Hormuz is one of the world’s most critical chokepoints:
Carries ~20% of global oil trade
Key route for LNG exports
Strategic leverage point in global conflicts

## Slide 23
Scenario: Closure or Disruption of the Strait
Lecture
10
www.midocean.ae
• Sharp increase in energy prices
Inflation resulted from increasing cost of production
• Supply chain disruptions
• Rising transport and insurance costs
Immediate Effects:

## Slide 24
Scenario: Closure or Disruption of the Strait
Lecture
10
www.midocean.ae
Budget overruns
Schedule delays
Reduced quality
Potential loss of feasibility
Project-Level Impact:

## Slide 25
Scenario: Closure or Disruption of the Strait
Lecture
10
www.midocean.ae
Supply chain restructuring
Shift toward nearshoring and diversification
Long-Term Effects:

## Slide 26
Geopolitics and Business Continuity
Lecture
10
www.midocean.ae
Business Continuity Definition:
The ability to maintain or quickly recover operations during disruptions.
Geopolitical Impact:
Supply interruptions
Resource shortages
Stakeholder pressure
Integration Requirement:
Risk Management must be integrated with Business Continuity Planning (BCP).

## Slide 27
Energy Price Shocks and Their Impact
Lecture
10
www.midocean.ae
Energy is a critical input across all economic activities.
Impacts:
Increased operating and production costs
Reduced profit margins
Higher break-even points
Lower project feasibility (NPV decline)

## Slide 28
Energy Price Shocks and Their Impact
Lecture
10
www.midocean.ae
Financial Forecasting Risks:
Budget uncertainty
Model inaccuracy
Cash flow instability

## Slide 29
Global Supply Chain Disruptions
Lecture
10
www.midocean.ae
Key Effects:
Increased freight costs
Delays and uncertainty
Logistics bottlenecks
Strategic Shift:
From efficiency → resilience
Reshoring / Nearshoring

## Slide 30
Global Supply Chain Disruptions
Lecture
10
www.midocean.ae
Impact on Projects:
Schedule delays
Cost overruns
Quality degradation

## Slide 31
Macroeconomic and Financial Risks
Lecture
10
www.midocean.ae
Imported Inflation
Higher input costs
Profit margin pressure
Budget instability

## Slide 32
Macroeconomic and Financial Risks
Lecture
10
www.midocean.ae
Exchange Rate Volatility
Increased import costs
Revenue instability
Planning challenges

## Slide 33
Macroeconomic and Financial Risks
Lecture
10
www.midocean.ae
Rising Interest Rates
Higher cost of capital
Reduced project feasibility
Limited access to financing

## Slide 34
Macroeconomic and Financial Risks
Lecture
10
www.midocean.ae
Liquidity Risk
Inability to meet short-term obligations
Operational disruptions
Potential project collapse

## Slide 35
Compound Risks
Lecture
10
www.midocean.ae
Definition:
Risks resulting from the interaction of multiple risk types.
Cascading Risks Example:
Oil disruption → energy price increase → cost rise → delays → reduced ROI → financing difficulty
Management Tools:
Network mapping
Scenario analysis
Stress testing

## Slide 36
Advanced Risk Management Tools
Lecture
10
www.midocean.ae
Scenario Planning
Multiple future possibilities
Improved decision-making
Stress Testing
Simulating extreme conditions
Identifying breaking points

## Slide 37
Advanced Risk Management Tools
Lecture
10
www.midocean.ae
Sensitivity Analysis
Identifying key risk drivers
AI in Risk Prediction
Predictive analytics
Sentiment analysis
Pattern recognition

## Slide 38
Advanced Risk Management Tools
Lecture
10
www.midocean.ae
Early Warning Indicators
Financial, operational, external signals
Proactive risk response

## Slide 39
Mitigation and Adaptation Strategies
Lecture
10
www.midocean.ae
Key Strategies:
Supplier and energy diversification
Financial hedging
Business continuity planning
Organizational resilience

## Slide 40
Managing Extreme Uncertainty
Lecture
10
www.midocean.ae
Key Approaches:
Decision-making under pressure
Agile project management
Continuous reprioritization

## Slide 41
Role of Project Managers in Crises
Lecture
10
www.midocean.ae
Transformation:
From:
Plan executor
To:
Strategic risk leader
Required Skills:
Strategic thinking
Crisis management
Stakeholder communication

## Slide 42
Role of Project Managers in Crises
Lecture
10
www.midocean.ae
New Role:
Decision-maker
Risk analyst
Crisis leader

## Slide 43
Thank You