## ورقة1
student name |  | Afnan D Alzahrani | student Id | 2021206147
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
1 | OPPORTUNITIES | freedom of mobility | high | moderate | metro and bus wide networks | establish private lane for bus to move faster connect metro and bus networks to google maps | project manger | مشروع مترو الرياض
2 | OPPORTUNITIES | Improve air quality | high | moderate | reducing road traffic by using metro or bus | low cost fees to use the metro or bus plant trees along metro side | envriomntal manger | مشروع مترو الرياض
3 | THREATS | traffic accidents increment | high | high | increase in population incerease in oil prices | encourge people to use the metro and bus. Broadcast helpful info to public in how to use the metro and bus | project manger | مشروع مترو الرياض
4 | THREATS | fire in a metro station | high | low | flammable substance electric short circuit intentional fire | apply security measure apply periodic maintenance | Safety manager | مشروع مترو الرياض
5
6
7
8
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## ورقة2 (hidden)
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low