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	Activity
	Work Package
	Description
	Time (DAY)
	Dependencies
	Start Date
	Due Date

	A
	1.1.
	Brand & Logo
	40
	-
	01/01/2022
	02/10/2022

	B
	1.2.
	Media Sponsor
	15
	A
	02/10/2022
	02/20/2022

	C
	1.3.
	Social Media
	30
	A
	02/10/2022
	03/10/2022

	D
	2.1
	Select Location
	15
	A
	02/10/2022
	02/25/2022

	E
	2.2.1.
	Civil defense requirement
	15
	B
	02/20/2022
	03/07/2022

	F
	2.2.2.
	Government permits
	60
	C
	03/10/2022
	05/10/2022

	G
	2.2.3.
	Insurance
	40
	F
	05/10/2022
	06/20/2022

	H
	2.3.
	Layout Design
	10
	E,D
	03/07/2022
	04/01/2022

	I
	2.4.
	Prepare Site
	50
	G
	06/20/2022
	08/10/2022

	J
	2.5.
	Install & test security System
	10
	H
	04/01/2022
	04/06/2022

	K
	3.1.
	Supplier agreements
	15
	F
	06/14/2022
	06/24/2022

	L
	3.2.
	Equipment installation
	25
	I,K
	08/10/2022
	09/05/2022

	M
	3.3.
	Material supply
	15
	J
	04/06/2022
	04/26/2022

	N
	4.1.
	Packaging style
	20
	B
	03/06/2022
	03/21/2022

	O
	4.2.
	Packaging tools & materials
	15
	N,E
	03/07/2022
	03/17/2022

	P
	5.1.
	Identifying categories
	15
	O
	03/17/2022
	03/27/2022

	Q
	5.2.
	Interviews
	40
	M,L
	09/05/2022
	10/15/2022

	R
	5.3.
	Candidacy
	10
	P,M
	05/01/2022
	05/26/2022

	S
	5.4.
	Hiring
	15
	M
	06/18/2022
	07/08/2022

	T
	5.5.
	Training
	40
	Q
	10/15/2022
	11/25/2022

	U
	6.1.
	Equipment test
	15
	X,R
	04/21/2022
	05/01/2022

	V
	6.2.
	Material test
	10
	U
	06/29/2022
	07/09/2022

	W
	6.3.
	Product test
	20
	S,T
	11/25/2022
	12/15/2022

	X
	6.4.
	Packaging test
	25
	P
	03/27/2022
	04/01/2022

	Y
	6.5.
	Quality & safety test
	20
	V,W
	12/15/2022
	12/31/2022


	[image: ]

	[image: ]



Public
Public
Public
image2.png
Schadule Network Diagram

Activity List
s[5 [ 90
L X
20 |35
50 [15] 65 65 [10] 75 7 [10] 85 115 5] 140 140] 10] 150
- N o 3 -] R - u
2%5] | 280 0] [ 2%0 20] |30 3o [325 2 |3
] 150] 10] 160 5] 20] 365
L v
40 [10] 50 50 | 15 65 65 | 25| %0 0]s]|s 95 115 115 20] 135 2 |38 ES L
.| 5 e H | f - [l - s
25 235 25 250 250 275 275 280 280 300 30 325 I
1 25| 20] 345
2u5] a0] 265
I 3
25| 285
245 285] 40] 325
25 5| |35





image3.png
NaME
- = Fiberglass Project
A-1.1.8r2nd &Logo
5-1.2. Media Sponsor
€- 13,5003l Media
D- 21 Select Location
£-221.Cil defense requirement
F-222 Govemment permits
G- 223, Insurance
H- 23, Layout Design
|24 prepare s
3-25.Instal & test securty System
K31 Suppier sgresments
L- 32 Equipment instalation
M- 33, Material supply
N-4.1. Packaging styie
- 42 Packaging too's & materisls
P-5.1. Identifying categories
Q-52 Intenvews.
R-53.Candidacy.
5-s4Hing
T-55.Taining
U-6:1. Equipment test
V- 62, Material test
W- 63, Product test
-84 Packaging test

¥-65.Quality & safety test

© £ 221 il deensereqirement

N Y ——,

@ - 25. st e securiy System

Lg © G- 223 msurnce
+-[.| @ 23 vt

R e

L+q [ YT ——

© =-53 Gy

U IR

C___al
 EBNRRNERRNNNNNN

© a-52 ntevens

AMANNN

@ -5 Tining

SRR

6.4, Packaging test

V@D © v s

D O ity syt




image1.emf
Fiberglass Factory

1. Marketing

1.1. Brand & Logo

2. Site

2.1. Select Location

2.3. Layout Design

2.5. Install & test 

security System

2.2.3. Insurance

2.2. Permits

2.2.1. Civil defense 

requirement

2.2.2. Government 

permits

1.2. Media Sponsor

3. Preparation

3.2. Equipment 

installation

3.3. Material supply

4. Packaging

4.1. Packaging style

4.2. Packaging tools 

& materials 

5. Staff

5.1. Identifying 

categories

5.2. Interviews

3.1. Supplier 

agreements

5.3. Candidacy

5.4. Hiring 

5.5. Training

6. Testing

6.1. Equipment test

6.2. Material test

6.3. Product test

6.4. Packaging test 

6.5. Quality test

2.4. Prepare Site

1.3. Social Media


Microsoft_Visio_Drawing.vsdx
Fiberglass Factory
1. Marketing
1.1. Brand & Logo
2. Site
2.1. Select Location
2.3. Layout Design
2.5. Install & test security System
2.2.3. Insurance
2.2. Permits
2.2.1. Civil defense requirement
2.2.2. Government permits
1.2. Media Sponsor
3. Preparation
3.2. Equipment installation
3.3. Material supply
4. Packaging
4.1. Packaging style
4.2. Packaging tools & materials
5. Staff
5.1. Identifying categories
5.2. Interviews
3.1. Supplier agreements
5.3. Candidacy
5.4. Hiring
5.5. Training
6. Testing
6.1. Equipment test
6.2. Material test
6.3. Product test
6.4. Packaging test
6.5. Quality test
2.4. Prepare Site
1.3. Social Media



