## Contract Management Risk Reg.
CONTRACT MANAGEMENT RISK REGISTER |  | RISK ITEM DESCRIPTION | RISK CATEGORY | RISK LIKELIHOOD | RISK CONSEQUENCE | RISK RATING
NEC (New Engineering Contract) risk register can be used to record any project risks |  | Conveyor speed can be changed | Design Information | Possible | Moderate | MEDIUM
RISK ID: R01
PROJECT ITEM: 3.12
|  | Equipment from China delayed at customs | Delay | Likely | Minor | MEDIUM
COMPANY: | RISK ID: R02
Engineering Experts LLC | PROJECT ITEM: 4.02
CLIENT: |  | Calculation data access restricted | Access | Unlikely | Low | LOW
Best Consumers gmbh | RISK ID: R03
PROJECT ITEM: 5.11
PROJECT:
Big factory construction (#L235876-1123) |  | Not enough space for row materials to pass | Works Area | Possible | Major | HIGH
RISK ID: R04
PROJECT ITEM: 7.22
Project risk is defined as an uncertain event or condition which has either a negative or positive impact on a project. The negative impact of a project risk item can be quantified by risk rating. The rating is determined by measuring the associated likelihood of occurrence and level of consequence. As shown in the table (which you can remove), a sample risk matrix can be used to determine the risk rating. The scale of likelihood is standardised as almost certain, likely, possible, unlikely, and rare; the scale of consequence is standardised as serious, major, moderate, minor, and low; and the scale of risk rating is standardised as extreme, high, medium, low, and negligible.
|  | Large number of unexperienced employees | Workmanship | Likely | Minor | MEDIUM
RISK ID: R05
PROJECT ITEM: 6.17
|  | Inspection findings on safety equipment | Safety | Rare | Moderate | LOW
RISK ID: R06
PROJECT ITEM: 5.11

## ©
© TemplateLab.com