## Slide 1
PMG 202
Project Planning
Prepared by Dr. Maryam ZORGUI
Lecture 7
PART I :
Initiate & Plan a Project
Project
Schedule, Budget, Risks
Communication
&
Plan

## Slide 2: In the previous lessons…
Project Planning is all about choosing and designing effective policies and methodologies to attain Project Objectives.
The Project Planning Phase refers to:
Developing a Project to make it ready for Investment.
Determines the jobs/tasks required to attain Project Objectives.
Lecture 7

## Slide 3: In the previous lessons…
The project planning stages are enlisted below:
Identifying the key project sponsors and stakeholders, to determine the basis of project scope, budget, and time-frame for project execution.
Upon enlisting the stake-holder requirements, prioritizing/setting project objectives.
Identifying the project deliverables required to attain the project objectives.
Creating the project schedule.
Identifying the project risks, if any, and develop suitable mitigation plans.
Communicating and presenting the project plan to stakeholders.
Lecture 7

## Slide 4: Syllabus .
II- Project Budget
I- Project Schedule
III- Project Risks
V- Project Communication
IV- Project Plan
Lecture 7

## Slide 5: I- The Project Schedule
I-1- What is a Project Schedule?
We can’t expect a ragingly successful Project without a great Schedule.
A list of required tasks along with the time and the Resources needed will help you arrive at your destination as planned.
Project Scheduling is an important skill for any Project Manager, even if you think it’s a really simple Project.

## Slide 6: I- The Project Schedule
A Project Schedule is a timetable that shows the start and end date of all project tasks, how the tasks relate to each other and usually which team members or other resources are responsible for delivery.
It is a dynamic document that is created during initial the Planning stage. The approved Project Schedule acts as a baseline to work to, but it is maintained and updated throughout the Project as things change.
While schedules are often thought of as planning and control tools, they are also critical communication tools for Team members and Stakeholders.

## Slide 7: I- The Project Schedule
The project schedule:
outlines the time needed for the required tasks
establishes milestones to be met to complete the project on time
allocates resources across tasks
can be presented in various forms to suit different stakeholders

## Slide 8: I- The Project Schedule
I-2- The 3 main types of Project Schedule
There are many ways that the Project Schedule can be displayed to meet the needs of the target audience using it.
Three commonly used schedule formats are the:

## Slide 9: I- The Project Schedule
I-3- The benefits of effective Project Scheduling
The Project Schedule guides the Project Team as they deliver the Project.
It communicates progress to the Team, Management, and other Stakeholders.
Done well, it makes the entire Project run more smoothly and helps you finish up on time and on budget.

## Slide 10: I- The Project Schedule
The Project Schedule:
Contributes heavily to Project Success.
Provides a clear roadmap to everyone at the beginning of the Project.
Manages Stakeholder expectations.
Monitors and communicates Project Progress.
Ensures buy-in and accountability for Tasks and Deadlines.
Lets the Team know which Tasks rely on others.
Serves as an early warning system for potential Project issues.
Reserves your Resources for when you need them.

## Slide 11: I- The Project Schedule
I-4 -Project scheduling tools and techniques
Project Managers use a range of tools and techniques to create, track and control their Project Schedules.
These days, the tools are almost always digital.
Here’s a brief description of some of the most
common tools and techniques:

## Slide 12: I- The Project Schedule

## Slide 13: I- The Project Schedule

## Slide 14: I- The Project Schedule

## Slide 15: I- The Project Schedule

## Slide 16: I- The Project Schedule

## Slide 17: I- The Project Schedule

## Slide 18: I- The Project Schedule
I-5- Getting started with your Project Schedule
When you are first planning your project, ask yourself these three key questions.
If you have scoped these answers, completing a full Project
schedule will be much easier.

## Slide 19: I- The Project Schedule
I-6- How to do Project Scheduling
Scheduling is part of the planning process. Some simple steps to effectively schedule your projects are to:
Confirm the project activities: make sure they cover your Project Scope
Sequence activities: determine which order the tasks need to be completed
Determine dependencies: identify tasks that rely on each other
Determine durations: accurately estimate how long each task will take
Establish milestones: set the key dates that need to be met
Allocate resources: internal staff, contractors, tools, and workspaces
Assess Risks: and decide how it will be dealt with in your schedule

## Slide 20: I- The Project Schedule
8-Define baseline schedule: taking into account the dependencies, sequence, resources, durations, and risks, lay out all tasks on a timeline
9-Monitor and control: decide how you will monitor, control and report on any changes to the schedule.

## Slide 21: II- Project Budget
II-1- What is a Project Budget?
A Project Budget is the total estimated cost of completing each project activity over each phase of a Project.
It’s important as it helps set expenditure expectations and is critical in getting project approval, ensuring funds are ready at the right time, and measuring performance.
It’s a dynamic document, continuously monitored, reviewed, and updated throughout the project.

## Slide 22: II- Project Budget
“The Budget is your plan. It’s the baseline that lets you measure your performance against the actual costs as the project moves forward. It helps you hit targets, answer questions, and there’s just the satisfaction of knowing you’re on track.” Les Carleton, Program Director and AIPM NSW Chapter Councillor
Notes: The NSW Chapter is a thriving and active group of project professionals with AIPM: The Australian Institute of Project Management

## Slide 23: II- Project Budget
II-2- What are the components of a Project Budget?
Project Budgets contain all the costs associated with the project.
It generally includes:
* Labour costs: employee wages, benefits, payroll taxes, and overheads.
* Material procurement costs: goods, services, equipment, and supplies needed for the project that come from external providers.

## Slide 24: II- Project Budget
Under each of these categories, the costs can usually be separated into two broad categories:
* Fixed costs: these are set for the project and will not change. For example, if you need a certain quantity of a particular item to deliver your project and you have a firm quote from a supplier, this is a fixed cost.
* Variable costs: these change based on activity. For example, if you have a subcontractor working by the hour on your project and it goes over time, the cost goes up. Variable costs need the most monitoring.

## Slide 25: II- Project Budget
II-3- What is the purpose of a project budget?
The Project Budget is designed to:
Aid in the decision-making process. This could be deciding whether the project goes ahead or choosing how much to invest in different activities within the project.
Communicate to stakeholders how much money is needed and when it’s needed.
Give the project manager a baseline to help them work out if the project is spending along its desired path.

## Slide 26: II- Project Budget
II-4- The benefits of effective project budgeting
We can all agree a budget is essential for any project, but the benefits extend far beyond just knowing what the project is going to cost. Effective project budgeting has the following benefits:
By knowing how much money is available for each project activity, you can easily pinpoint areas that need attention.
One of the trickiest parts of project management is having the right human resources available. The project budget helps determine exactly what skills you need for what length of time, which is especially useful when people are working across multiple projects.
The budget is an effective management tool to see if you’re on track to meet goals.

## Slide 27: II- Project Budget
It helps prioritize activities that can be completed within the resources available.
Sometimes this means reining in your ambitions but at least you’ll be delivering to expectations.
Helps promote future thinking and planning.
Project Managers who can deliver great outcomes while effectively controlling budgets have great career prospects!

## Slide 28: II- Project Budget

## Slide 29: II- Project Budget
II-5-How to estimate budget for a Project
Budgeting is a critical skill for a project manager and one that takes time to master. To help you build your budgeting competency, we’ve created a step-by-step guide for you to use as a checklist to ensure you cover all bases.
Refer to your Project Scope : the Project Scope contains the goals, deliverables, tasks, and deadlines for the project.
Define the Resources you need: list all the people and items that you need to complete the project within deadlines.
Understand the Resource Rate: people who will be working on the project will work at a specific rate, with more experienced people costing more, but often able to complete tasks faster and to a higher standard. Materials for the project get charged at a rate too.

## Slide 30: II- Project Budget
4- Assign Budget estimates: now that you have a list of resources, begin assigning a number to each. Each project will be different, but here are some Estimating Techniques to get you started:
  ​Use historical data
  Use maths
  Consult Subject Matter Experts (SMEs)
  Consult suppliers
5- Establish a contingency fund: Having an emergency fund means there’s a reserve for when costs increase.
6- Build the Budget: compile the estimates into your project management software or budget template.
7- Obtain approval: When you’re presenting your budget to management or stakeholders, you want it to be right. You’ll also need to be able to confidently justify the thinking behind the numbers.

## Slide 31: II- Project Budget
II-6- 9 expert tips for better project budgeting
Watch Project Scope like a hawk: there’s no surer way to blow budget than the dreaded Scope Creep.
Divide your Budget into useful timeframes: For example, you might want to analyze weekly staff costs so that you can quickly address overruns rather than leaving it until the end of the month (or the end of the project) when any issues have compounded.
Try not to let your contractors know what your contingency is: Set the expectation that they can’t exceed the budget unless you know about it well in advance and can manage it accordingly.
Involve others: Consult experts inside and outside of your organization to learn from them. So, communicate widely, and often.

## Slide 32: II- Project Budget
5.Understand your budget: whether you are using spreadsheets, budget templates, or more sophisticated software, keep track of your assumptions and calculations so that you remember how you arrived at your budget estimate.
6. Don’t fall for the Generation-Skipping Transfer (GST) trap:
make sure you treat GST consistently throughout. Many a budget derails because of GST confusion.
7. Consider lag: With a schedule, you know immediately if you’ve missed a date. But in most companies, financial information is delayed because of reporting practices. Understand your finance systems and account for them during your Project.
8.Update the Budget in real-time: if there are changes, you need to update your Budget regularly so you and your Team are tracking against the right numbers.
9.Record the lessons you learn along the way: this will help you and others in future projects.

## Slide 33: III- Project Risks
III-1- Project Risk Planning
Risk Planning is one of the most important components of the Project Implementation Guide as it helps you to understand how to plan for potential risks affecting the implementation of your endeavour and minimize the likelihood or consequence of unpleasant and negative results that may jeopardize the achievement of project goals and objectives.
When you start implementing your Project endeavour you need to plan and manage for potential risks; otherwise, you’re likely to fail with achieving the objectives and goals of the project. Designing and implementing a Risk Management Plan Template will help you handle the challenge.

## Slide 34: III- Project Risks
II-2- What are risk categories?
Categories of Risk are specific elements within a Project or its operational environment that could go wrong during the planning, implementation, or follow-up phases of an activity.
These Risk Categories consider things such as costs, timeline, available staff, public reception, and available inventory.
They look at the details that go into making a successful Project and consider what would happen if one or more of those details veered off course.

## Slide 35: III- Project Risks
Risk Categories can be defined as:
the classification of Risks as per the Business Activities of the organization and provides a structured overview of the underlying and potential risks faced by them.
Most commonly used Risk classifications include Strategic, financial, operational, people, regulatory and finance.

## Slide 36: III- Project Risks
III-3- Why do you use Risk Categories?
Risk Categories help identify risks.
It ensures that the users can track the origin of the underlying and potential risks faced by a Project.
These categories help determine the efficiency of the control systems implemented in all the departments of a Project.
It ensures that risk identification is made comprehensively, covering all the probable aspects of the underlying and upcoming risk conditions.
With these categories, users can determine the areas that are highly prone to risks, and it even allows in the identification of standard and probable causes.
With Risk Categories, users can even develop appropriate risk dealing mechanisms.

## Slide 37: III- Project Risks
III-4-Top 4 types of Project Risks
A Risk Breakdown Structure outlines the various potential risks within a Project. There are four main types of Project Risks: Technical, External, Organizational, and Project Management

## Slide 38: III- Project Risks

## Slide 39: III- Project Risks
III-5- How to Identify Categories of Risk?
An organization must scrutinize its process assets to find out if the same has a defined set of Risk Categories or not.
The users can make use of techniques like the SWOT Analysis, documentation reviews, information gathering techniques, Brainstorming, interviewing, Checklist Analysis, risk register, outputs of risk identification, impact matrix, Risk data quality assessment, simulation technique, etc.

## Slide 40: III- Project Risks

## Slide 41: III- Project Risks
III-5-2- The Checklist Analysis (CLA)
Checklist analysis (CLA) is a technique that can be used to identify and manage risk.
The checklist is developed by listing items, steps, or tasks and is then analyzed against criteria to determine if the procedure is completed correctly.
The checklists should be developed using historical information or knowledge gained from similar Projects in the past.

## Slide 42: IV- Project Communication
IV-1- Project Communication
Effective Communication is often the foundation of successful Projects.
Good Communication can unite team members and Stakeholders to a Project’s Strategy, Objectives and Budget.
It can also enable everyone involved in the Project to understand his or her roles, which may make them more likely to support the Project.

## Slide 43
IV-2- Why is a Project Communication Plan Important?
Without a Project Communication Plan, Projects can incur more risk and fail to meet desired outcomes.
Research by the Project Management Institute (PMI) supports this assertion.
IV- Project Communication

## Slide 44
IV-3- Tips for More Effective Project Communication
Project managers and C-Suite executives often agree that effective Communication to Stakeholders throughout the Project Lifecycle is an essential core competency.
Here are some tips to communicate more effectively:
* Make communication a priority
* Don’t assume you know everything
* Keep things positive
* Switch up the communication channels
* Keep updates timely and concise
IV- Project Communication

## Slide 45
V-4- How to Develop a
Project Communication Plan
When developing a Communication Strategy, here are a few questions to ask:
IV- Project Communication

## Slide 46
IV-5- The Project Kickoff Meeting
The Project Kickoff is part of the Project Initiation Phase of the Project Life Cycle. It’s a critical Project Management activity that involves preparing the team members and the client team on expectations, communication and collaboration for the Project.
It informs the Project Planning Phase of the Project, and also allows your team and the client to iron out and finalize details such as Project Timeline, Project Management methodology , success measurement, and more.
IV- Project Communication

## Slide 47
IV-5-1- Internal Project Kickoffs
The purpose of an internal Project Kickoff is to bring the Project Team up to speed and properly prepare them for the official kickoff meeting with the client.
As the Project Manager, your job is to educate them, bring the team together, set expectations for the project, and ensure a clear understanding of the project among all team members (and yourself!).
Once you’ve got the internal kickoff out of the way, the Client Project Kickoff meeting is next.
IV- Project Communication

## Slide 48: IV- Project Communication
IV-5-2- The Project Kickoff Meeting
We can think of the Project Kickoff Meeting as having two parts — a pre-client kickoff meeting, and a client kickoff meeting.
Here’s a little secret: we don’t want your first meeting with the client or key stakeholder to be the official kickoff meeting with the full client team and full project team.
Instead, hold a pre-client kickoff meeting first — this is worthwhile for a few reasons:

## Slide 49: IV- Project Communication
You’ll be able to nail down the Project Approval Process without other attendees chiming in and claiming they need to be involved.
You’ll be able to confirm the Statement of Work and Scope of the Project .
You’ll be able to establish a positive relationship with the client right off the bat, setting the tone for a good rapport and working relationship as the Project Progresses.
You’ll be able to iron out a few other important details in advance, such as collaboration tools , what assets will be needed, and the kickoff meeting agenda.

## Slide 50: V- Project Plan
V-1- What is Project Plan
A good Project Plan is one of the most essential elements of success in Project Management .
From preventing Scope Creep , overblown budgets, and missed deadlines to minimizing stress and frustration.
So, how do you create a good Project Plan and what are the essential elements of a Project Plan?

## Slide 51: V- Project Plan
V-2- Who creates Project Plans?
The obvious answer to this is Project Managers. But everyone who has to manage Projects in their roles can benefit from creating Project Plans before starting a new project, especially in cases of similar or recurring projects.
A Project Plan saves you the time it takes to recreate the same project over again.
Team Members and Stakeholders involved in the Project and its results may provide input, expertise, costs, and other relevant information to be added in and approved before the Project Manager puts finishing touches on the Project Plan.

## Slide 52: V- Project Plan
V-3- Why are Project Plans important?
Project Plans are important because they provide a shared vision for what the project aims to accomplish.
Project Plans give clarity on the responsibilities of each Team Member and Stakeholder in the Project. They also organize the Project's work from start to finish and prevent extraneous work from crowding out critical tasks.
Project Plans can become a powerful communication tool within the team throughout the Project. They serve as an important written reference for the Project Manager, Team Members, and External Stakeholders. These plans also help to mitigate Risk and maintain Quality at all stages of the project — from planning to completion.

## Slide 53: V- Project Plan
V-4- Elements of a Project Plan you shouldn't overlook
There are essential elements you must include to create a good Project Plan.
Keep in mind that creating and working with a flawed project plan is just as bad as working without one.
Timeline, costs, and deliverables should be detailed clearly to show the Scope of your project.
In the ten sections below, you’ll find ten essential elements of a Project Plan you shouldn't overlook.