## ورقة1
student name |  | Marwan Marwi | student Id | 2021206089
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
1 | THREATS | Miscommunication and misunderstanding | high | high | Issues, delay | Using standard official channels, Acquiring translators ,Hold awareness sessions. | Project Manager | مشروع مترو الرياض
2 | THREATS | Increase costs, as consequence of Economic inflation | high | moderate | Global oil price | Long term contracting,diversification of supply sources. | Procurements Manager | مشروع مترو الرياض
3 | OPPORTUNITIES | Exemption from government fees | high | high | help private sector | Benefiting from government support for the private sector. Opening channels of communication with the government | Government relations manager | مشروع مترو الرياض
4 | OPPORTUNITIES | Tax Exemption | high | high | High Society Cooperation | Adopting social community initiatives,Cooperation with humanitarian sector organizations | Public relations manager | مشروع مترو الرياض
5
6
7
8
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## ورقة2
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low