## Slide 1
Prepared by Dr. Tarek Mohamed
Project Procurement and
Supply Chain
Lecture 5
PMG 433

## Slide 2
Foundational knowledge of Project Procurement
Lecture 5
PMG 433
Dr. Tarek Mohamed
Prepared by

## Slide 3
Course Agenda
Define project procurement.
Explain the procurement management process.
Understand procurement planning.
Identify procurement documents.
Differentiate contract types.
Explain procurement risks.
Understand AI applications in project procurement.
Chapter

## Slide 4
Definition
Project procurement is the process of acquiring products, services, or resources from external suppliers to complete a project successfully.
Project procurement ensures that the right goods and services are acquired at the right quality, cost, and time to achieve the project's objectives.
Purpose
Obtain the required goods and services for the project.
Achieve the best value for money.
Ensure quality standards are met.
Minimize procurement risks.
Deliver resources on time.
Comply with legal, ethical, and contractual requirements.
What is Project Procurement?

## Slide 5
Why importance of Project Procurement matters:
Reduces project cost
Improves quality
Ensures timely delivery
Provides access to expertise
Manages supplier relationships
Supports project success
Importance of Project Procurement

## Slide 7
Plan Procurement –
Identify what needs to be purchased and prepare the procurement strategy.
Solicit Suppliers –
Request bids, quotations, or proposals from potential vendors.
Evaluate and Select Suppliers –
Compare offers based on cost, quality, experience, and capability.
Award and Manage Contracts –
Negotiate, sign, and administer contracts while monitoring supplier
performance.
Close Procurement –
Verify that all contractual obligations have been fulfilled and formally
the contract.
Key Activities in Project Procurement

## Slide 9
According to project management standards, procurement includes:
Plan Procurement Management
Conduct Procurements
Control Procurements
Project Procurement Management Processes

## Slide 10
Project Need ↓ Plan Procurement ↓ Prepare Procurement Documents ↓ Request Bids/Proposals ↓ Evaluate Suppliers ↓ Award Contract ↓ Manage Contract ↓ Close Procurement
Procurement Life Cycle Flow

## Slide 11
Procurement Life Cycle Flow Project: Purchase an MRI Machine for a hospital
Stage | Example
Identify the Need | The hospital requires a new MRI machine to improve diagnostic services.
Plan Procurement | Define technical specifications, budget, maintenance requirements, and delivery schedule.
Prepare Documents | Develop the SOW and issue an RFQ or RFP.
Solicit Quotations | Request quotations from approved medical equipment suppliers.
Evaluate Offers | Compare image quality, warranty, maintenance support, training, price, and delivery time.
Award Contract | Select the supplier offering the best value.
Manage Contract | Monitor manufacturing, shipping, installation, staff training, and acceptance testing.
Close Procurement | Confirm successful installation, complete payment, and close the contract.

## Slide 12
Make-or-buy analysis
Budget estimation
Risk assessment
Procurement schedule
Supplier strategy
Output:
Procurement Management Plan
Procurement Planning

## Slide 13
Statement of Work (SOW)
Describes the products, services, or work to performed, including
requirements and deliverables.
Request for Proposal (RFP)
Invites suppliers to submit detailed technical and commercial proposals for
complex procurements.
Request for Quotation (RFQ)
Requests suppliers to provide price quotations for well-defined goods or services.
Invitation to Bid (ITB)
Invites qualified suppliers to submit competitive bids, usually when
requirements are clearly specified.
Procurement Documents

## Slide 14
Bid/Proposal Evaluation Report
Documents the evaluation process and compares supplier proposals based on predefined criteria.
Purchase Order (PO)
A formal document authorizing the purchase of goods or services from a supplier.
Contract Agreement
A legally binding document that defines the rights, responsibilities, terms, conditions, and obligations of both buyer and seller.
Contract Change Order
Authorizes approved changes to the scope, cost, schedule, or other contract terms.
Procurement Documents

## Slide 15
Procurement Performance Report
Tracks supplier performance, delivery status, quality, costs, and compliance with the contract.
Procurement Closure Report Confirms that all contractual obligations have been completed and documents lessons learned before formally closing the procurement.
Procurement Documents

## Slide 16
Project procurement varies by industry, but in every case the company purchases goods, services, or expertise from external suppliers to support a project.
Example 1: Construction Project
Project: Build a 20-story office building
Procurement Items
Cement
Steel reinforcement
Glass façade
Elevators
Air conditioning systems
Electrical wiring
Fire protection systems
Construction equipment rental
Architectural consulting services
Examples of Project Procurements in Companies

## Slide 17
Example 2: IT Project
Project: Implement an Enterprise Resource Planning (ERP) system
Procurement Items
ERP software licenses
Cloud hosting services
Servers
Database software
Cybersecurity solutions
IT consulting services
User training services
Examples of Project Procurements in Companies

## Slide 18
Example 3: Hospital Project
Project: Build a new hospital wing
Procurement Items
CT and MRI scanners
Hospital beds
Ventilators
Laboratory equipment
Medical gases system
Nurse call system
Building construction services
Examples of Project Procurements in Companies

## Slide 19
Example 4: Manufacturing Project
Project: Expand a factory
Procurement Items
CNC machines
Industrial robots
Conveyors
Forklifts
Packaging machines
Quality inspection equipment
Examples of Project Procurements in Companies

## Slide 20
Example 5: Renewable Energy Project
Project: Construct a solar power plant
Procurement Items
Solar panels
Inverters
Batteries
Transformers
Monitoring systems
Civil construction services
Electrical installation services
Examples of Project Procurements in Companies

## Slide 21
Steps:
Issue solicitation
Receive proposals
Technical evaluation
Financial evaluation
5. Negotiation
6. Contract award
Supplier Selection Process

## Slide 26
A contract is a mutually binding agreement that obligates the seller to provide the specified products or services and obligates the buyer to pay for them
Contracts can clarify responsibilities and sharpen focus on key deliverables of a project
Because contracts are legally binding, there is more accountability for delivering the work as stated in the contract
A recent trend in outsourcing is the increasing size of contracts
Contracts

## Slide 27: Types of Contracts
Different types of contracts can be used in different situations
Fixed price or lump sum contracts: involve a fixed total price for a well-defined product or service
Cost reimbursable contracts: involve payment to the seller for direct and indirect costs
Time and material contracts: hybrid of both fixed price and cost reimbursable contracts, often used by consultants
Unit price contracts: require the buyer to pay the seller a predetermined amount per unit of service
A single contract can actually include all four of these categories, if it makes sense for that particular procurement

## Slide 28: Cost Reimbursable Contracts
Cost plus incentive fee (CPIF): the buyer pays the supplier for allowable performance costs plus a predetermined fee and an incentive bonus
Cost plus fixed fee (CPFF): the buyer pays the supplier for allowable performance costs plus a fixed fee payment usually based on a percentage of estimated costs
Cost plus percentage of costs (CPPC): the buyer pays the supplier for allowable performance costs plus a predetermined percentage based on total costs

## Slide 30
A statement of work is a description of the work required for the procurement
If a SOW is used as part of a contract to describe only the work required for that particular contract, it is called a contract statement of work
A SOW is a type of scope statement
A good SOW gives bidders a better understanding of the buyer’s expectations
Contract Statement of Work (SOW)

## Slide 32
A well-written Statement of Work should answer the following questions:
What work will be done? (Scope)
Why is the project being undertaken? (Purpose and objectives)
Who is responsible? (Roles and responsibilities)
When will the work be completed? (Schedule)
How will success be measured? (Acceptance criteria and success metrics)
How much will it cost? (Budget and payment milestones)
Statement of Work (SOW)

## Slide 33
Supplier delays
Poor quality
Cost overruns
Contract disputes
Supply shortages
Currency fluctuations
Procurement Risks

## Slide 35
Artificial Intelligence (AI) is transforming project procurement by automating routine tasks, analyzing large volumes of data, predicting risks, and supporting better decision-making. Below are practical examples that can be used in a Project Management course.
AI can help with:
Supplier evaluation
Demand forecasting
Contract analysis
Risk prediction
Fraud detection
Invoice automation
Spend analysis
Supplier performance monitoring
AI in Project Procurement

## Slide 37
Procurement supports project success.
Planning is essential.
Contract selection affects project risk.
Supplier evaluation is critical.
Procurement requires continuous monitoring.
AI is transforming procurement through automation and analytics.
Summary

## Slide 38
Summary of Learning Objectives
Define project procurement.
Explain the procurement management process.
Understand procurement planning.
Identify procurement documents.
Differentiate contract types.
Explain procurement risks.
Understand AI applications in project procurement.
Chapter

## Slide 39
Morris, P. W., & Pinto, J. K. (Eds.). (2007). The Wiley guide to project technology, supply chain, and procurement management (Vol. 4). John Wiley & Sons.
Schwalbe, K. (2015). Information technology project management. Cengage Learning.
Baily, P., Farmer, D., Crocker, B., Jessop, D., & Jones, D. (2008). Procurement principles and management. Pearson Education.
Supply Chain Council
Essential Reference

## Slide 40
Thank You