## Slide 1
Project Business Analysis
Lecture 6
PMG 461 – MGM 461
Eng. Ahmed Hussein, MBA, PfMP©, PMP©, CMP APMG
Prepared by
Planning for Business Analysis

## Slide 2
What we will cover
Lecture
06
Planning for Business Analysis
Developing the business analysis Work Plan
6 – 2

## Slide 3
In Previous Lectures
Lecture
06
6 – 3
Business Analysts elicit requirements from stakeholders using various qualitative and quantitative techniques. Selection based on project considerations and complexity, number of stakeholders and their location , available time and budget.
Business analysts contribute to identifying and engaging stakeholders as they serve as the bridge between the project technical team and business users. They engage stakeholders through applying various engagement strategies.
Business Activity Models captures Different stakeholders views of the problem, requirements, solution, and works to eliminate redundancies and conflicts creating a consensus model that includes all views.
Requirements are engineered through Elicitation, Analysis, Documentation, and Validation.

## Slide 4
Planning for Business Analysis
Lecture
06
6 – 4

## Slide 5
Planning for Business Analysis:
Lecture
06
6 – 5
Begins at the project start where the Business Analyst should understand project context and characteristics.
Business analysis planning consists of the activities performed to ensure that the optimal business approach is selected for the project.

## Slide 6
Planning for Business Analysis:
Lecture
06
6 – 6
Business analysis planning depends on project Lifecycle:
  Traditional  upfront planning
  Agile  some planning upfront and continued over the course of the project
There is no one approach that will work for all projects, methods, tools, and techniques are tailored to the needs of the project.

## Slide 7
Planning for Business Analysis:
Lecture
06
6 – 7
Project Manager and Business Analyst work closely together to develop business analysis plan.
Planning is integrated into the overall project plan ( as part of Planning specifically Scope Management)
10 Knowledge Areas
Integration
Scope
Schedule
Cost
Quality
Risk
Resources
Procurement
Stakeholder
Communication
Monitoring and Controlling
Initiating
Planning
Executing
Closing

## Slide 8
What happens if we bypass Planning?
Lecture
06
6 – 8
Lack of Scope of work understanding and stakeholder’s expectations
Inaccurate estimates due to lack of understanding of time and effort needed.
Pressure on time and rushing activities resulting in inaccurate requirements and increased risks of changes or problems in delivered solution.

## Slide 9
Benefits of a Business Analysis Plan
Lecture
06
6 – 9
Sets expectation with all stakeholders (sponsor, stakeholders, and project team).
Clear definition of roles and accountabilities for business analysis activities.
Buy-in and support for business analysis.
Provides context to supports estimation of activities.
Efficient execution of business analysis activities.

## Slide 10
How to Perform Business Analysis Planning?
Lecture
06
6 – 10
Review Charter (for size, complexity, type, risk, lifecycle, technology, constraints, …)
Review any planning documents
Review records of similar projects done in the past

## Slide 11
How to Perform Business Analysis Planning?
Lecture
06
6 – 11
Meet with project manager and may be sponsor to understand the context of the project
Review (or sometimes perform or participate in) Stakeholders identified and stakeholder analysis, looking for:
Culture and Attitude, # of stakeholders, conflicting needs, ..)
Location, Impact, and Influence

## Slide 12
What is included in a Business Analysis Plan?
Lecture
06
6 – 12
Types of elicitation techniques to be used.
Analysis and Modeling Techniques to be used.
How requirements will be documented.
Business Analysis deliverables.
Roles and Responsibilities.

## Slide 13
What is included in a Business Analysis Plan?
Lecture
06
6 – 13
How Requirements will be Prioritized.
How requirements will be tracked.
How requirements will be validated and verified
Acceptance criteria for requirements.
Communication Approach

## Slide 14
Planning for Elicitation
Lecture
06
6 – 14
Includes:
Which techniques to use
Sequence of activities
Factors to consider:
Project Lifecycle
# of stakeholders and location
Time and Budget Constraints
Type of deliverables required
Level of details needed

## Slide 15
Elicitation Plan will impact Project:
Lecture
06
6 – 15
Resources
Time
Cost
Quality
Risks
Communication
Stakeholders

## Slide 16
Strategies for Sequencing Elicitation Activities
Lecture
06
6 – 16
Highest Business Value
Higher Risks
Technical Challenges
Dependencies
Organizational Hierarchy
Business Analyst should consider which areas to address first based on several factors as:

## Slide 17
Requirements Prioritization
Lecture
06
6 – 17
Defines how requirements will be prioritized prior to elicitation.
Sets expectation with stakeholders
Minimizes conflict
Factors to consider:
When to do prioritization?
Who will be involved?
Techniques to be used
Criteria
Who will approve?
Must Have (HIGH)
Should HAVE (MEDIUM)
Nice to Have (LOW)

## Slide 18
Requirements Prioritization Criteria
Lecture
06
6 – 18
Value
Addressing high-value or important requirements first to realize benefits early.
Cost
Evaluate criteria based on their costs
Difficulty
How difficult to fulfill the requirement

## Slide 19
Requirements Prioritization Criteria
Lecture
06
6 – 19
Regulatory
Mandated requirements for compliance with regulations and legislations
Risk
Implementing high-risk requirements first

## Slide 20
Requirements Traceability
Lecture
06
6 – 20
A Traceability Matrix is a grid that allows linking requirement to deliverables.
Use to track realization of requirements throughout the project.
Ensures each requirement has value.
Provides a structure for managing changes.
Includes Requirement attributes.

## Slide 21
Traceability Decisions
Lecture
06
6 – 21
Types of requirements to be traced
Level of detail (each deliverable or WBS level)
Attributes to be traced
Different requirement status (approve, reject, cancel)
How will traceability be performed and tools used?
Timing
Who will trace?

## Slide 22
What do we Track and Monitor?
Lecture
06
6 – 22
Business needs
Objectives
Detailed Requirements
Design Components
Development Components
Test Scenarios and use cases

## Slide 23
Benefits of Tracing Requirements
Lecture
06
6 – 23
Ensure each requirement adds business value
Meet customer expectations
Manage scope

## Slide 24
Sample Requirements Traceability Matrix
Lecture
06
6 – 24
Requirement Information |  |  | Relationship Traceability |  |  | 
ID | Requirement | Source | Business Objective | Deliverable | Verification | Validation
Unique ID for requirement | Description of the requirement | Name Of person who identified the requirements | List the business objective that is met by fulfilling the requirement. | Identify the deliverable that is associated with the requirement. | Describe the metric that is used to measure the satisfaction of the requirement. | Describe the technique that will be used to validate that the requirement meets the stakeholder needs.

## Slide 25
Validation vs. Verification
Lecture
06
6 – 25
Validation
Assurance that requirements for a system or product or deliverable meets the needs of the stakeholder.
Done as part of Elicitation.
BEFORE working on delivering the requirement,
Verification
Evaluation if a system or product or deliverable complies with set requirements or specifications.
Done as part of execution, monitoring and controlling
AFTER delivering the requirement.

## Slide 26
Communication Approach
Lecture
06
6 – 26
Describes how and when business analysis information will be structured and communicated to stakeholders.
Forms part of the overall project communication plan.
Considerations:
  Which information
  To Who
  Stakeholder preferences
  How (method)
  Tools
  Who will prepare and send the information

## Slide 27
Sample Requirements Documentation Template
Lecture
06
6 – 27
ID | Requirement | Source | Category | Priority | Acceptance Criteria | Test
A unique ID for the requirement. | Description of the requirement | Name of person who identified the requirement). | Functional Non Functional Business … | Must have, Should have, or Nice to have. | The criteria that must be met for the stakeholder to approve that the requirement has been fulfilled. | The method that will be used to verify that the requirement has been met.

## Slide 28
Requirements Change Process
Lecture
06
6 – 28
Describes how we will manage changes to requirements throughout the project.
Part of the overall project change management.
Considerations:
  How requirement changes will be proposed?
  How changes will be reviewed?
  How decisions for changes will be made?
  How changes will be communicated?

## Slide 29
Sample Business Analysis Plan (1/4)
Lecture
06
6 – 29
Business Analysis Plan |  |  |  |  |  |  | 
Project ID: |  |  | Project Title: |  |  |  | 
Project Sponsor: |  |  | Project Manager: |  |  | Date Prepared: | 
Requirements Collection: Describe how requirements will be collected or elicited. Consider techniques such as brainstorming, interviewing, observation, etc |  |  |  |  |  |  | 
Requirements Analysis: Describe how requirements will be analyzed for prioritization, categorization, and impact to the product or project approach. |  |  |  |  |  |  | 

## Slide 30
Sample Business Analysis Plan (2/4)
Lecture
06
6 – 30
Business Analysis Plan |  |  |  |  |  |  | 
Project ID: |  |  | Project Title: |  |  |  | 
Project Sponsor: |  |  | Project Manager: |  |  | Date Prepared: | 
Requirements Categories: Identify categories for requirements such as business, stakeholder, quality, etc |  |  |  |  |  |  | 
Requirements Documentation: Define how requirements will be documented |  |  |  |  |  |  | 
Requirements Prioritization: Identify the prioritization approach for requirements. |  |  |  |  |  |  | 

## Slide 31
Sample Business Analysis Plan (3/4)
Lecture
06
6 – 31
Business Analysis Plan |  |  |  |  |  |  | 
Project ID: |  |  | Project Title: |  |  |  | 
Project Sponsor: |  |  | Project Manager: |  |  | Date Prepared: | 
Requirements Metrics: Document the metrics that requirements will be measured against. |  |  |  |  |  |  | 
Requirements Traceability Structure: Identify the information that will be used to link requirements from their origin to the deliverables that satisfy them. |  |  |  |  |  |  | 

## Slide 32
Sample Business Analysis Plan (4/4)
Lecture
06
6 – 32
Business Analysis Plan |  |  |  |  |  |  | 
Project ID: |  |  | Project Title: |  |  |  | 
Project Sponsor: |  |  | Project Manager: |  |  | Date Prepared: | 
Requirements Tracking: Describe how often and what techniques will be used to track progress on requirements. |  |  |  |  |  |  | 
Requirements Reporting: Describe how reporting on requirements will be conducted and the frequency of such reporting. |  |  |  |  |  |  | 
Requirements Validation: Identify the various methods that will be used to validate requirements such as inspection, audits, demonstration, testing, etc. |  |  |  |  |  |  | 

## Slide 33
Approving Business Analysis Plan
Lecture
06
6 – 33
Business Analysis Plan should be Reviewed and Formally Approved.
Reviewers and Approvers may be Project Manager, Project Sponsor, or key stakeholders.

## Slide 34
Developing the Work Plan
Lecture
06
6 – 34

## Slide 35
Business Analysis Workplan
Lecture
06
6 – 35
Covers the tasks and activities to be performed.
Includes sequence, dependencies, durations, start and finish dates, and responsibilities.
Similar to and usually integrated with the Project Schedule

## Slide 36
Business Analysis Workplan
Lecture
06
6 – 36
Identify Deliverables
Determine Tasks and Activities for each Deliverable
Determine sequence and dependencies of tasks
Determine Roles and Responsibilities
Identify Resources
Estimate Durations
Consolidate into an integrated work plan

## Slide 37
Sample Business Analysis Workplan Template
Lecture
06
6 – 37
ID | Deliverable | Task | Dependency | Resources | Duration | Start Date | Finish Date | Responsible

## Slide 38
Key Points
Lecture
06
6 – 38
Business Analysis Planning is crucial for effectiveness of business analysis efforts.
Business Analysis planning is done in coordination with overall project planning.
Business Analysis plan is concerned with key considerations and decisions for business analysis.
Business Analysis Workplan is concerned with activities, dependencies, estimates and is part of project schedule.
Business Analysis plans should be reviewed and formally approved.

## Slide 39
6 – 39
For Discussion Panel and Next Lecture:
Watch the video: “Business Analyst Full Course In 2 Hours | Business Analyst Training For Beginners | Simplilearn”
Watch the video: “Business Analyst Training for Beginners | Business Analysis Tutorial | Invensis Learning”
For Discussion Panel and Next Lecture
06
Lecture

## Slide 40
Thank You