## ورقة1
student name |  | Mohamed mahmoud sadek | student Id | 2021206086
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
1 | THREATS | technical challenges | high | moderate | Issues, delay, | Equipment has to be brought in and the tunnel has to be dug with high and quick efinacy | Project Manger | مشروع مترو الرياض
2 | THREATS | Safety issues | high | moderate | workers could be exposed to risk | Extra safety precautions should be put in place | Risk Owner | مشروع مترو الرياض
3 | OPPORTUNITIES | Solve the problem of overcrowding and increase the population | high | high | Traffic optimization | Urging the community to use it by raising awareness of what is beneficial to the community | Project Manger | مشروع مترو الرياض
4 | OPPORTUNITIES | Increase job opportunities | high | high | Improving the unemployment rate | Adobiting Hr consultant to hire the best employees with high education and skills | HR manager | مشروع مترو الرياض
5
6
7
8
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## Sheet1
Activity | Optimistic Time | Most Likely Time | Pessimistic Time | Immediate Predecessor Activities | ET | Q2 | Q
a | 10 | 22 | 28 |  | 21 | 9 | 3
b | 12 | 24 | 30 |  | 23 | 9 | 3
c | 6 | 12 | 18 |  | 12 | 4 | 2
d | 4 | 16 | 34 | a | 17 | 25 | 5
e | 8 | 8 | 20 | a,b,c | 10 | 4 | 2
f | 8 | 14 | 20 | a,b,c | 14 | 4 | 2
g | 4 | 4 | 4 | a,b,c | 4 | 0 | 0
h | 4 | 14 | 18 | c | 13 | 5.4444 | 2.3333
i | 6 | 16 | 38 | g,h | 18 | 28.4444 | 5.3333
j | 4 | 10 | 16 | d,e | 10 | 4 | 2
Activity | Predecessor Activities | Duration, Days (normal, crash) |  | Cost, $ (normal, crash)
a |  | 5,4 |  | 50, 100 | -50 | 100 | 50 | 50 | 5 | 5
b | a | 3,2 |  | 30, 90 | -60 | 90 | 30 | 30 | 3
c | a | 3,3 |  | 40, 40 | 0 | 40 | 40 | 40 |  | 3
d* | a | 5,2 |  | 50, 140 | -30 | 50 | 50 | 50
e** | b | 4,2 |  | 20, 100 | -80 | 20 | 100 | 20 | 4
f* | c | 3,1 |  | 30, 110 | -40 | 30 | 30 | 30 |  | 3
[6 empty] | 330 | 300 | 220 | 12 | 11

## ورقة2 (hidden)
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low