## ورقة1
student name |  |  | student Id
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
1 | THREATS | covid 19 | high | high | project delay | extend the project deadline | operation | مشروع الهايبر لوب
2 | THREATS | GCC countries credence | high | moderate | reduse the spread | use it localy through multiple cities | project management | مشروع الهايبر لوب
3 | OPPORTUNITIES | Low demand due covid19 | high | high | cheaper material | forcast and demand | planning department | مشروع الهايبر لوب
4 | OPPORTUNITIES | working from home | moderate | moderate | Less need for employees in office | transportation allowance saving | management departments | مشروع الهايبر لوب
5
6
7
8
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## ورقة2 (hidden)
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low