## ورقة1
student name |  | Ahmed Qadiri | student Id | 2021206216
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
1 | OPPORTUNITIES | Covied epidemic will affect on hiring from outside the country | high | high | Saudization | rehabilitaion national competences | Hr Manger | مشروع مترو الرياض
2 | OPPORTUNITIES | Using new technology | high | high | Better performance | willHelp to get better performance and optimize project operation | IT and Project manger | مشروع مترو الرياض
5 | THREATS | Supplier commitment | high | high | Delay and project was not delivered on time | Set financial penalties to avoid any delay | Project manger | مشروع مترو الرياض
6 | THREATS | Using huge drilling machines with high electric current rates | high | moderate | delay , Issue,and cost | Regular maintenance and Giving employees courses on how machines work and how to avoid any risks | Project manger
7
8
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## ورقة2 (hidden)
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low