## Slide 1: Project Communications Lecture 9
PMG 201
EVALUATING AND TERMINATING THE PROJECT
Everyone’s Smart University

## Slide 2: Objective
1 . Evaluation
Evaluation Criteria
Measurement
2. Project Auditing
The Audit Process
The Audit Report
3. Project Termination
When to Terminate a Project
Types of Project Termination
The Termination Process
The Project Final Report

## Slide 3: 1 . Evaluation
1 . Evaluation
Evaluation Criteria
Measurement

## Slide 4: Evaluation
The term “ evaluate ” means to set the value of or appraise. A project evaluation appraises the progress and performance relative to the project ’ s initial or revised plan.

## Slide 5: Purpose of Evaluation
Assess performance
Reveal areas of deviation from original scope &/or goals
Snoop out potential problem areas
Keep stakeholders informed

## Slide 6: Two Types of Evaluation
Formative evaluation
  Throughout project lifecycle
  Provide information for corrective action
  “What’s happening?” & “How’s progress?”
Summary evaluation
  After project completed
  AKA “Lessons Learned”
  “What happened and what resulted?”

## Slide 7: Formative Evaluation
Complex relationships among cost, time, & scope
CT&S are always interrelated and draw from the same limited resource pool
Cannot just look at one criteria

## Slide 8: Goals of Evaluation
Reveals problem areas
Alerts personnel to potential problem areas
Identifies opportunities to increase customer satisfaction by reducing costs, accelerating work, or enhancing project outcomes

## Slide 9: Evaluation Criteria
There are many different measures that may be applied in a project evaluation. As indicated, senior management may have particular areas they want evaluated for future planning and decisions, and these should be indicated in the charge to the evaluation committee.
Certainly, one of the major evaluation criteria would be the project ’ s apparent “ success ” to date.
The criteria noted above are usually sufficient for purely routine projects,

## Slide 10: Items to Consider for Project Evaluation Report Recommendations
• Communication with the client and senior management.
• Locating opportunities for technological advances.
• Reduction of indirect costs and direct costs.
• Improving the project - management process.
• Identification of risks in the organization ’ s use of projects.
• Utilization of the skills resulting from project members ’ work on projects.
• Employment of general management experience gained by project managers.
• Improving the organization ’ s use of projects.
• Increasing the speed of obtaining results in projects.

## Slide 11: Measurement
Measuring the project ’ s performance against a planned budget and schedule is relatively straightforward, and it is not too difficult to determine if individual milestones have been reached. As we have noted several times, there are complications regarding measurement of actual expenditures and earned values, as well as with reporting on difficult technical issues that may have been deferred while progress was being made along other fronts.

## Slide 12: project evaluation
A project evaluation is an appraisal for use by top management. Its criteria should include the needs of management; the organization ’ s stated and unstated goals; the original selection basis for the project; and its success to date in terms of its efficiency, customer impact/satisfaction, business success, and future potential. Measuring the project ’ s success on budget, schedule, and performance is easier than measuring revenues or qualitative, subjective factors. Establishing the measures at project formation is helpful, as well as using carefully standardized measurement techniques for the subjective factors.

## Slide 13: 2. Project Auditing
2. Project Auditing
The Audit Process
The Audit Report

## Slide 14: Project Auditing
A very special type of evaluation is the formal audit. The project audit is a thorough examination of the management of a project, its methodology and procedures, its records, properties, inventories, budgets, expenditures, progress, and so on.
The project audit is not a fi nancialaudit , but is far broader in scope and may deal with the whole or any part of the project.
For a comparison of the two,. It can also be very flexible, and can focus on any issues of interest to senior management. The project audit is also broader than the traditional management audit that focuses its attention on the organization ’ s management systems and operation.

## Slide 15: The Audit Process
The timing of the audit depends on the purpose of the audit, Because early problem identification leads to easier solutions, it is often helpful to have an audit early in the project ’ s life.
Such audits are usually focused on technical issues. Later audits tend to focus more on budget and schedule because most of the technical issues are resolved by this time. Thus, these later audits are typically of less value to the project team and of more interest to general management.
An obvious case here is the post project audit , often contractually required by the customer as well as a common ingredient in the Final Project Report.

## Slide 16: Typical steps in a project audit are:
1. Familiarize the audit team with the requirements of the project, including its basis for selection and any special charges by upper management.
2. Audit the project on - site.
3. Write up the audit report in the required format (discussed in the next subsection).
4. Distribute the report.

## Slide 17: The Audit Report
If the audit is to be taken seriously, all the information must be credibly presented. The data should be carefully checked, and all calculations verified. Deciding what to include and what to exclude is also important. The audit report should be written with a “ constructive ” tone or project morale may suffer to the point of endangering the project. Bear in mind, however, that constructive criticism never feels that constructive to the criticizee.

## Slide 18: The Audit Report con. ….
At a minimum, the following information should be contained in the report:
1.Introduction : A brief description of the project that includes the project ’ s direct goals and objectives.
2. Current status : This compares the work actually completed to the project plan along several measures of performance.
3. Future project status : The auditor ’ s conclusions regarding project progress and recommendations for changes in technical approach, schedule, or budget should be made in this section.

## Slide 19: The Audit Report con. ….
4. Critical management issues : Any issues that the auditor feels senior management should monitor should be identified here. The relationship between these issues and the project objectives should be briefly described.
5. Risk analysis and risk management : This section addresses the potential for project failure or monetary loss.
6. Final comments : This section contains caveats, assumptions, limitations, and information applicable to other projects.

## Slide 20
The project audit is a thorough examination of the entire project at any level of depth. Early audits tend to focus on more technical aspects of the project while later audits focus on schedule and cost. The audit team must have full access to project data and staff familiar with the project, including the project team.
Working with the project team is a delicate behavioral process. The final audit report should be written with a professional and constructive tone and should include the following sections: introduction, current status, future status, critical management issues, risk analysis and risk management, plus final comments.

## Slide 21: 3. Project Termination
3. Project Termination
When to Terminate a Project
Types of Project Termination
The Termination Process
The Project Final Report

## Slide 22: Project Termination
Eventually the project is terminated, either quickly or slowly, but the manner in which it is closed out will have a major impact on the quality of life in the organization. Occasionally, the way project termination is managed can have an impact on the success of the project. Invariably, however, it has a major effect on the residual attitudes toward the project held by senior management, the client, the project team, and even others in the organization. It also has a major effect on the organization ’ s successful use of projects in the future.

## Slide 23: When to Terminate a Project
If one adopts the position that sunk costs are irrelevant to current investment decisions, a primary criterion for project continuance or termination should be whether or not the organization is willing to invest the time and cost required to complete the project, given its current status and expected outcome.

## Slide 24: When to Terminate?
Will Project Still Achieve Minimum Goals Set for It? If No, Terminate! If Yes, You Still Might Want to Combine Projects
Burton Dean Comments that Projects Should be Terminated When Probability of Commercial or Technical Failure is Sufficiently High
Problem: How Do You Measure Success/Failure?

## Slide 25: Types of Project Termination
Termination by Extinction
Termination by Addition
Termination by Integration
Termination by Starvation (Lack of Budget)

## Slide 26: Project Termination
Breaking Up is Hard to Do …
One Must Reassign
People – In the Case of Non-Recurring Projects, to Other Projects
Space – Often Difficult for People to Give Up
Equipment – Must Find New Uses or Sell (Can also Include Leftover Material)

## Slide 27: Success Factors (Pinto & Slevin)
Project Mission
Top-Management Support
Project Schedule/Plan
Client Consultation
Personnel
Technical Tasks
Client Acceptance
Monitoring and Feedback
Communication
Trouble-Shooting

## Slide 28: The Termination Decision
Does the Project Qualify Against Success Factors?
Various Models Have Been Proposed that Input Factors and Output Desirability or Net Present Value – In Practice Decision is Largely Subjective
Does Project Meet Goals/Objectives Originally Set for It at Present Time?
Problem is Time has Elapsed since Goals were Set – Is Current Expected Output/Outcome > Estimated Cost Required to Complete Project?

## Slide 29: Implementation of Termination
A Project in Itself
Need for Planning/Budgeting/Scheduling
Need to Resist “Stretch Out”
Termination Managers Can be Useful

## Slide 30: Main Duties of the Termination Manager
• Ensure completion of the work, including that of subcontractors.
• Notify the client of project completion and ensure that delivery and installation are accomplished. Acceptance of the project must be acknowledged by the client.
• Ensure that documentation is complete, including the project fi nal report.
• Clear all accounts and documentation for fi nal billings and client invoicing.
• Redistribute personnel, materials, equipment, and other project resources to appropriate places, including the return of client - provided resources.

## Slide 31: Main Duties of the Termination Manager cont. …
• Clear the project with legal counsel, including fi lings for patents and recording and archiving all nondisclosure documents.
• Determine what records to keep and deliver them to safe and responsible people, such as the organization ’ s archivist, or store them in the organization ’ s archives.
• Ascertain any product support requirements (e.g., spares, service manuals) and ensure that such support will be delivered.
• Oversee the closing of the project ’ s books.

## Slide 32: Final Reports
1. Project Performance
2. Administrative Performance
3. Organizational Structure
4. Project and Administrative Teams
5. Techniques of Project Management

## Slide 33: Final Reports
How the report is written, and in what style, is a matter of taste and preference. In any case, the following items should be addressed.
Project performance
Administrative performance
Organizational structure
Project teamwork
Project management techniques

## Slide 34: Monthly Progress Reports
Brief project status summary
“Red Flag” items & corrective action
Accomplishments, changes, & projections
Minor problem areas & corrective action
Cost & manpower situation

## Slide 35: Reports to Project Manager
Work completed to date
Forecasts:
  Costs at completion
  Schedule expectations
Financial status
  Incurred costs
  Planned vs. actual

## Slide 36: Reports to Customer
Work completion status & projections
Changes (by requests &/or events)
  Impacts on cost/time/scope
PM should bear responsibility
  Honest & frequent
  Avoid “Surprises”

## Slide 37
Projects are usually terminated either based on
(1) the degree to which they are meeting their goals or
(2) the degree to which they qualify on factors shown to be linked to success or failure in other projects.
The most common reason for early termination is the probability of a technical or commercial failure. The four types of project termination are extinction, addition, integration, and starvation. The termination decision should be decided by a management committee, run by a termination manager, and executed as a project in itself. Placing the project team members in new assignments is a particularly important aspect of termination.

## Slide 38
The PM should prepare a project final report that makes recommendations for improving the organization ’ s future project - management practices.