## Slide 1
Project Monitoring Course
Prepared & presented by:
Dr. Dhouha Melliti
2022-2023
Lecture 02: Part(2)
Norms, standards and management
for monitoring and evaluation

## Slide 2
General Introduction
Lecture 2
«My favorite project? It's the next one». Frank Lloyd Wright

## Slide 3
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
3. 2.The components of a project monitoring and evaluation system
A sound project M&E system requires six main components which together help to ensure that M&E is relevant to the project, within the capacity of the project management organisation, and is used to good effect. Each is considered briefly below.

## Slide 4
Session 1: General introducton
Lecture 2
(1) Clear statements of measurable objectives for the project and its components
- Projects are designed to contribute to long-term sectoral development goals, but at the level of project purpose their outcomes should be quite specific and complete.
- Objectives at the level of project purpose should be specific to the project interventions, realistic in the timeframe for their implementation and measurable for evaluation.

## Slide 5
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
(2) A structured set of indicators covering: inputs, process, outputs, outcomes, impact, and exogenous factors.
Indicators provide the qualitative and quantitative detail necessary to monitor and evaluate progress and achievements at all levels of the project hierarchy.
The ability to define an indicator, and agree with partners and stakeholders a target and the timing for its achievement, is a demonstration that project objectives are clearly stated, and are understood and supported.

## Slide 6
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
A logical structure for project monitoring and evaluation indicators
Logic | Indicators | Nature of the indicators | 
Goal | Impact | Long-term statistical evidence | Exogenous indicators
Purpose | Outcomes | Social and economic surveys of project effects and outcomes | 
Outputs | Output | Managementobservation, records,andi nternal reporting. | 
Activities | Process | Task managementofprocesses. | 
Inputs | Input | Financial accounts Management records of inventories and usage. | 

## Slide 7
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
2.1- Input indicators
are quantified and time-bound statements of the resources financed by the project, and are usually monitored by routine accounting and management records. They are mainly used by managers closest to implementation, and are consulted frequently (daily or weekly).
Lecture 2

## Slide 8
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
2.2- Process indicators
Monitor the activities completed during implementation, and are often specified as milestones or completion of sub-contracted tasks, as set out in time- scaled work schedules. One of the best process indicators is often to closely monitor the project's procurement processes.
Lecture 2

## Slide 9
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
2.3- Output indicators
Monitor the production of goods and delivery of services by the project. They are often evaluated and reported with the use of performance measures based on cost or operational ratios.
The indicators for inputs, activities and outputs, and the systems used for data collection, recording and reporting are sometimes collectively referred to as the project physical and financial monitoring system, or management information system (MIS).
Lecture 2

## Slide 10
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
2.4- Outcome indicators
Are specific to a project’s purpose and the logical chain of cause and effect that underlies its design. Often achievement of outcomes will depend at least in part on the actions of beneficiaries in responding to project outputs, and indicators will depend on data collected from beneficiaries, eg change in crop yields or cropping pattern, and investment by farmers in land management improvements.
Lecture 2

## Slide 11
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
2.5- Impact indicators
refer to medium or long-term developmental change to which the project is expected to contribute. Dealing with the effects of project outcomes on beneficiaries, measures of change often involve statistics concerning economic or social welfare, collected either from existing regional or sectoral statistics or through relatively demanding surveys of beneficiaries.
Lecture 2

## Slide 12
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
2.6- Exogenous indicators
Are those that cover factors outside the control of the project but which might affect its outcome, including risks (parameters identified during project design that might compromise project benefits) and the performance of the sector in which the project operates. Use of logical framework analysis for project design will guide the identification of exogenous indicators to match the key assumptions made about necessary external conditions at each level of the logical hierarchy
Lecture 2

## Slide 13
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
(3)Data collection mechanisms capable of recording progress over time, including baselines and a means to compare progress and achievements against targets.
Within project M&E systems there will be a need to collect information of the baseline situation and for measurement of change over time for the indicators selected. It is vital to think about the sources of data, the reliability of that information and the costs and responsibilities.

## Slide 14
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
Potential problems with secondary data can arise in a number of ways.
Incomplete coverage of the specific project area,
Inability to disaggregate the data to match the boundaries of the project area or sub-areas,
Inability to disaggregate the data to match the project affected population or sub- groups,
Inconsistencies in data collection in surveys implemented in different areas,
Inaccuracies arising from inappropriate choice of measurement and collection methods or inadequate training and supervision of data collection staff

## Slide 15
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
Data collection will incur costs of staff time and other resources, whilst excessive collection of unnecessary data will slow down processes of analysis and reporting, and may lead to a failure to communicate clear messages.
Thus it is important to collect only the data that will be used effectively to improve management and decision-making.

## Slide 16
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
It is important to think about the following aspects when planning data collection:
What – the data to be collected, in what form, with what degree of aggregation or consolidation, and for what purpose.
When – the frequency of data collection and reporting.
Who – the responsible persons, their responsibilities and capacities.
How - methods and procedures for data collection, checking, validation and storage, and for analysis and reporting.
Where – locations for data collection and processing, and the destinations for reported information.

## Slide 17
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
Bio-physical measurements
Measurements of physical change over time.
Selected methods need to be adapted to local conditions, skills and resources, and it may be necessary to seek a compromise between local capacities and technological appropriateness and the achievable level of scientific accuracy.

## Slide 18
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
Sampling methods
The following will be needed to achieve a representative sample and valid and reliable results for the project area, system or target population.
Clarification and accurate listing of the sampling frame: a listing of the sampling units that make up the population to be studied.

## Slide 19
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
Formal surveys
A typical formal survey involves taking a range of measurements or observations from a relatively large sample.
Surveys are commonly used at the start and end of a project, to gather baseline information and compare outcomes to targets. A survey can also be carried out as part of a mid-term review, to monitor progress and adapt project implementation as needed.

## Slide 20
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
Semi-structured interviews
This data collection technique is commonly used in informal surveys and typically involves a relatively small and non-random sample.
It is used to gain information from an individual or a small group, using a series of broad questions to guide the conversations, but allowing for new questions to arise as a result of the discussion

## Slide 21
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
Key informant interviews
Key informants can be an important source of information for project M&E.
Questioning is generally semi-structured and open-ended but can make use of structured close-ended questionnaires.
Key informants will be a small and purposively selected sample, chosen because of their particular knowledge and position.
The selection of informants should adequately represent possibly diverse viewpoints and concerns, and should be sensitive to gender or other sources of bias
Community meetings take the form of public meetings with a larger group. When used for the purpose of gathering project M&E information, they should be based on an interview guide or checklist and facilitated by an interdisciplinary team rather than a single interviewer.

## Slide 22
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
Focus group interviews
Discussion with selected groups that are familiar with pertinent issues is another technique that can be used to explore issues and processes, and to clarify details and gather opinions, before designing a formal and structured survey.
Focus groups are particularly useful for assessing opinions of change and the causes of change, and the quality of project services, and for identifying areas that need improvement.

## Slide 23
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
Key informant interviews
Key informants can be an important source of information for project M&E.
Questioning is generally semi-structured and open-ended but can make use of structured close-ended questionnaires.
Key informants will be a small and purposively selected sample, chosen because of their particular knowledge and position.
The selection of informants should adequately represent possibly diverse viewpoints and concerns, and should be sensitive to gender or other sources of bias

## Slide 24
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
Rapid Appraisal (RA)
RRA can be described as a systematic but semi-structured research activity carried out by a multidisciplinary team over a relatively short period of time.
It can involve a range of informal data collection techniques such as semi-structured interviews, transect walks, mapping, and wealth and matrix ranking.
It can be used as part of the project M&E system, either at appraisal to gather baseline information and help improve project design.

## Slide 25
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
Participatory Appraisal (PA)
PA uses a similar array of data collection methods to RRA but places greater emphasis on the participation of local people in identifying the issues to be investigated and in the collection and analysis of data.
Such approaches should be integral to participatory approaches to project management and implementation.

## Slide 26
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
Direct observation
This method involves structured observation of an activity, behaviour, relationship, phenomenon, network, or process in the field.
It can be used to understand the context in which M&E data are collected, and help explain M&E results.
Phenomena and processes can be studied in their natural setting and a holistic understanding gained.

## Slide 27
Written documents analysis and review of programme records
This method involves reviewing project documents and records such as administrative databases, training materials, correspondence and routine progress reports.
It can be very useful in identifying issues to investigate further and provide evidence of action, change, and impact, to support respondents’ perceptions.
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS

## Slide 28
(4)Where applicable, building on data collection with an evaluation framework and methodology capable of establishing causation (attribution).
As a continuously available mode of analysis for project managers ongoing evaluation can be used to address the following key questions:
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS

## Slide 29
Is the response of the targeted populations as anticipated and satisfactory?
What are the effects of the project on agricultural and other rural products?
Are there any unanticipated effects, positive or negative, for the project or in relation to its wider environment?
Can the causes of all observed changes be discerned and established with evidence?
Does the logic of the intervention model of the project remain valid (ie is it the right design)?
Are any ad hoc special or diagnostic studies needed to help answer any of these questions?
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS

## Slide 30
Experimental designs (randomisation)
These are considered the most robust of the evaluation methodologies and require a randomised selection of the target population as part of the project design.
A random selection into treatment and control groups is made within a defined area and population.
There is no difference between the two groups besides the fact that the treatment group have access to or are influenced by the project or programme
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS

## Slide 31
Non-experimental or quasi-experimental designs
These techniques generate comparison groups that resemble the treatment group, at least in observed characteristics, through use of econometric methods.
Their main benefits are that they can draw on existing data sources and can be performed after a project has been implemented.
Their principal disadvantages are that the reliability of the results is often reduced as the methodology is less robust statistically and the methods required can be statistically complex.
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS

## Slide 32
Qualitative methods
These techniques often provide critical insights into beneficiaries’ perspectives, the value of programs to beneficiaries, the processes that may have affected outcomes and a deeper interpretation of results observed using quantitative analysis.
Because measuring the counterfactual is at the core of impact analysis techniques, qualitative designs have generally been used in conjunction with other evaluation techniques.
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS

## Slide 33
Integrating quantitative and qualitative methods
Integrating quantitative and qualitative evaluations can often be the best approach to meet a project's information needs.
In combining the two approaches, qualitative methods can be used to inform the key impact evaluation questions, improve the questionnaire or the stratification of the quantitative sample, and analyse the social,economic, and political context within which a project takes place,
Quantitative methods can be used to inform qualitative data collection strategies, to inform on the extent to which the results observed in the qualitative work can be generalised to a larger population.
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS

## Slide 34
(5) Clear mechanisms for reporting and use of M&E results in decision- making.
A good flow of information is also closely linked to the development of accountability within the project, sector, government, and donor.
The highest payoffs to evaluation arise at the policy and programme level, but project-level evaluation offers an easier and less sensitive starting point in many instances.
Information from monitoring and evaluation can be used to demonstrate accountability and to promote knowledge transfers and adaptive learning in government agencies and other organisations.
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS

## Slide 35
Lecture 2
(6)Sustainable organisational arrangements for data collection, management, analysis and reporting.
In terms of organisational arrangements there is no single correct way to build a project M&E system.
Projects vary in their characteristics and requirements, and countries and organisations are at different stages of development with respect to good public management practices in general, and M&E in particular. It is also important to recognise that M&E systems are continuous works in progress that must be flexible and adaptable to changing needs and circumstances.
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS

## Slide 36
Logical framework analysis indicates that project management will need to develop systems to provide information at all levels, from basic operational inventories and accounting through to generation of statistics about outcomes and impact.
Building on the concept of a structured set of indicators, the table bellow shows the typical nature and location of responsibility for M&E components at each level.
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS

## Slide 37
Organisation of project monitoring and evaluation
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
Objectives | Indicators | M&Ecomponents | ResponsibilityforM&E
Goal | Impact | Longtermstatistical evidence of project impact Exogenous indicators for risk factors and unanticipated wider environmental and social impacts | National or sectoral agencies and/or independent specialists
Purpose | Outcomes | Socioeconomic surveys M&E of leading indicators Diagnostic studies | Project management and/or independent specialists
Outputs | Output | MIS for physical and financial monitoring M&E components | Project staff
Activities | Process |  | 
Inputs | Input |  | 

## Slide 38
Lecture 2
  3.3- Participatory project monitoring and evaluation
It has been recognised that there is an increased need to engage in direct dialogue with stakeholders involved in development projects..
One critical dimension of this engagement is to involve stakeholders in the monitoring and evaluation of project activities, outputs and outcomes.
Participatory monitoring and evaluation is a process of collaborative problem-solving through the generation and use of knowledge, and through corrective action based on shared decision-making involving all stakeholders. Its key principles are:
    local people are active participants – not just sources of information
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS

## Slide 39
Lecture 2
  3.4-Learning and M&E systems
Learning and ‘lesson learning’ have become common parlance in development. So why is this and what exactly do we mean by ‘learning’?
Models of experiential learning typically comprise four dimensions of learning: having an experience; reflecting on that experience; conceptualising from the experience; and then testing out new ideas/concepts which lead to a new experience
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS

## Slide 40
Lecture 2
  CARE and reflective practice
Having asked a question that begs an answer, and designed a plan for collecting that information, staff need to reflect on their experiences and ask such questions as:
  What were the anticipated effects?
  Were there some unanticipated effects?
  What have we learned from this?
  What might we have to relearn or unlearn in our work?
  What are our next steps?
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS

## Slide 41
Understanding and designing project monitoring and evaluation systems can be informed by the concepts and method of logical framework analysis. This provides the means to structure indicators and the organisation of all monitoring and evaluation activities. The steps involved in planning and implementation of a project M&E system are relatively straightforward, but the challenges arise in determination of the right balance of approaches and methods to be used.
Lecture 2
Session Summary 1/2

## Slide 42
Lecture 2
Session Summary 1/2
The approaches for data collection, evaluation and reporting that are selected must be well tailored to a project’s characteristics and to local conditions and capacities. It is important to understand monitoring and evaluation as an essential part of good management, and one that requires acceptance of the notion of learning and of the creation of a learning environment.

## Slide 43
Lecture 2