## Slide 1: Project Feasibility Study Lecture 4
PMG201
THE WORLD OF PROJECT MANAGEMENT
Everyone’s Smart University

## Slide 2: LEARNING OUTCOMES
What Is a Project?
Project Management vs. General Management
What Is Managed? The Three Goals of a Project
The Life Cycles of Projects
Selecting Projects to Meet Organizational Objectives
Confronting Uncertainty—the Management of Risk
The Project Portfolio Process

## Slide 3: What Is a Project?
Project, Defined
At first A project is an endeavor to accomplish a specific objective through a unique set of interrelated tasks and the effective utilization of resources.

## Slide 4: Project, Defined
A secondary effect of using multidisciplinary teams to deal with complex problems is conflict. Projects are characterized by conflict. As we will see in later chapters, the project schedule, budget, and specifications conflict with each other.

## Slide 5: Project, Defined
The needs and desires of the client conflict with those of the project team, the senior management of the organization conducting the project and others who may have a less direct stake in the project. Some of the most intense conflicts are those between members of the project team.

## Slide 6: Project, Defined
Much more will be said about this in later chapters. For the moment, it is sufficient to recognize that projects and conflict are inseparable companions, an environment that is unsuitable and uncomfortable for conflict avoiders.

## Slide 7: Project, Defined
Finally, it is appropriate to ask, “ Why projects? ” The reason is simple. We form projects in order to fi x the responsibility and authority for the achievement of an organizational goal on an individual or small group when the job does not clearly fall within the definition of routine work.

## Slide 8: Attributes of a Project
6
Has a well-defined objective
Composed of a series of interdependent tasks
Utilizes various resources
Has a specific time frame
Has a customer
Involves a degree of uncertainty
Notes: 6
6
6
6
6
6
8
8
8

## Slide 9: Constraints
8
Scope
Cost
Schedule
Customer satisfaction
Notes: 8
8
8
8
8
8
11
11
11

## Slide 10: Unforeseen Circumstances
9
Unforeseen circumstances may jeopardize achievement of the project objective.
The challenge facing the project manager is to prevent, anticipate, and/or overcome such circumstances.
Notes: 9
9
9
9
9
9
14
14
14

## Slide 11: The Project Management Process
15
The project management process means planning the work and then working the plan.
Notes: 15
15
15
15
15
15
21
21
21

## Slide 12: The Project Management Process (Cont.)
16
Clearly define the project objective.
Divide and subdivide the project.
Define the specific activities that need to be performed.
Graphically portray the activities in a network diagram.
Notes: 16
16
16
16
16
16
22
22
22

## Slide 13: The Project Management Process (Cont.)
17
Make a time estimate.
Make a cost estimate.
Calculate a project schedule and budget.
Notes: 17
17
17
17
17
17
24
24
24

## Slide 14: Controlling Projects
18
Establish a baseline plan.
Monitor progress.
Measure actual progress and compare it to planned progress.
Take corrective action if the project is behind schedule, overrunning the budget, or not meeting technical specifications.
Notes: 18
18
18
18
18
18
25
25
25

## Slide 15: Benefits of Project Management
19
Satisfied customers
Additional business
Expansion of career opportunities
Satisfaction of being on a winning team
Improved knowledge and skills
When projects are successful, everybody WINS
Notes: 19
19
19
19
19
19
28
28
28

## Slide 16: Trends in Project Management
Many recent developments in project management are being driven by quickly changing global markets, technology, and education.
Global competition is putting pressure on prices, response times, and product/service innovation. Computer and telecommunication technology, along with rapidly expanding higher education across the world allows the use of project management for types of projects and in regions where these sophisticated tools had never been considered before.

## Slide 17: Trends in Project Management
Achieving Strategic Goals
Achieving Routine Goals
Improving Project Effectiveness
Virtual Projects
Quasi - Projects

## Slide 18: Trends in Project Management
A project, then, is a temporary endeavor undertaken to create a unique product or service. It is specific, timely, usually multidisciplinary, and always conflict ridden. Projects are parts of overall programs and may be broken down into tasks, subtasks, and further if desired. Current trends in project management are noted.

## Slide 19: PROJECT MANAGEMENT VS. GENERAL MANAGEMENT
Project management differs from general management largely because projects differ from what we have referred to as “ non projects. ” The naturally high level of conflict present in projects means that the project manager (PM) must have special skills in conflict resolution.

## Slide 20: PROJECT MANAGEMENT VS. GENERAL MANAGEMENT
The fact that projects are unique means that the PM must be creative and flexible, and have the ability to adjust rapidly to changes. When managing no projects, the general manager tries to “ manage by exception. ” In other words, for non projects almost everything is routine and is handled routinely by subordinates. The manager deals only with the exceptions. For the PM, almost everything is an exception.

## Slide 21: Major Differences
1- Project management differs greatly from general management. Every project is planned, budgeted, scheduled, and controlled as a unique task. Unlike non projects, projects are often multidisciplinary and usually have considerable need to cross departmental boundaries for technology, information, resources, and personnel. Crossing these boundaries tends to lead to intergroup conflict. The development of a detailed project plan based on the scope and due date of the project is critical to the project ’ s success.

## Slide 22: Major Differences
2- Unlike their general management counterparts, project managers have responsibility for accomplishing a project, but little or no legitimate authority to command the required resources from the functional departments. The PM must be skilled at win - win negotiation to obtain these resources.

## Slide 23: WHAT IS MANAGED? THE THREE GOALS OF A PROJECT
The performance of a project is measured by three criteria. Is the project on time or early? Is the project on or under budget? Does the project deliver the agreed - upon outputs to the satisfaction of the customer? Figure 1-1 shows the three goals of a project. The performance of the project and the PM is measured by the degree to which these goals are achieved.

## Slide 24
One of these goals, scope, is set primarily by the client (although the client agrees to all three when contracting for the project). It is the client who must decide what capabilities are required of the project ’ s deliverables — and this is what makes the project unique. Some writers insist that “ quality ” is a separate and distinct goal of the project along with time, cost, and scope. We do not agree because we consider quality an inherent part of the project specifications. If we did not live in an uncertain world in which

## Slide 25: The Project Life Cycle
There are two different paths (life cycles) along which projects progress from start to completion. One is S - shaped and the other is J - shaped. It is an important distinction because identifying the different life cycles helps the PM to focus attention on appropriate matters to ensure successful project completion.

## Slide 26: The Project Life Cycle
10
Projects are “born” when a need is identified by the customer.
Project life cycles vary in length, from a few weeks to several years.
Not all projects formally go through all four phases of the project life cycle.
Notes: 10
10
10
10
10
10
16
16
16

## Slide 27: Phases of the Project Life Cycle 1
11
The first phase involves the identification of a need, problem, or opportunity.
  The need and requirements are usually written by the customer into a document called a request for proposal (RFP).
Notes: 11
11
11
11
11
11
17
17
17

## Slide 28: Phases of the Project Life Cycle 2
The second phase is the development of a proposed solution to the need or problem.
  This phase results in the submission of a proposal.
  The customer and the winning contractor negotiate and sign a contract (agreement).
12
Notes: 12
12
12
12
12
12
18
18
18

## Slide 29: Phases of the Project Life Cycle 3
13
The third phase is performing the project.
  Different types of resources are utilized
  Results in the accomplishment of the project objective
Notes: 13
13
13
13
13
13
19
19
19

## Slide 30: Phases of the Project Life Cycle 4
14
The final phase is terminating the project.
  Perform close-out activities
  Evaluate performance
  Invite customer feedback
Notes: 14
14
14
14
14
14
20
20
20

## Slide 31: SELECTING PROJECTS TO MEET ORGANIZATIONAL OBJECTIVES
The accomplishment of important tasks and goals in organizations today is being achieved increasingly through the use of projects. A new kind of organization has emerged recently to deal with the accelerating growth in the number of multiple, simultaneously ongoing, and often interrelated projects in organizations.

## Slide 32: methods for selecting projects
There are many different methods for selecting projects, but they may be grouped into two fundamental types, nonnumeric and numeric.
Nonnumeric Selection Methods
Numeric Selection Methods

## Slide 33: Nonnumeric Selection Methods
The Sacred Cow
The Operating/Competitive Necessity
Comparative Benefits

## Slide 34: 2- Numeric Selection Methods
Financial Assessment Methods
Financial Options and Opportunity Costs
Scoring Methods

## Slide 35: CONFRONTING UNCERTAINTY — THE MANAGEMENT OF RISK
As we note throughout this book, projects are all about uncertainty, and effective project management requires an ability to deal with uncertainty.
The time required to complete a project, the availability and costs of key resources, the timing of solutions to technological problems, a wide variety of macroeconomic variables, the whims of a client, the actions taken by competitors, even the likelihood that the output of a project will perform as expected,

## Slide 36
all these exemplify the uncertainties encountered when managing projects. While there are actions that may be taken to reduce the uncertainty, no actions of a PM can ever eliminate it.
Considering Uncertainty in Project Selection Decisions
Considering Disaster

## Slide 37: THE PROJECT PORTFOLIO PROCESS
The Project Portfolio Process (PPP) attempts to link the organization ’ s projects directly to the goals and strategy of the organization. This occurs not only in the project ’ s initiation and planning phases, but also throughout the life cycle of the projects as they are managed and eventually brought to completion.
Thus, the PPP is also a means for monitoring and controlling the organization ’ s strategic projects,

## Slide 38: THE PROJECT PORTFOLIO PROCESS
Step 1: Establish a Project Council
Step 2: Identify Project Categories and Criteria
Step 3: Collect Project Data
Step 4: Assess Resource Availability
Step 5: Reduce the Project and Criteria Set
Step 6: Prioritize the Projects within Categories
Step 7: Select the Projects to Be Funded and Held in Reserve
Step 8: Implement the Process

## Slide 39: THE PROJECT PORTFOLIO PROCESS
Projects are often subdivisions of major programs. Long - run success is determined by the organization ’ s portfolio of projects. Classified by the extent of innovation in product and process, there are four types of projects:

## Slide 40: THE PROJECT PORTFOLIO PROCESS
derivative, breakthrough, platform, and R & D projects. The actual mix of projects is a direct expression of the organization ’ s competitive strategy. A proper mix of project categories can help ensure its long - run competitive position. It is important for the Project Council or PMO to preplan project portfolio adjustments to respond to significant changes in the state of competition and other industrial crises.