## Slide 1: PMG 622 Agile Project Management LECTURE 05: IMPLEMENTING AGILE: DELIVERING IN AN AGILE ENVIRONMENT [Part 2 of 2]
Everyone’s Smart University
دكتور مهندس استشاري ادارة المشروعات
Eng. Dr. Akram Mustafa Suliman Ali,
PhD. AU, BEng. & MSc. AAST, CEng CMarEng MIMarEST, PE, PMP®,
ASQ CSSBB, ISO Lead Auditor, NDT Level II,

## Slide 2: Quick Review and Introduction

## Slide 3: Scrum roles, artifacts & ceremonies
SCRUM ARTIFICATS
  Product Backlog
  Sprint Backlog
  Increment
SCRUM CERMONIES
  Sprint Planning.
  Daily Scrum.
  Sprint Review.
  Sprint Retrospective.
SCRUM ROLES
  Product Owner
  Development Team Members
  Scrum Master
Notes: Product; Increment; Content
Process; Context

## Slide 5: daily stand-up questions
iteration-based agile (TIME-BOXED) SCRUM | flow-based agile (INCREMENT) KANBAN
What did I complete since the last standup? | What do we need to do to advance this piece of work?
What am I planning to complete between now and the next standup? | Is anyone working on anything that is not on the board?
What are my impediments (or risks or problems)? | What do we need to finish as a team?
 | Are there any bottlenecks or blockers to the flow of work?

## Slide 6: TROUBLESHOOTING AGILE PROJECT CHALLENGES

## Slide 7: Agile Pain Points and Troubleshooting Possibilities [1/8]
Pain Point | Troubleshooting Possibilities
Unclear purpose or mission for the team | Agile chartering for purpose–vision, mission, and mission tests
Unclear working agreements for the team | Agile chartering for alignment–values, principles, and working agreements
Unclear team context | Agile chartering for context–boundaries, committed assets, and prospective analysis
Notes: Agile approaches were born out of the need to solve issues associated with
high rates of change, uncertainty, and complexity on projects. Due to these
origins, they contain a variety of tools and techniques for dealing with issues that
present problems in predictive approaches. Refer to

## Slide 8: Agile Pain Points and Troubleshooting Possibilities [2/8]
Pain Point | Troubleshooting Possibilities
Unclear requirements | Help sponsors and stakeholders craft a product vision. Consider building a product roadmap using specification by example, user story mapping, and impact mapping. Bring the team and product owner together to clarify the expectations and value of a requirement. Progressively decompose roadmap into backlog of smaller, concrete requirements.
Poor user experience | User experience design practices included in the development team involve users early and often.
Notes: Agile approaches were born out of the need to solve issues associated with
high rates of change, uncertainty, and complexity on projects. Due to these
origins, they contain a variety of tools and techniques for dealing with issues that
present problems in predictive approaches. Refer to

## Slide 9: Agile Pain Points and Troubleshooting Possibilities [3/8]
Pain Point | Troubleshooting Possibilities
Inaccurate estimation | Reduce story size by splitting stories. Use relative estimation with the entire team to estimate. Consider agile modeling or spiking to understand what the story is.
Unclear work assignments or work progress | Help the team learn that they self-manage their work. Consider kanban boards to see the flow of work. Consider a daily standup to walk the board and see what work is where.

## Slide 10: Agile Pain Points and Troubleshooting Possibilities [4/8]
Pain Point | Troubleshooting Possibilities
Team struggles with obstacles | A servant leader can help clear these obstacles. If the team doesn't know the options they have, consider a coach. Sometimes, the team needs to escalate stories the team or servant leader has not been able to remove.
Work delays/overruns due to Insufficiently refined product backlog items | Product owner and team workshop stories together. Create a definition of ready for the stories. Consider splitting stories to use smaller stories
Defects | Consider the technical practices that work for the environment. Some possibilities are: pair work, collective product ownership, pervasive testing (test-driven and automated testing approaches) and a robust definition of done.

## Slide 11: Agile Pain Points and Troubleshooting Possibilities [5/8]
Pain Point | Troubleshooting Possibilities
Work is not complete | Team defines definition of done for stories including acceptance criteria. Also add release criteria for projects.
Technical debt (degraded code quality) | Refactoring, agile modeling, pervasive testing, automated code quality analysis, definition of Done
Slow or no improvement in the teamwork process | Capture no more than three items to improve at each retrospective. Ask the servant leader to help the team learn how to integrate those items.

## Slide 12: Agile Pain Points and Troubleshooting Possibilities [6/8]
Pain Point | Troubleshooting Possibilities
Too much product complexity | For software and non-software encourage the team always to be thinking “What is the simplest thing that would work?” and apply the agile principle of “Simplicity--the art of maximizing the amount of work not done”. These help reduce complexity.
Too much upfront work leading to rework | Instead of much upfront work, consider team spikes to learn. In addition, measure the WIP during the beginning of the project and see what the team's options are to deliver value instead of designs. Shorten iterations and create a robust definition of done.

## Slide 13: Agile Pain Points and Troubleshooting Possibilities [7/8]
Pain Point | Troubleshooting Possibilities
False starts, wasted efforts | Ask the product owner to become an integral part of the team.
Inefficiently ordered product backlog items | Rank with value including cost of delay divided by duration and other value models
Rush/wait uneven flow of work | Plan to the team's capacity and not more. Ask people to stop multitasking and be dedicated to one team. Ask the team to work as pairs, a swarm, or mob to even out the capabilities across the entire team.

## Slide 14: Agile Pain Points and Troubleshooting Possibilities [8/8]
Pain Point | Troubleshooting Possibilities
Impossible stakeholder demands | Servant leadership to work with this stakeholder (and possibly product owner).
Unexpected or unforeseen delays | Ask the team to check in more often, use Kanban boards to see the flow of work and work in progress limits to understand the impact of the demands on the team or product. Also track impediments and impediment removal on an impediment board.
Siloed teams, instead of cross-functional teams | Ask the people who are part of projects to selforganize as cross-functional teams. Use servant leadership skills to help the managers understand why agile needs cross-functional teams.

## Slide 15: MEASUREMENTS IN AGILE PROJECTS

## Slide 16: Transitioning to agile
Using different measurements
Looking at new metrics that matter to the team and to management
These metrics matter because they focus on customer value

## Slide 17: AGILE TEAMS MEASURE RESULTS
Agile favors empirical and value-based measurements instead of predictive measurements.
Agile measures what the team delivers, not what the team predicts it will deliver.
Agile is based on working products of demonstrable value to customers and not managing to a baseline
Notes: there is evidence that the smaller the chunk of work, the more likely people are to deliver it.
As an example, if the team averages 50 story points per iteration, and the
team estimates there are about another 500 points remaining, the team
estimates it has about 10 iterations remaining. As the product owner refines
the stories remaining and as the team refines its estimates, the project estimate
could go up or down, but the team can provide an estimate.

## Slide 18: Agile duration prediction
Once the team establishes a reliable velocity (average stories or story points per iteration) or the average cycle time, the team can predict how much longer the project will take
Teams might discover it can take four to eight iterations to achieve a stable velocity. The teams need the feedback from each iteration to learn about how they work and how to improve.

## Slide 19: Velocity,
The sum of the story point sizes for the features actually completed in this iteration, allows the team to plan its next capacity more accurately by looking at its historical performance.

## Slide 20: Sprint burndown charts

## Slide 21: Sprint Burnup charts

## Slide 22: Burndown and burnup charts
Burndowns show the effect of team members multitasking, stories that are too large, or team members out of the office.
Especially with teams new to agile, the burnup will show changes in scope during the iteration. Burnups allow teams to see what they have accomplished, which helps the team proceed to the next piece of work.

## Slide 23: Flow-based agile teams measurements:
Lead time (the total time it takes to deliver an item, measured from the time it is added to the board to the moment it is completed)
Cycle time (the time required to process an item)
Response time (the time that an item waits until work starts)
Teams measure cycle time to see bottlenecks and delays, not necessarily inside the team.

## Slide 24: tip
When teams depend on external people or groups, measure cycle time to see how long it takes for the team to complete the work.
Measure lead time to see the external dependencies after the team completes its work.
Teams can also measure the reaction time, the time from ready to the first column, to see how long it takes them—on average—to respond to new requests.

## Slide 25
When the team has met its WIP limits, the team cannot pull work from the left into the next column. Instead, the team works from the right-most full column and asks, “What do we do as a team to move this work into the next column?”
Notes: Each feature is unique, so its cycle time is unique. However, a product owner might notice that smaller features have smaller cycle times. The product owner wants to see throughput, so the product owner creates smaller features or works
with the team to do so.

## Slide 26: Capacity measures & predictability measures
Burnups, burndowns (capacity measures) and lead time, and cycle time (predictability measures) are useful for in-the-moment measurements. They help a team understand how much more work they have and whether the team might finish on time.
Measuring story points is not the same as measuring completed stories or features. Some teams attempt to measure story points without completing the actual feature or story. When teams measure only story points, they measure capacity, not finished work, which violates the principle of “the primary measure of progress is working software” (or, other product if not software).
Each team has its own capacity. When a team uses story points, be aware that the number of story points a team can complete in a given time is unique to that team.
When teams provide their own units of measure, teams are better able to assess and estimate and deliver their work.

## Slide 27: The downside of relative estimation
There is no way to compare teams or add velocity across teams

## Slide 28: feature burnup/burndown chart
These charts provide trends of completion over time
Show that requirements grew during the project.
The features complete line shows that the team completes features at a regular pace.
The total features line shows how the project's total features changed over time.
The features remaining burndown line shows that the rate of feature completion varies.
Every time features are added to the project, the burndown line changes.

## Slide 30: PRODUCT BACKLOG BURNUP CHART
Earned value in agile is based on finished features
The product backlog burnup chart shows completed work compared to total expected work at interval milestones or iterations.
A team can only finish one story at a time.
To complete a large feature that contains several stories, the team will have remaining stories to complete and may not complete that entire feature until several more time periods have passed.
The team can show its completed value with a product backlog burnup chart

## Slide 32: EARNED VALUE IN AN AGILE CONTEXT
Traditional EVM metrics like schedule performance index (SPI) and cost performance index (CPI) can be easily translated into agile terms.
For example, if the team planned to complete 30 story points in an iteration, but only completed 25 then the SPI is 25/30 or 0.83 (the team is working at only 83% of the rate planned).
Likewise, CPI is the earned value (completed features value) to date divided by the actual costs to date or, as shown in Figure, $2.2M /
$2.8M = 0.79. This means a result of only 79 cents on the dollar compared to plan