## Slide 1
Project Time Management
Lecture 9
PMG 212
www.midocean.ae
Prepared by Dr. Nael Yousry
Presented by Dr. Amira Elfekky

## Slide 2
Prepared by Dr. Nael Yousry
Project Time Management
Lecture 9
PMG 212
Presented by Dr. Amira Elfekky

## Slide 3
Agenda
Acceleration and Schedule Compression
Case study
Case study – Create WBS
Case study – Create activity
Case study – Scheduling
Project duration versus cost
Acceleration and Schedule Compression
www.midocean.ae
09
Chapter

## Slide 4
Agenda
Acceleration and Schedule Compression
Case study
Case study – Create WBS
Case study – Create activity
Case study – Scheduling
Project duration versus cost
Acceleration and Schedule Compression
www.midocean.ae
09
Chapter

## Slide 5
Case study
Road Network
A
B
C
D
1
1
3
2
1
3
2
4
3
2
3
2
1
www.midocean.ae
09
Chapter

## Slide 6
Agenda
Acceleration and Schedule Compression
Case study
Case study – Create WBS
Case study – Create activity
Case study – Scheduling
Project duration versus cost
Acceleration and Schedule Compression
www.midocean.ae
09
Chapter

## Slide 7
Case study – Create WBS
www.midocean.ae
09
Chapter

## Slide 8
Case study – Create WBS
Click
www.midocean.ae
09
Chapter

## Slide 9
Case study – Create WBS
www.midocean.ae
09
Chapter

## Slide 10
Agenda
Acceleration and Schedule Compression
Case study
Case study – Create WBS
Case study – Create activity
Case study – Scheduling
Project duration versus cost
Acceleration and Schedule Compression
www.midocean.ae
09
Chapter

## Slide 11
Case study – Create activity code
Activity | Code
Excavation | EX
Replacement | RE
Ferma Layer | FR
Base Layer | BA
Prime Coat | PR
Layer Bond | LB
Tack Coat | TA
Asphalt Layer | AS
Curbs | CU
Sign Traffic | ST
Draw Axis | DR
Pavement Layer | PV
www.midocean.ae
09
Chapter

## Slide 12
Agenda
Acceleration and Schedule Compression
Case study
Case study – Create WBS
Case study – Create activity
Case study – Scheduling
Project duration versus cost
Acceleration and Schedule Compression
www.midocean.ae
09
Chapter

## Slide 13
Case study – Create activity
www.midocean.ae
09
Chapter

## Slide 14
Case study – Create activity
www.midocean.ae
09
Chapter

## Slide 15
Case study – Create activity
www.midocean.ae
09
Chapter

## Slide 16
Agenda
Acceleration and Schedule Compression
Case study
Case study – Create WBS
Case study – Create activity
Case study – Scheduling
Project duration versus cost
Acceleration and Schedule Compression
www.midocean.ae
09
Chapter

## Slide 17
Case study – Scheduling
www.midocean.ae
09
Chapter

## Slide 18
Agenda
Acceleration and Schedule Compression
Case study
Case study – Create WBS
Case study – Create activity
Case study – Scheduling
Project duration versus cost
Acceleration and Schedule Compression
www.midocean.ae
09
Chapter

## Slide 19
Project duration versus cost
www.midocean.ae
09
Chapter

## Slide 20
Agenda
Acceleration and Schedule Compression
Case study
Case study – Create WBS
Case study – Create activity
Case study – Scheduling
Project duration versus cost
Acceleration and Schedule Compression
www.midocean.ae
09
Chapter

## Slide 21
Acceleration and Schedule Compression
Construction projects always have delivery dates. Some are dictated by the owner, and some are dictated by the contractor.
Most delivery dates are contractual.
There are a multitude of reasons, but the most prominent one is that a project needs a delivery date for control.
Without a delivery date, there is no goal and human nature’s proclivity toward procrastination takes over.
www.midocean.ae
09
Chapter

## Slide 22
Acceleration
Delivering on time or ahead of schedule is important for all parties, from subcontractors all the way up to the owner.
Finishing within or under budget is another important goal.
The real achievement, however, is doing both simultaneously. Unfortunately, this may not always be possible.
www.midocean.ae
09
Chapter

## Slide 23
Acceleration
At the point where an accelerated pace of the work is diagnosed as the cure
for delay, the project manager may have to make the decision to spend money.
Acceleration is defined as the addition of resources or work hours to a task
or project.
Acceleration results in schedule compression or reducing the duration of the task or shortening the entire project without diminishing the scope of the
project.
www.midocean.ae
09
Chapter

## Slide 24
Acceleration
The acceleration must be applied to the critical path or a critical task.
To accelerate a noncritical task rarely benefits the schedule.
There are three different types of acceleration that the average project may potentially encounter.
Acceleration is issued in the form of written direction from the owner to the contractor and can be classified in three categories: actual, constructive, and forced.
www.midocean.ae
09
Chapter

## Slide 25
Actual Acceleration
Actual acceleration is the directive to complete the project ahead of the accepted or contractual schedule.
This directive comes from the owner to the contractor through the architect, and is then passed on to the subcontractors.
www.midocean.ae
09
Chapter

## Slide 26
Constructive Acceleration
Constructive acceleration occurs when the contractor requests an extension of time and is denied.
If the delay that resulted in the request for an extension of time is an excusable delay, the extension should be granted.
www.midocean.ae
09
Chapter

## Slide 27
Constructive Acceleration
Constructive acceleration exists when the following conditions occur:
  ● There is an excusable delay to the project.
  ● The contractor requests a justifiable extension of time for the excusable delay.
  ● The request for an extension is denied.
www.midocean.ae
09
Chapter

## Slide 28
Constructive Acceleration
Constructive acceleration exists when the following conditions occur:
  ● The contractor is directed to achieve the original completion date.
  ● The contractor actually accelerates the work to meet the original date.
  ● The contractor incurs additional costs for acceleration.
www.midocean.ae
09
Chapter

## Slide 29
Forced Acceleration
There is also a need for acceleration when delay occurs as a result of nonperformance.
This type of acceleration is sometimes referred to as forced acceleration.
This occurs frequently when a subcontractor on the critical path is falling behind.
While this is not acceleration in the truest sense of the definition, it does require an increase in production.
www.midocean.ae
09
Chapter

## Slide 30
Schedule Compression
The decision to accelerate work and incur costs must have a tangible benefit to the project.
Schedule compression is not always about the shortest duration of the task.
It is more about the balance of getting the shortest duration for the least
cost.
www.midocean.ae
09
Chapter

## Slide 31
Schedule Compression
Schedule compression is generally defined as modifying the plan and/or schedule to complete critical tasks or the project early.
Schedule compression is the resequencing or rescheduling of tasks with minimal or no cost impact.
www.midocean.ae
09
Chapter

## Slide 32
Thank You